## Title
<Project Name>
| Apple Silicon Checklist | Instructions:
The checklist is generic and intended to cover all categories of chips.
If a particular item is not applicable, please put a NA instead of the date - with a comment in the Comments column describing why it is a NA.
Please do NOT: grey-out any items/cells OR un-grey any greyed out cells without Apple approval. No Alterations or Deletions are allowed.
Most items have a comment associated with it, explaining what is expected and when. Please follow it meticulously.
1. All the items which are not greyed out and are marked with MMDDYY need to be reviewed in the respective reviews - Kick-off and/or Mid-Term and/or Final.
The MMDDYY is to be replaced by actual date of the review of the item.
2. The items which are due to be reviewed at the Kiick-off - should be presented at the Kick-off. They are clearly indicated in the Kick-off Review Column.
If any item is not ready in time for the kick-off meeting, an estimated date of delivery as close as possible should be provided.
| Version 2.9 | The dates for the Mid-Term (MDR) and Final (FDR) Design Reviews should be chalked out during the Kick-off and entered into the appropriate columns.
| 2017-10-16 | 3. Some items that are due during the MDR are clearly indicated in the Mid-Term Review column. The purpose of this review is to make sure project is on track.
Reviewing all the items marked for this review and taking required corrective actions will make the FDR easier.
Apple Confidential
4. The items indicated in Final review column are to be reviewed during the FDR.
Some items, which are dependant on final reports, may have to be reviewed between the FDR and the actual tapeout.
A checklist review should be included in the agenda of the FDR, and the status of items which have been reviewed to satisfaction should be changed from OPEN to CLOSED after approval from Apple.
All the items which are not NA shall be CLOSED before a tapeout approval is requested.
The table of DRI below should be completely filled out before the Kick-off of the project. ( Please see below for the defintion and expection of a DRI )
Key members | DRI | Contact Information (email and cell phone number) | Tab | DRI for the Tab | Contact Information (email and cell phone number)
Director | Amin Shokrollahi | amin@kandou.com, +41 (0)79 570 21 41 | "Project" | Chris Hall | hall@kandou.com, '+44 7921 473842
Project Manager | Anant Singh | anant@kandou.com, +44 7462 754 245 | "Block Risk Analysis" | Anant Singh | anant@kandou.com, +44 7462 754 245
Program Manager | Chris Hall | hall@kandou.com, '+44 7921 473842 | "Design Verification" | Anton Tschank | anton@kandou.com
Chip Lead | David Stauffer | david@kandou.com, +1 802 316 0808 | "Analog" | Kiarash Gharibdoust | kiarash@kandou.com
SerDes IP Lead | Kiarash Gharibdoust / Klaas Hofstra | kiarash@kandou.com / Klaas@kandou.com | Digital" | David Stauffer | david@kandou.com, +1 802 316 0808
Analog Layout and SerDes IP Integration Lead | Ivaylo Avramov | avramov@kandou.com | "A-D Contract" | Kiarash Gharibdoust / Klaas Hofstra | kiarash@kandou.com / Klaas@kandou.com
ESD Lead | Kiarash Gharibdoust | kiarash@kandou.com | "ESD & LUP" | Kiarash Gharibdoust | kiarash@kandou.com
Digital Lead | David Stauffer | david@kandou.com, +1 802 316 0808 | "Analog layout" | Ivaylo Avramov | avramov@kandou.com
Digital PnR Lead | Karsten Thuener | thuener@kandou.com | "Die fact sheet" | Chris Hall | hall@kandou.com, '+44 7921 473842
Top level / Integration Lead | Karsten Thuener | thuener@kandou.com | "Physical Design" "PnR visual Review" | Karsten Thuener | thuener@kandou.com
DV / AMS Lead | Anton Tschank | anton@kandou.com | "Packaging" | John Philips | phillips@kandou.com
Product Engineering Lead | Subhash C. Roy | subhash@kandou.com, +1 (781) 363-3555 | "Process" | Anant Singh / Frank Lavety | anant@kandou.com, +44 7462 754 245, lavety@kandou.com
Qualification Lead | Frank Lavety | lavety@kandou.com | "Qualification" | Frank Lavety | lavety@kandou.com
Package Lead | John Philips | phillips@kandou.com | "PTE" | Frank Lavety | lavety@kandou.com
Process Technology Lead | Anant Singh | anant@kandou.com, +44 7462 754 245 | "Additional Requests"
Test Engineering Lead | Frank Lavety | lavety@kandou.com | "ECO Update"
Other |  |  | "SCM Template"
Defintion of a DRI: Directly Responsible Individual .
Expectations of a DRI include, but are not limited to:
* Directly Responsible Subject Matter Expert.
* Direct single point of contact for communication with corresponding Apple DRI on the subject matter.
* Individual ability and authority to answer questions, provide accurate information and respond to queries.
* Knowledgeable of the internal organization and where to go / who to contact to get the needed information / resources.
Apple Confidential - Do not duplicate

## Project
[11 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions | JAN'19 F2F | Deliverables | Effort | Risk | Readiness
Silicon Vendor Information | 1.01 | List of all team members with contact information | 2017-12-15 |  |  | OPEN | Chris | List provided on Nov 1, update provided on 12/15/2017
| 1.02 | List all contractors / external design houses? | 2018-07-31 |  |  | OPEN |  | Open Silicon (FPGA validation, post-Silicon), Moortec (temp sensor)
| 1.03 | Vendor design methodology and best practices | 2019-04-25 |  |  | OPEN |  | In progress, presented through different teams methodologies in Dec and Jan F2F, aligning the requirements with OSI.
| 1.04 | List of CAD tools to be used for silicon development | 2017-11-01 |  |  | OPEN |  | List provided in company and methodology presentation on Nov 1, 2017
| 1.05 | Number of tool licenses available for this project | 2018-06-15 |  |  | OPEN |  | Kandou_RT_ConsolidateTools_Compute-Plan_110618.xlsx provided in June F2F.
| 1.06 | Number of servers availble for simulations and regressions | 2018-06-15 |  |  | OPEN |  | Kandou_RT_ConsolidateTools_Compute-Plan_110618.xlsx provided in June F2F.
| 1.07 | Vendor RTL coding guidelines | 2017-11-01 |  |  | OPEN |  | Item provided in company and methodology presentation on Nov 1, 2017
| 1.08 | Vendor Sychronous design practices | MMDDYY |  |  | OPEN |  | ? KB needs more clarification
| 1.09 | Vendor BIST methodology for memories and analog IP | 2018-11-30 |  |  | OPEN |  | Item discussed in Nov 6-8, 2018 F2F.
| 1.1 | Vendor version control system for all IP | MMDDYY |  |  | OPEN
| 1.11 | Vendor design and tape out checklists | 2019-03-25 |  | MMDDYY | OPEN |  | The item will be ready at latest one month prior to TO.
| 1.12 | Manufacturing flow | 2019-03-25 |  |  | OPEN |  | The item will be ready at latest one month prior to TO.
| 1.13 | Qualifcation Plan (HTOL) | 2019-03-25 |  |  | OPEN |  | The item will be ready at latest one month prior to TO.
| 1.14 | Characterication Plan | 2019-03-25 |  |  | OPEN |  | The item will be ready at latest one month prior to TO.
| 1.15 | Package Qualfication Plan |  |  | 2019-03-25 | OPEN |  | The item will be ready at latest one month prior to TO. | (Removed in v3.2, retained for v2.9)
| 1.16 | Silicon Validation Plan |  |  | 2019-03-25 | OPEN |  | The item will be ready at latest one month prior to TO.
| 1.17 | Any other applicable Qualification / Reliablity specs (please list in comments) | MMDDYY |  |  | OPEN |  | N/A
| 1.18 | Qualification Plan Results |  |  | MMDDYY | OPEN |  | An update will be provided prior to TO
Project Design | 2.01 | Engineering requirements specification (ERS or ARD) | MMDDYY |  |  | OPEN
| 2.02 | Silicon datasheet |  | 2018-11-15 | 2019-08-15 | OPEN |  | 3rd date would be after final characterization, thus Dec 2019. Which one should be put here?
| 2.03 | Die Fact Sheet |  |  | 2019-03-25 | OPEN |  | Item will be provided prior to TO
| 2.04 | List of all analog and digital IP along with maturity: new, modified or exisitng | 2018-07-31 |  |  | OPEN |  | Provided in weekly meeting on 6/21/18, Radar AI 35187093. | (Removed in v3.2, retained for v2.9)
| 2.05 | User Guide, Programmers Guide, Theory of Operations, etc. | MMDDYY |  |  | OPEN |  | Could be Bombini software/UG. If yes, available by 15-Nov
| 2.06 | Package Review | MMDDYY |  |  | OPEN |  | The date will be specified once when vendor is selected (at latest Feb 2018). | (Removed in v3.2, retained for v2.9)
| 2.07 | Any "Lessons learnt" from prioir projects incorporated in methodology and/or schedule | MMDDYY |  |  | OPEN |  | Lessons learnt from GW program could be incorporated by CP1.
| 2.08 | Review Specification Compliance Matrix (SCM) | 2018-12-31 |  |  | OPEN
| 2.09 | All "deferred" RADARs and ECOs from previous gen reviewed - if applicable | MMDDYY |  |  | OPEN |  | N/A
NOTE: The following document(s) should be used as master reference documents:
1 | Document 080-00061-<rev> - List of Apple Specifications for Management of Integrated Circuit Components - A Ready reference for all latest specs to be used. [Current rev 080-00061-M]
2 | Spreadsheet 080-00128-<rev>.xlsx - IC Qualification report Template. [Current rev 080-00128-C]
3 | Document 062-0101-<rev> - General Qualification Procedure for Integrated Circuits - Spec for Package Qulaification Plan. [Current rev 062-0101-AB]
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Silicon Vendor Information | 1.13 | Qualifcation Plan per 062-0101 and 080-00128 (v3.2/1,13) | 2019-03-25 |  |  | OPEN |  | The item will be ready at latest one month prior to TO. KB is using document revisons 062-0101-AC and and 080-00128-D
Note on C3: Title, Email address, office phone number and cell phone numbers of all members working on project To be filled in on the title page also. Please state the role/tasks/division of labor for each.
Note on C4: If Yes, please work with the PM to get special clearances and approvals. If any are added at any time during the project please notify the Apple PM immediately.
Note on C5: - If an existing design methodology and best practices document exists, that should be shared with Apple. - indicate which sections from the document will be applicable to the flow and methodology in the current project. - indicate which section from the document will be used with an altered flow. - If a document does not exist then one answering the metholodology related questions from each tab should be prepared.
Note on C6: Simulators, Lint, Revision Control, Bug Tracking, Code Coverage, synthesis, STA, PnR, Physical Verification, Power Analysis, LPE, RC extraction, Any internal tools or scripts
Note on C9: Review guildelines for: syncronizers, hand instanitiated gates, polarity conventions, case/else statement usage, complete all branches with default, useage of 1-hot FSM's, useage of feedback flops (should plan to initialize to a known state).
Note on C10: Asynchronous reset assertion, synchronous de-assertion. Reset generation logic designed to prevent glitches. Sync/Async relation between clocks. If phase relationship between clocks is required, has this been verified to be maintained in all functional scenarios. Sync flop placement is close in layout
Note on C11: Hard IP and memories DFT methodology.
Note on C12: - The version control system used for IP management. - Version control system used for design db management.
Note on C13: At Kick-off: - If an internal design and/or tapeout checklist(s) exists, it should be presented at kick-off. At Final Review: - A completed version(s) should be shared at final review. (In addition to completing the Apple checklist).
Note on C14: Details of the entire manufacturing flow for the device.
Note on C15: Should be based on the spec General Qualification Procedure for Integrated Circuits (Sepc # 062 -0101 ) as referenced in the document List of Apple Specifications for Management of Integrated Circuit Components. ( Document # 080-00061 )
Note on C16: Should be based on the spec General Qualification Procedure for Integrated Circuits (Sepc # 062 -0101 ) as referenced in the document List of Apple Specifications for Management of Integrated Circuit Components. ( Document # 080-00061 ) Complete the provided Qualification Plan Results Template qualification-plan-results-ddmmyyyy.template-v1.x.xlsx
Note on C17: Should be based on the spec General Qualification Procedure for Integrated Circuits (Sepc # 062 -0101 ) as referenced in the document List of Apple Specifications for Management of Integrated Circuit Components. ( Document # 080-00061 ) Please fill out the Packaging Tab in this checklist.
Note on C19: Please use the following document as reference for applicable specs List of Apple Specifications for Management of Integrated Circuit components (Document number 080 - 00061)
Note on C20: Complete the provided Qualification Plan Report Template 080-00128-<rev>.xlsx
Note on C22: To be completed by kick-off
Note on C23: Please refer to the doucment List of Apple Specifications for Management of Integrated Circuit components (Document # 080 - 00061 ) for applicable specs to follow.
Note on C24: Please Use Die Fact Template Tab
Note on C25: - List of all Ips with history - Associate a risk level with each IP (high, medium or low).
Note on C26: If applicable: eg. user/programmers guide for processor/co-processor used in design
Note on C27: Please fill the "Packaging" tab in this checklist.
Note on C28: At kickoff: - make sure that mistakes, slips from the prior projects are not repeated. - a plan is in place to address those.
Note on C29: Use the SCM template tab in this checklist
Note on C30: - Not applicable to new, first in a series project. - If the project is a derivative or revision or next generation of an older project - review all the RADARs filed for older project(s) and make sure any applicable fixes are in the current RTL - review all the ECOs which were deferred and include the applicable ones in current implementation.
Note on C44: Should be based on the spec General Qualification Procedure for Integrated Circuits (Sepc # 062 -0101 ) as referenced in the document List of Apple Specifications for Management of Integrated Circuit Components. ( Document # 080-00061 )

## Block Risk Analysis
1 | Summary list of all the new, modified and reused blocks for the silicon
Block Name | Block Type | Block Status | Block Source | Silicon Status |  |  | Modification Details | [5 empty] | Risk Level & Justification | Remarks | KickOff Due Date | Mid-term Due Date | Final Due Date | Status | DRI
|  |  |  | Bench Characterization | Production Test | Shipment Volume | Technology |  | Architecture/Design/Soft Changes |  | Placement/Layouts Changes
[7 empty] | Source Design | Current Design | Source Design | Current Design | Source Design | Current Design
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
[15 empty] | MMDDYY |  |  | OPEN
2 | Summary list of all the open and closed bugs from the most recent Silicon/Design that affect the block under reuse
Item # | Product | Blocks Affected | Bug/Issue | [5 empty] | Bug Type | Root Cause (Why Missed) |  |  | Solution (FIX) |  |  | Methodology Improvements |  |  | KickOff Due Date | Mid-term Due Date | Final Due Date | Status | DRI
Example | ABC | Digital Route | Floating gates in digital route | [5 empty] | Digital Functional Bug | Design did not route with the floating node check |  |  | Floating node check integrated as part of P&R sign-off |  |  | Floating node check added as mandatory requirement for the P&R sign-off flow
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
[19 empty] | MMDDYY | MMDDYY |  | OPEN
Apple Confidential - Do not duplicate
Note on B4: Add the name of the block at an abstract level that can be simulated and re-used independently. Examples : Opamp, Bandgap, Charge pump, LDO etc. RTLs of blocks, DSP cores etc.
Note on C4: Select the type of block from the dropdown list, i.e. Analog, Digital, DSP etc.
Note on D4: New Block : Designed from scratch with no leverage from previous architecture/circuit/RTL/P&R/schematic designs Reused Block : Desgined using leveraged architecture/circuit/RTL/P&R/schematic designs with absolutely "NO" modifications. A block -reuse is when there is absolutely no chnage to any part of the design, layout, technology, enviornement conditions (i.e. supply, load, noise, coupling, technology etc). The verification of re-used block must re-produce exactly same outcomes as in the source. Modified Block : A modified designs leverages architecture/circuit/RTL/P&R/schematic etc from previous desgins. There is a clear defination of what is leveraged and what needs to change. A simple layout modfication or re-floorplannign is also a modification that must be documented and verified. There is a clear plan to verify the modfications and mitigate the risks associated with the modfications
Note on E4: Specify the soruce of the block : New Blocks : Not Applicable Reused Blocks : Source product name, testchip name etc. For the standard blocks from the central library, specify the latest product that used this cells in silicon. Such blocks include ESD cells, IOs, OTP cells etc. Modified Blocks : Source product name, testchip name etc. For the standard blocks from the central library, specify the latest product that used this cells in silicon. Such blocks include ESD cells, IOs, OTP cells etc.
Note on F4: Status of the source silicon
Note on I4: Modifications from the source silicon
Note on O4: -What's the risk level of changes ? Specific : Low/Medium/High - Justification : of the risk level selected - Risk Mitigation : What checks/simulations planned to address the risks ?
Note on U4: Who is "Directly Responsible Individual" for this action item ?
Note on F5: If done, provide details : - Number of parts - Process Corners - Voltage Ranges - Temperature Range - Frequency Range
Note on G5: If done, provide details : - Number of parts - Process Corners - Voltage Ranges - Temperature Range - Frequency Range
Note on H5: If shipping : - Volume -Observed Yield
Note on I6: Provide details : - Source Node - Technology FAB
Note on J6: Provide details : - Current Node - Technology FAB
Note on K6: High Level details of source IP/Block Architecture/Design/RTL etc to highlight changes
Note on L6: High Level details of current IP/Block Architecture/Design/RTL etc to highlight changes
Note on M6: High Level details of source IP/Block Placement/Layouts/Floorplans etc to highlight changes
Note on N6: High Level details of current IP/Block Placement/Layouts/Floorplans etc to highlight changes
Note on D35: Identify open and closed bugs for the latest silicon that is source of a block (design/schematics/architecture/layout/RTL etc) in the current design.
Note on E35: Provide a crisp summary of the bug/issue from the latest silicon(/design)
Note on K35: Identify the Bug type and provide details : analog/digtal, functional/parametric, Mixed signal etc.
Note on L35: Provide crisp details that why this was missed in the last silicon/design ?
Note on O35: What is the proposed or applied solution? Why does this make sense ? Verified ?
Note on R35: What improvements in methodology is applied to not miss this type of bugs/issues ?
Note on U35: All the Open/Closed bugs must be notified
Note on V35: Bug that are unndergoing fixes must be closed by this time
Note on Y35: Who is "Directly Responsible Individual" for this action item ?

## Design Verification
[15 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Due Date | Mid-term Due Date | Final Due Date | Status | DRI | Comments/Questions | Nov F2F | JAN'19 F2F | Deliverables | End March Checkpoint | T/O completeion Risk | KB Status | Effort | Risk | Readiness
Attribute Lists / Test Plans | 1.01 | List all features (attributes) that will be verified along with a priority tag (high/med/low) on each attribute. |  | 2018-09-30 | 2018-11-30 | OPEN | Anton | A comprehensiuve list will be supplied when initial verification plan is created. ETA e/o November | This is in progress and on track for the e/o November target |  | Vplans now available: Chip level: CIO:<MH16 REPO>/documentation/verification/vplans/cio/working/vplan_cio.xlsx CIO_VIP: <MH16 REPO>/documentation/verification/vplans/cio/working/vplan_cio_vip.xlsx DP: <MH16 REPO>/documentation/verification/vplans/dp/working/vplan_dp.xlsx + Cadence TripleCheck USB:<MH16 REPO>/documentation/verification/vplans/usb3/working/vplan_usb3.xlsx and <MH16 REPO>/documentation/verification/vplans/usb3/working/vplan_usb3_cadance.xlsx Wasp: <WP16_REPO>/documentation/verification/vplans/vplan_serdes.xlsx WP RX : <WP16_REPO>/documentation/verification/vplans/vplan_serdes_rx.xlsx WP TX : <WP16_REPO>/documentation/verification/vplans/vplan_serdes_tx.xlsx WP Top: WP RX : <WP16_REPO>/documentation/verification/vplans/vplan_serdes_top.xlsx AMS:<WP16 REPO>/documentation/verification/ams/vplans/* |  |  | CLOSED
| 1.01.1 | Common Block Level Attributes |  | 2018-11-30 | 2019-02-28 | OPEN | [7 empty] | OPEN
| 1.01.1.1 | Verify all reset conditions |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | In progress but can only be completed once design implementation is complete |  |  | In progress and on-going. Priority has been adding mission mode tests however apb reset, and some FSM resets have already been done. Jasper CDC and Superlint covers some of this too. We also use Jasper CSR but have had some tool issues with performance. Currently covvered by asserions and UVM |  | OPEN
| 1.01.1.2 | Verify reset conditions for all mission mode states |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | This is in progress as we proceed with verification. Some tests asynchronously asserts resets but not allblocks are complete yet |  | OPEN
| 1.01.1.3 | Register Tests |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | In progress. We will have random UVM read/write tests. Also planning on using Jasper CSR |  |  | Random read/write tests already available. Also Jasper CSR setup but not robust due to perfomance issues |  | OPEN
| 1.01.1.4 | Reset Value Test from every external interface |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.1.5 | Write/Read Test from every external interface |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We use UVM to do register read/writes. This is already in place. We also have Jasper CSR setup but have performance issues with tool |  | OPEN
| 1.01.1.6 | No address aliasing |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | This is being done. The UVM register model is already checking for this implicitly |  |  | This is checked through our methodology and scripting. It's just not possible to generate aliased registers. Same scripting is used for RTL memory map. Furthermore Our UVM register layer checks for this. |  | CLOSED
| 1.01.1.7 | Exception or error conditions - Error detection and recovery |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.1.8 | Clock frequency testing |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | This is in progress and being checked through the various frequency modes we have. More dedicated checkers will be implemented. |  |  | This is checked through functional UVM tests and also checkers that we have in our envirnmnet including SVA assertions. |  | OPEN
| 1.01.1.9 | Clock Gating |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Tested through Jasper CDC setup and functional tests. These have been invaluable. Handed CDC runs to design team for the moment so turaound time to address issues can be sped up |  | OPEN
| 1.01.1.10 | Power Gating |  | MMDDYY | MMDDYY | NA |  | Current POR is that there's no powe gating | [5 empty] | NA
| 1.01.1.11 | Clamp Values of Isolation cells when power gated. Verify all outputs have isolation cells. |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 1.01.1.12 | Reset values of I/Os |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Framework in place but spec/design is only just completeing. Will not be comple by end of Month. Update: We now have a script that checks for reset values across the Ananlog/Digital interface. This is currently maintained by design team. |  | OPEN
| 1.01.1.13 | Coverage |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | Coverage driven methodology is being used. | (Removed in v3.2, retained for v2.9) |  | Due to late design, priority is on A0. Coverage will not be closed pre A0 TO. |  | OPEN
| 1.01.1.14 | Verify all I/Os toggle |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | This is planned to be done and is part of methodology. Can only be completed when design implementation is completed. |  |  | This is part of our methodology and coverage closure. However, we will not be able to complete this task un til after A0 |  | OPEN
| 1.01.2 | Common Fullchip Attributes |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.2.1 | Verify all reset conditions |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | Similar comment to #5 above |  |  | Similar status to item #1.01.1.1 |  | OPEN
| 1.01.2.2 | Verify reset conditions for all mission mode states |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | Similar comment to #6 above |  |  |  |  | OPEN
| 1.01.2.3 | Register Tests |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | Similar comment to #7 above |  |  | Similar status to item #1.01.1.3 also tested in part of the protocol specific tests e.g. CIO |  | OPEN
| 1.01.2.4 | Reset Value Test from every external interface |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Similar status to item #1.01.1.3 |  | OPEN
| 1.01.2.5 | Write/Read Test from every external interface |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We have UVM based tests with register model already in place |  | OPEN
| 1.01.2.6 | No address aliasing |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Similar comment to #1.01.1.6 |  | OPEN
| 1.01.2.7 | Exception or error conditions - Error detection and recovery |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We have various frequecny checkers for various blocks. TripleCheck also tests for this for USB and DP |  | OPEN
| 1.01.2.8 | Clock frequency testing |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.2.9 | Clock Gating |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.2.10 | Power Gating |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 1.01.2.11 | Clamp Values of Isolation cells when power gated. Verify all outputs have isolation cells. |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 1.01.2.12 | Reset values of I/Os |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Not yet done for the full chip level. It’s currently tested indirectly via the VIP but plan is to add dedicated tests and assertions for this. |  | OPEN
| 1.01.2.13 | Configurability of I/Os - Pullup/Pulldowns, Input/Output |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.2.14 | Verify all interrupts |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | This is not priority for A0. However there are designer unit level testing that checks some for this as risk mitigation. |  | OPEN
| 1.01.2.15 | What is done for PLL verification |  | 2019-01-31 | 2019-03-31 | OPEN |  | Behavioral model and co-simulation with schematic | Testing lock and unlock through various config changes (divider settings, enable/disable) and frequency change. | (Removed in v3.2 and replaced with a similar item 2,14, retained for v2.9) | Not sure what else is required here | We have very detailed Real-Number behavioral models. In Addition AMS simulations are run to confirm functionality of various loops and also startup and reset. Simulations are currently on going on both AMS and UVM front. Most loops have now been checked and converging. |  | OPEN
| 1.01.2.16 | Verify all I/Os toggle |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 1.01.2.17 | Brownout simulation - Check if POR will generate a reset signal when voltage droops |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | This is handled by analog designers for PLL and not performed as part of Verification team. To follow up with Roger |  | OPEN
| 1.02 | Indicate how each attribute will be verified with self checking capability - unit and/or top level, directed vs constrained random, assertions, monitors, emulation…etc. |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | Our TBs are self checking using constrained random UVM environment. In addition we use assertions for protocol checking and contol oriented logic. We do not have emulation, however we have FPGA environment which has been used to validate the protocols at core (USB, CIO and DP)n to some extent |  | OPEN
| 1.03 | List critical use cases & performance scenarios that will be verified plus the goals to be met. |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | Available as per vplan? |  | CLOSED
| 1.04 | List of key features that will be verified end-to-end. |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | All protocol logic are testted end to end using VIPs for Host and Device. It includes also responses sent. We use Cadence VIP for USB3.2 and DP. We've developed our own VIP for CIO and also have a setup with CDNS VIP connected |  | OPEN
| 1.05 | Estimated resource requirements per attribute, completion versus plan show trajectory. |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | Really behind schedule due to spec and design lateness. Also issues with Cadnce VIPs |  | OPEN
| 1.06 | List all visually verified attributes. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | This can only be done at sign-off as right now we don't know what will have to be visually tested. We endeavour to have automated tests at all times unless absolutely needed |  | OPEN
| 1.07 | List featuresonly tested at the block level and not tested at full chip. What are the risk in not testing these at full chip |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | There will be items that cannot be checked at chip level for now and rely on designer unit level testing due to schedule constraints;. However, we don't have a full list yet |  | OPEN
| 1.08 | Show how each item in Data Sheet and ERS mapped to the test plan item(s) |  | 2018-12-15 | 2019-01-31 | OPEN | [5 empty] | We have detailed vplans that references the spec. In addition for chip level, we use vmananger and spec is annotated on vplans. (applies mostly to USB and DP) |  | OPEN
| 1.09 | List stimuli relying on analog models, its limitations. Need digital logic stressed independent of analog model limitation | 2018-06-30 | 2019-01-31 | 2019-02-28 | OPEN |  | In progress, data review at MRD | No direct stimuli is dependent on analog models. We have however some control knobs in analog models such as ffset registers which are used to inject offset, noise etc in the analog as a means of stressing the design and checking algorithm loops |  |  | Nov f2F omment is comprehensive |  | CLOSED
Verification Environment | 2.01 | Description of verification methodology ; test bench & nature of stimulus ; randomization of configuration; constraints. | 2018-02-01 | 2018-02-01 | 2018-06-30 | OPEN |  | We already have a mature methodology and coding guidelines in place, especially for SerDes. Chip level is re-using the same methodology and common blocks where possible are shared. For AMS, co-simulation will be performed on blocks that have loops between analog and digital as well as top level tests (reset, any order power up etc) | Covered by material presented in Dec'17 (Radar AI 35931905) and June'18 F2F (Radar AI 40623962). |  |  |  |  | CLOSED
| 2.01.1 | Review list of random constraints and make sure nothing is over-constrained |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Agree. There will be an audit to all testcases and sequences but prioriyt is on A0 verification. Likely will be done post A0. Coverage closure and UNR will also identify some items |  | OPEN
| 2.02 | List drivers / checkers / models / monitors / assertions that will be included. | 2018-06-30 | 2019-01-31 | 2019-03-31 | OPEN |  | In progress, data review at MRD | each interface has it's own UVM agent (monitor, driver etc). On the analog to digital interface we have assertins to check correct signal and protoc behaviour. A comprehensive list will be provided once TB development is complete |  |  | Not all checkers have been impelemented yet as verification is still on going. Majority of this can be provided though but during signoff and not 31/03 |  | OPEN
| 2.02.1 | List all VIPs used in DV env, specify vendor/version/maturity/limitation | 2018-02-01 | 2018-08-31 | 2018-10-31 | OPEN |  | Current POR is to use USB3.1/3.2 and DP 1.4 from Cadence. We'll be early adopters for 3.2 For CIO, we are developing an internal VIP and also working closely with CDNS to use their VIP as soo as it's available as early adopters | Using CDNS VIP for DP v1.4, USB 3.2. These includes it compliance testsuites (Triple Check). Fot CIO, we are developing our own internal VIP. We will also be using CDNS CIO VIP for device and Host as an extra sanity check. We'll integrate retimer version as soon as they have it available too |  |  |  |  | CLOSED
| 2.03 | Details on architectural/reference model for comparison with RTL. Review of co-verification model. | 2018-04-01 | 2018-11-15 | 2019-01-31 | OPEN |  | We'll be using aspects of TAU model in our envronment to support 3 way comparison. Chip level will have a detailed design based model of the SerDes | In progress. We've already sytarted using TAU in our envirnment. Channel model is incoporated and started correlation work for block level (VGA, CTLE, LTE etc.) |  |  | We use Tau where available. We also run some sims between bmod and schematic and visually compare that they are functionally equivalent. Hower this process is not fully automated yet. We also have triggers to notify on any schematic that has been updated which contains a bmod |  | OPEN
| 2.04 | Formal verification where applicable or alternative methods adopted. |  | 2018-12-31 | 2019-02-28 | OPEN |  | We'll use formal for small control based blocks. Also formal apps such as CDC, UNR, connevctivity checks and register checking will be used througout the project. Using Jasper as our formal tool. |  | (Removed in v3.2, retained for v2.9) |  | We use Jasper as our formal tool. Mainly been used for SuperLint, CDC and CSR. We have some block that have FPV running |  | CLOSED
| 2.05 | Regression approach : # of licenses, # of servers, frequency of runs & debug turnaround…etc. | 2018-06-30 | 2018-11-15 | 2019-01-31 | OPEN |  | We have a matur regression methodology that will be adopted for both chip level and SerDes IP level. For Chip level, vmanager will also be used. We run nightly regression, long regressions and sanity regression whenever there's a design/TB change | This item is pretty much done. Vmanager is used at chip verification. Regression flow up and running for SerDes envirnments. Leaving open to finalise on number of licenses. |  |  | Most regressions will complete overnight. To run all modes of USB and DP, it requires 2-3 days. |  | OPEN
| 2.06 | Environment performance & profiling. | 2018-06-30 | 2019-01-31 | 2019-03-31 | OPEN |  | We regularly provile our verification environments. Both in times of run time and memory usage |  |  |  | We perform profiling as we progress or when we hit performance issues. That has generally been on the SerDes |  | OPEN
| 2.07 | Version management methodology - Database tagging and RTL release procedure | 2018-02-01 |  |  | OPEN |  | We'll use SOS and GIT. Regressions will be done on a regression only work area and database will be updated before every regression and tagged appropriately |  |  |  | We use database Management system. Unfortunately there's a mix of two. Clisofot SOS (For analog and mostly SerDes TB) and GIT (mostly for RTL, and chip level TB) |  | CLOSED
| 2.08 | Limitiations in the current environment | 2018-06-30 | 2019-12-31 | 2019-02-28 | OPEN |  | In progress, data review at MRD |  |  |  | Verification is still in flight. Main limitiation is on schedule rather than TB limitations. Where there are gaps, we tend to approach the issue in multiple ways e.g. Formal + Sim |  | OPEN
| 2.09 | Provide a detailed test bench diagram including all checkers, monitors, models and connections. |  | 2018-12-31 | 2019-03-31 | OPEN | [5 empty] | We have diagrams available but since verification is still in progress, some details will be missing and would not be complete. |  | OPEN
| 2.1 | review and sign off any RTL simulation workaround to speed up simulation - forces/deposits |  | 2019-01-31 | 2019-02-28 | OPEN | [5 empty] | Sign-off item. Incidentally, we are already doing this for SerDes and have a target to not have any forces/deposits by the 15/03 |  | OPEN
| 2.11 | review and sign off any RTL simulation workaround to speed up simulation - simulation only defines/parameters used etc |  | 2019-01-31 | 2019-02-28 | OPEN | [5 empty] | Sign-off item. Only available very close to TO |  | OPEN
| 2.12 | List of Negative tests to break the checkers,assertions, monitors and scoreboards to ensure the validity of the checkers |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We will not have time to fully complete this before A0. Priority is on A0 priorities |  | OPEN
| 2.13 | Out of bound access to array/bit-vector run time detection |  | 2019-01-31 | 2019-02-28 | OPEN | [5 empty] | We run sims with out of counds checking enabled. We also have Jasper SuperLint running and flag issues to designers. Not closing since this is sign-off item |  | OPEN
| 2.14 | Implement timing checkers on all interface signals |  | 2019-01-15 | 2019-03-15 | OPEN | [5 empty] | We run gatelevel sims with SDF annotatetd. We also have some extra assertions to check timing e.g. on APB. However, some interfaces like TWI will need similar assertions |  | OPEN
Clock Domain | 3.01 | List all areas of the design that spans multiple clock domains. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We use Jasper CDC. Many issues flaggd and addressed by design team. However we are waiting for CDC strategy document/spec |  | OPEN
| 3.02 | Methodology used for ensuring robustness of clock crossing logic; review any changes since last checkpoint(KO,MDR,etc) | 2018-02-28 | 2019-01-31 | 2019-03-31 | OPEN |  | POR is to use Jasper CDC. We already have evaluated this and have flows that already run this (mainly done by designers) |  |  |  | Same comment as above |  | OPEN
| 3.03 | Produce waveforms that prove the robustness of logic crossing clock boundaries. |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 3.04 | Verify clock gating entry & exit. |  | 2019-01-31 | 2019-03-15 | OPEN | [7 empty] | OPEN
| 3.05 | Clock frequency randomization. Run tests at all the supported clock frequencies. | 2018-06-30 | 2018-12-31 | 2019-02-28 | OPEN |  | In progress, data review at MRD |  |  |  | All supported data rates are being run. We also have a synchroniser delay model to inject metastability |  | OPEN
| 3.06 | Synchronizer randomization (n and n + 1) propogation delay. | 2018-06-30 | 2018-11-30 | 2018-12-31 | OPEN |  | We already have a strategy based on previous project but planning on further improvements |  |  |  | Synchroniser delays being randomised as part of our methodology |  | OPEN
| 3.07 | Share RTL for the synchronizer model to confirm synchronizer randomization |  | 2018-12-31 | 2019-01-31 | OPEN | [5 empty] | We have RTL and Coverage model for synchroniser randomisation. Will be provided at sign-off |  | OPEN
| 3.08 | Check and confirm synchronizer randomization never disabled |  | 2019-01-31 | 2019-05-15 | OPEN |  | This is also part of sign-off. We also run Formal checks using Jasper CDC app. | We also collect coverage on synchronizer model |  |  | We collect coverage on synchroniser randomisation. There are sometimes exception when dealing with analog configurations. |  | OPEN
Compliance Testing | 4.01 | Version numbers of specifications. | 2018-06-30 | 2018-12-31 | 2019-02-28 | OPEN |  | In progress, data review at MRD | [5 empty] | OPEN
| 4.02 | Source of stimulus. How is compliance of checkers ensured. | 2018-06-30 | 2019-01-31 | 2019-03-15 | OPEN |  | For DP and USB we will use Tripple Check compliance testsuite as part of CDNS VIP, Others will be in-house with back annotated tesplan vs speciications and coverage |  |  |  | DP and USB uses Cadence VIP with TripleCheck compliance test-suite. CIO uses our own internal VIP |  | OPEN
| 4.03 | Chip-to-chip interfaces (e.g. I2C, SPI, MIPI, DisplayPort, PCIe, JTAG). | 2018-06-30 | 2018-12-31 | 2019-02-28 | OPEN |  | In progress, data review at MRD |  |  |  | APB, I2C(TWI) uses our own internally generated |  | OPEN
Power Gating Verification | 5.01 | Description of methodology, power domains, flows & identification of key scenarios. |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 5.02 | Verify behavior of power gates and isolation cells. |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 5.03 | Verify low power modes, entry & exit. |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 5.04 | Verify race between power gating entry and exit |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
| 5.05 | X Insertion and X propogation | 2019-01-31 | 2019-01-31 | 2019-03-15 | OPEN |  | Plan to use formal X prop apps | [5 empty] | OPEN
| 5.06 | Power aware gate sims |  | MMDDYY | MMDDYY | NA | [7 empty] | NA
Performance Verification | 6.01 | List of key scenarios and metrics identified (e.g. mbps, interrupts per second, dynamic range) |  | 2019-01-31 | 2019-03-15 | OPEN | [7 empty] | OPEN
| 6.02 | How is performance verified (e.g. checkers, end of sim checks). |  | 2018-12-31 | 2019-02-28 | OPEN | [5 empty] | We have end-of sim checks to make sure that there were atleast passes, no error and warnings gets reported. We also dump simulation times, cpu and mem usage. We use these to rank sims. However as verification is still in flight, this item is not completed and not extensively monitored |  | OPEN
Stress Testing | 7.01 | Verification of all inputs and outputs enabled simultaneously, concurrent transactions. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We use a constraint random verinment. Most I/O are started simultaneously |  | OPEN
| 7.02 | Verification of extreme resource contention and backpressure scenarios. Verify flow control logic. |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 7.03 | Verification of high error rates on memories and protected data interfaces. Verify error correction logic. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | No memories in our system |  | NA
| 7.04 | Verification with Mid-simulation reset. |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 7.05 | Verification with random X replacement at simulation startup, to negate X optimism. |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 7.06 | Out of bound access to reserved/unspecified memory space - add tests for intentional error injection, add run time monitor to check for unintentianal error occurrence. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | For register address spaces, tis part tested in our RAL testing. However not fully complete for all blocks. We also have Jasper CSR setup, but having performance issues with the tool. |  | OPEN
Debug Capabilities | 8.01 | Review verification of debug features in the design (DFT/Test Modes/Dig Mux/etc.). |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We have had several design reviews and recently interface reveiews with Architects and design teams. DFT (ATPG/Scan) is handled outside the team by Ravindra. For functional DFT modes, this is partly covered by us e.g loopback, debug clks etc. However for A0 priority has been on mission mode features |  | OPEN
| 8.02 | Verify test mode entry/exit doesn’t affect normal functional mode |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Not done yet. Currently priority is on mission mode. This is partly covered by DFT team |  | OPEN
Gate Level Verification | 9.01 | Describe the methodology - flow, flat vs hierarchial; mix of RTL & gates; block vs top level; unit delay vs sd. | 2019-01-31 | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We do GLS on full PNR netlist hence no RTL at IP level. For Chip level, Serdes IP and comdig may be RTL and the rest of protocol logic will be gates. For SeRDes IP side, the digital is wholly in gates whilst analog is behavioral models. Pnr netlist is semi hierachical. |  | OPEN
| 9.02 | Review gate simulation test cases and results, and estimate degree of coverage. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We have some setup for GLS done at chip level, however, we haven't started full GLS sims as we are waiting for PnR netlist. For SerDes IP, setup for GLS is planned to commence soon but will also be gated by availabilty of timing clean netlist. As for SDF + unit delay. We run first setup with unit delay for flow flush then sign-off based on SDF back annoted with Min and Max delays. Time permitting typical corner will also be run. |  | OPEN
| 9.03 | List forces for initial state, back-door initializations, and other simulation speed-up techniques. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | We avoid forces at all costs. For std flops without reset, we have a random initialisation model that is bound to the cell to perform initialisation. Simulation speed-ups are typically performed by modifying various timing paramaters through FRONTDOOR MM accesses (APB). These are randomised and for sign-off full sim is run. |  | OPEN
| 9.04 | What was done for I/O cell verification? Include propagation delay of the IO cells in SDF back-annotated gatesims |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 9.05 | Gate-level simualtion of test vectors. |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | For GLS we run same tests as UVM environment (albeit a subset) . For DFT vectors, these are run against fullchip gates by DFT team again on min/max corners |  | OPEN
| 9.06 | Functional verification of DFT |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
| 9.07 | Do not disable any timing checks in Gatesims with SDF - List if any exclusions or modifications made for GLS |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Agreed. We do not disable any timing checks. However, for SerDes IP, when changing configurations, analog signals may transition rabidly so on such kind of configuration changes (e.e.g coming out of reset), nobling of notifiers can be done for a very short burst.They are done at the output of notifier so violation (if any) wilol still be seen in logs |  | OPEN
| 9.08 | What does the flip-flop model output under setup and hold violations | 2019-01-31 | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
Mixed Mode Verification | 10.01 | Tools, methodology, stimulus and areas of the design where applicable. | 2018-02-28 | 2018-10-31 | 2018-12-31 | OPEN | Anton/Siva | We have a methodology in place that uses DMS2.0 Spectre/Xcelium. Some dedicated AMS sims also for tightly coupled loops between analog and digital. We've also worked on AMS testplan methodology | This item is pretty much done. Vwe have mature metjodologies and evaluation of all the tools has been completed |  |  | For simulation, we use Cadence Xcelium with UVM constrained random testbench. For AMS/DMS we use Xcelium + Spectre (APS++). For chip level protocols such as USB and DP, we use VIPs from Cadence. For formal FPV we use Jasper. We also use Jasper Apps for UNR, CSR, SUperlint and CDC |  | OPEN
| 10.02 | Review level-shifter verification strategy. |  | 2018-12-31 | 2019-02-28 | OPEN | [7 empty] | OPEN
| 10.03 | Review behavioral models for analog blocks - generate x's for uninit or unpowered blocks - publish all x states and show how resolved |  | 2018-11-30 | 2019-02-28 | OPEN |  |  | All our behavioral models are pessimistic and strategy is always to generate X's if supplies and biases are not correctly setup |  |  | This is exactly our methodology. We model our analog cells at deepest level possible. The models also includes connectivity and supply checks. If power supplies do not have the correct value, the X's are forced into the outputs. The same approach we do for control signals and trimming bits. If they are Z or X's the we also generate X;s on outputs. For GLS, some protction may be needed but only on a need basis |  | OPEN
| 10.04 | Review work done to prove equivalency between model and actual design. |  | 2018-12-31 | 2019-03-31 | OPEN |  |  | This is work in progress. We've already done a 1st pass equivalence chek of some blocks. Compared bmods vs schematics vs TAU |  |  | Currently this is achieved by running simulations at cell level comparing transistor sims versus behavioral ones. In Addition we run the same UVM testbench in our DMS environment where the models are replaced by real analog design. Further cross checks are done with Architectural model (TAU) where applicable. We also have automatic triggers to make sure we are notified of a change in a cell that contains a bmod. |  | OPEN
| 10.05 | Toggle coverage between analog and digital interface. 100% coverage with waivers. |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | This has always been our strategy and we have a clearly defined workflow |  |  | This is our methodology,. We look for 100% toggle coverage. We have to apply some waivers for static signals such as supplies or DFT test modes. However, for A0, we will not be able to achieve 100% coevrage due to late design |  | OPEN
| 10.06 | Review Netlisting warnings for the full chip and sub-system |  | 2019-12-31 | 28/12/209 | OPEN |  |  | In progress. Warnings are regularly reviewed and addressed during netlist generation. |  |  | This is always reviewed and have scripts that are run automatically on design change to check fo validity of netlist |  | OPEN
| 10.07 | Require POR/Bringup simulations with all schematics for analog with digital RTL |  | 2019-01-31 | 2019-03-31 | OPEN |  |  | This is planned for. We will have a powere up and reset check including any order power up with full schematics and RTL. We also use DMS flow in various co-simulation testing |  |  | Yes, this is part of our methodology and planned for. We perform bringup tests, resets and any order power up |  | OPEN
| 10.08 | Specify chip loading condition simulated in top level AMS. |  | 2019-01-31 | 2019-03-31 | OPEN | [7 empty] | OPEN
Coverage | 11.01 | Structural (code) coverage is required. Provide details on coverage tool and methodology. | 2018-02-28 | 2018-06-30 |  | OPEN |  | We already have a good strategy and robust. It was explained on the F2F explained in the outline. Code coverage goal is 100% with waiver file used to exclude reviwed items that cannot be covered. Functional coverage goal is 100% | Coverage tool used is Cadence IMC. Coverage is collected during nightly regressions and mergerd. Toggle coverage, Line coverage, expression coverage, FSM coverage is collected. Waiver file is maintained and reviewed. When design is updated or critical TB updates are made, coverage is emptied. |  |  |  |  | CLOSED
| 11.01.1 | Do not include register reset or read/write tests in coverage. | 2018-04-01 |  |  | OPEN |  | Agreed. We do this already | [5 empty] | CLOSED
| 11.02 | Plans for functional coverage and the scope. What areas of the design will be covered? | 2018-02-28 | 2018-12-31 |  | OPEN |  | Will autogenerate mojority of cover groups right from vplan. Fucntion coverage also collected for assertions | [5 empty] | OPEN
| 11.03 | Identify code coverage waiver methodology. | 2018-02-28 |  |  | OPEN |  | We already have a methodology on this. Coverage waivers are only added after review and confimation from designer. A comment, date and owner for the waiver is also captured | [5 empty] | CLOSED
| 11.03.1 | Require 100% Code coverage in Statement, Branch, Expression, Toggle, FSM (State+Arc) with approved waivers |  | 2019-01-31 | 2019-03-31 | OPEN |  | Agreed and we do this too |  |  |  | Design too late to complete coverage closure. A0 verification will only focus on mission mode and startup |  | OPEN
| 11.03.2 | Generate code coverage reports with approved waivers included and prove 100% coverage |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Design too late to complete coverage closure. A0 verification will only focus on mission mode and startup |  | OPEN
| 11.04 | Require 100% assertion coverage with approved waivers |  | 2019-01-31 | 2019-03-31 | OPEN | [5 empty] | Design too late to complete coverage closure. A0 verification will only focus on mission mode and startup |  | OPEN
| 11.05 | Require 100% functional coverage |  |  | 2019-03-31 | OPEN | [5 empty] | Design too late to complete coverage closure. A0 verification will only focus on mission mode and startup |  | OPEN
Item 11,06 relating to ROM in v3.2 is N/A for TP and not included
Bug Tracking | 12.01 | Weekly bug tracking. Tool used? When does tracking start? | 2018-02-28 | 2018-10-31 | 2018-12-31 | OPEN |  | Every bug entered in bug tracking tool (redmine). Ver also keeps a summary in an easy formatted text file for generating curves etc. Graphs updated weekly | Tracking has already started |  |  | We use redmine. Bug tracking begins right from the start after a block feature has been implemented. |  | CLOSED
| 12.02 | Weekly reporting. New bugs: how found, nature, and severity. Rate of find/fix/closure; oldest bugs. Vulnerable parts of the design as indicated by bugs. |  | 2018-10-31 | 2019-11-30 | OPEN |  | We collect all manner of metrics and plot graphs. Currently working on streamlining these and generate weekly graphs that will contain this info and also status of coverage and pass/fail | Improving on this. Weekly reporting will comence 15 Nov |  |  | Bug statistics can easily been generated via redmine based on criteria, severity and dates |  | CLOSED
| 12.03 | After closing, no bug should be re-opened. Need to file as new bug |  | 2018-02-28 | 2018-02-28 | OPEN |  | Agree totally. This is our approach too | [5 empty] | CLOSED
Emulation | 13.01 | For RTL targetted for FPGA |  | 2018-12-31 | 2019-02-28 | OPEN |  | FPGA environment being developed to test legacy DP and USB modes. |  |  |  | We have some limited FPGA testing of the 3 chip level protocols we have. i.e. USB gen 1x1, DP and CIO. Simulation vectors for these were generated by the same TB we use fior simulation. Currently FPGA activities are covered by design team. More details will be provided |  | OPEN
| 13.01.1 | Review Regression strategy |  | 2018-12-31 | 2019-02-28 | OPEN |  |  | Test stimulus generated by the same tests run using the VIP environment. Data is cross checked between FPGA envirnment and VIP |  |  | Same as 13.01 above |  | OPEN
| 13.01.2 | Review Test Plan |  | 2018-12-31 | 2019-02-28 | OPEN |  |  | An initial draft of the testplan is available but needs review |  |  | Same as 13.01 above |  | OPEN
System Level Verification | 14.01 | Review plans for achieving this along with realistic use cases. |  | 2018-11-30 | 2019-01-31 | OPEN | [5 empty] | We have had various reviews with design/architects. Our vplans were also reviewed. For A0 we aligned on priorities for A0 |  | OPEN
RTL Freeze Criteria | 15.01 | List of tests required to freeze RTL |  | 2019-01-15 | 2019-02-28 | OPEN |  | Fully featured list to be regression clean | [5 empty] | OPEN
| 15.02 | Coverage required to freeze RTL |  | 2019-01-15 | 2019-02-28 | OPEN |  | 90% explained |  |  |  | Due to design lateness especially for SerDes IP, we have only started looking at coverage. It's not going to achieve our initials tartgets and looning at establishing what is needed for A0. For chip level, we are already evaluating coverage. This had been delayed due to VIP/Triple check issues, but numbers are good for RTL freeze there |  | OPEN
ECO Verification Methodology | 16.01 | How are ECOs verified with gate level net list and RTL? | 2018-04-01 | 2019-01-31 | 2019-03-31 | OPEN | Anton | We already have a methodology for this. ECOs are verified functionally using Gate level simulation which run on the same TB as RTL. In addition, formal logic comparison between RTL and GLS netlist is done using LEC |  |  |  | Same comment as the comment section |  | OPEN
COSIM | 17.01 | Review plans for simulating the design in SOC env: Need, deliverables and dates | 2018-06-30 | 2018-11-30 | 2019-01-31 | OPEN |  | Wevalready have a framework of doing this based on other projects. DMS flow will mostly be used for cosimulation as well as dedicated cosims for tighly coupled loops between analog and digital | In progress. We already have SOC environments up and running. For the Serdes IP, we'll use detailed analog models of the serdes with the digital part being the complete RTL |  |  | SOC cosim is only focussed on blocks where there is analog involved, e.g SBU. If there is a digital loop, a full cosim will be run with Ananlog section being schematic or extracted netlists. Where there's no loop, we dump PWL from a functioning sim and replay this in schematic to confirm behavioral model were correct |  | OPEN
DV and AMS Resource Planning | 18.01 | Provide DV/AMS resource plan including each member’s Name, Role (DV lead, AMS lead, DV, AMS), Permanent/Contractor, Location, Start Date, End Date, Bandwidth (100%, or xx% if supporting other Apple projects) | 2018-02-28 | 2018-09-30 | 2018-11-30 | OPEN |  | Resource and planning is constantly being monoitored and assesed. Recruitement is also on-going to address areas that are under-resouced. | Some contractors already on board. Permanent extra resources joining in November from our Denmark site. This pretty much fulfils our resource requirements albeit joining a bit later than planned but have plan to mitigate |  |  | This data is available. How shoud it be presented? AMS ver team consists of Siva, Achim and MarkR |  | OPEN
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Verification Environment | 2.15 | PLL - make sure RTL simulations use realistic behavioral model (v3.2/2,14) |  | MMDDYY | MMDDYY | OPEN | [5 empty] | We have very detailed RNM models. We also run cosims to confirm functionality
| 2.16 | Review all “FIXME” or “TODO” comments in the verification environment and close with proper documentation (v3.2/2,15) |  | MMDDYY | MMDDYY | OPEN | [5 empty] | Agreed. Sign-off item. However due to design lateness, verification is way behind schedule and therefore there are still many "TODOs/FIXMEs")
| 2.17 | Review all compilation/simulation warnings in the Testbench code and make sure all are closed with proper documentation (v3.2/2,16) |  | MMDDYY | MMDDYY | OPEN
| 2.18 | Review tool versions planned for DV/AMS execution (v3.2/2,17) | MMDDYY | MMDDYY | MMDDYY | OPEN
| 19.01 | Formal Verification - Overall Strategy (v3.2/19,01) | MMDDYY | MMDDYY | MMDDYY | OPEN | [5 empty] | We use Jasper (from Cadence). Use CDC, CSR, Superliny, Connectivity and UNR apps. We also use FPV to prove our own assertions which are mostly focussed on protocol level and block levels which are more control oriented
Formal Verification | 19.02 | List all formal proofkits developed or from external vendors (v3.2/19,02) |  | MMDDYY | MMDDYY | OPEN
| 19.03 | All critical warnings looked at fixed/waived (v3.2/19,03) |  | MMDDYY | MMDDYY | OPEN | [5 empty] | Post signoff
| 19.04 | FSM Checks (v3.2/19,04) |  | MMDDYY | MMDDYY | OPEN
| 19.04.1 | FSM STATE Transition reachability Checks (v3.2/19,04.1) |  | MMDDYY | MMDDYY | OPEN
| 19.04.2 | FSM LIVELOCK Checks (v3.2/19,04.2) |  | MMDDYY | MMDDYY | OPEN
| 19.04.3 | FSM DEADLOCK Checks (v3.2/19,04.3) |  | MMDDYY | MMDDYY | OPEN
| 19.05 | UNR Usage and UNR input constraints (v3.2/19,05) |  | MMDDYY | MMDDYY | OPEN
| 19.06 | Connectivity Checks (v3.2/19,06) |  | MMDDYY | MMDDYY | OPEN
Note on A3: Attributes are specific items to be validated through simulation. There must be a checking mechanism for the attribute. It can be a checker, reference model, assertion, functional coverage group or code coverage. Attributes are not test caes. Test cases can cover mutliple attributes. Attributes can also require multiple test cases to cover them.
Note on C6: Assert asynchronous resets in all modes of operation.
Note on C8: Read register values and check that they match the reset value after every defined reset condition.
Note on C10: Verify that every register has a unique address.
Note on C11: Verify that every error is detected and verify the recovery procedure for each error.
Note on C15: All outupts go to a defined state (0 or 1).
Note on C21: Assert asynchronous resets in all modes of operation.
Note on C23: Read register values and check that they match the reset value after every defined reset condition.
Note on C25: Verify that every register has a unique address.
Note on C26: Verify that every error is detected and verify the recovery procedure for each error.
Note on C30: All outupts go to a defined state (0 or 1).
Note on C34: Make sure all RTL simulations use realistic behavioral model for PLL
Note on C39: End to end is data transfer from input of the chip to the output of the chip. All possible permutations of paths must be tested. List what is not being tested.
Note on C43: Exceptions could include some analog specific parameters like PSRR, phase margin, buck efficiency, line and load transients and in general packaging, qual, ESD requirements, etc
Note on C47: Each random variable should have a matching functional cover property defined. e.g. packet length should have cover bin defined to include min, max, and appropriate short/long type of length ranges and sampled with the appropriate send/receive event. Exceptions should be disclosed and granted case by case.
Note on C53: This item is trying to ensure that the simulation environment is running as efficiently as possible. This can be done by running the simulator profiling tool to find simulation performance bottlenecks and large memory consumers.
Note on C57: e.g. force POR reset counter to roll over in 10 us instead of 10ms
Note on C58: e.g. define SIMULATION_SPEEDUP, defparam SHORT_RESET
Note on C59: Here we need to ensure that checkers are functional and no false postives on the checkers
Note on C60: Compile options to include "ii_warn" for NCSIM and "-boundscheck -ntb_opts check=all" for VCS
Note on C61: - include not only all external interfaces but also between internal blocks - functional and cycle accurate
Note on C74: - does it meet IEE spec - any assumptions made wrt spec which might preclude generic usage across designs - Is IP silicon proven - I2C requirements met: glitch filter (>50ns), 0ns hold for RX, 300ns hold for TX, slew rate limitation
Note on C77: For isolation cells, ensure correct polarity during powerdown mode
Note on C79: Have a test that places the power gating entry and exit events as close a possible. Repeat this test with appropriate delays to make sure that there isn't a timing window that will cause the logic to fail.
Note on C80: When a block is power gated all the flops that don't have retention must be corrupted to X (using power aware simulator or in house tool). Also simulation solution (e.g. xprop simulator option) is needed to eliminate X optimism in RTL simlation so simulator will not incorrectly prevent X's from propagating. (Verilog if/then and case statements are X optimisc and may not propagate X properly without special care.)
Note on C100: Have DFT tests (scan, JTAG, BIST) been simulated at top-level with full-chip schematics
Note on C102: Any modifications made to the Gate netlist, SDF, scripts or list of flops for disable timing check, etc
Note on C103: Does it propagate x or flag error as timing violation
Note on C107: All x state generation be logged, published, reviewed and show how resolved
Note on C112: get loading conditions (e.g. I2C/SPI etc) and model (battery model, cable model, panel model, etc) from Apple or corresponding vendor. Specify the source of the condition (from xyz specification, from Apple etc)
Note on C120: Provide explanantion for all assertions that cannot be reached, example: negative assertions
Note on C128: Make sure Regression strategy ensures running regression often enough for catching RTL changes that break FPGA
Note on C129: Make sure Test Plan is comprehensive enough to cover basic functionality of the FPGA
Note on C147: Make sure no forces used from DV environment for PLL Lock/Done signals
Note on C150: Provide details on choice for a particular version (if not latest) and if any known tool bugs and work-arounds
Note on C156: check all states are reachable, all state to state transitions are reachable, all transition arcs are reachable
Note on C157: Livelock is a situation where the state changes within only a subset of the states reachable from the initial states of the design.
Note on C158: Deadlock is a special case of live lock where the subset is only one state.
Note on C160: provide connectvity checks performed: A-D, register to pin, etc

## Analog
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review | Mid-term Review | Final Review | DRI | Comments/Questions Delivered on June 13-15 | Comments/Questions Delivered on Sept.-2018 (related to 'KickOff review' column) | Deliverables | Effort | Risk | Readiness | Comment
|  |  | 2018-07-31 | 2019-01-30 | 2019-03-31
Design | 1.01 | Provide Topology Overview or ASIC block diagram | DELIVERED | OPEN |  | Kiarash | Material prepared for Dec F2F. Update will be provided after project stage 1,2 check points. |  |  | 2 | 1 | ?
| 1.02 | Highlight and justify any custom (schematic based) digital design within analog domain, describe the design methodology used to implement the circuitry and explain how this circuitry is verified. | DELIVERED | OPEN |  |  | No custom (schematic based) digital design planned within analog domain. Required digital logic will be processed by digital flow/PD |  |  | ? | 3 | ?
| 1.03 | Highlight and justify all flip-flop without preset/scan in the analog domain | DELIVERED | OPEN | OPEN |  | Flip-flops w/o preset/scan will be only used in timing critical (high-speed) parts of the analog circuit. |  |  |  | 2 |  | Rm #7653
| 1.04 | High voltage lines should be identified and preferrably automatically checked thru DRC and not manually |  | OPEN | OPEN |  | SBU low impedance feedback paths identified as high-voltage (3.3V) lines. Due to block-hierarchy these lines will stay within analog control. TSMC 16nm DRC methodology includes marking every logical pin with voltage range and checks the stress conditions. |  |  |  | 4
| 1.05 | Check quiet analog lines for cross-talk from clock/noisy digital signals. | DELIVERED | OPEN | OPEN |  | We are aware to check such signals, so this task will be done as soon as we approach at this level of implementation/layout. |  |  |  | 4
| 1.06 | Analog/Digital boundary signals meets requirements | DELIVERED | OPEN | OPEN |  | All signals interfacing between analog and digital will go through standard-cells placed close to the boundary. Thereby timing will be considered. Different supplies between analog and digital logic will be checked either by analog simulation or probably by UPF (unified power format) flow. |  |  |  | 4
| 1.07 | Ensure that any analog circuit driving digital logic swings rail-rail across PVT |  | OPEN | OPEN |  | Update will be provided after project stage 2,3 check points. |  |  |  | 4
| 1.08 | Provide silicon to spice model correlation data or WAT vs. PDK | DELIVERED | OPEN | OPEN |  | All models are data is received from TSMC and available in project database. |  |  | 1 | 1 | 2
| 1.09 | Justify use of latches as latches can create problems if they receive illegal inputs. (Latches can be replaced by a Flip-flop with reset) | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next proct milestone (7/13/18) as the schematic hierachies will be completed at that time.
Analog Reports | 2.01 | Create and follow a compliance-to-spec table and simulation plan | DELIVERED | OPEN | OPEN |  | Each block has a dedicated spreadsheet including the required specification of the block. This spreadsheet is used in simulation to check the pass/fail spec of each individual block.
| 2.02 | DC operating point review. All devices stay in intented region of operation over PVT and signal range | DELIVERED | OPEN | OPEN |  | The key DC operating point vlaues for each block will be monitored and checked during verification.
| 2.03 | Stability report. Document bandwidth phase margin and gain margin over corners for all feedback loops. Provide GM and PM minima as well as zero crossing. | DELIVERED | OPEN | OPEN |  | All the continuous-time and discrete-time loops will have a dedicated testbench in order to check their stability. Small signal checks (phase margin, etc), as well as a large signal checks (transient step) will be performed for each loop.
| 2.04 | Parasitic coupling report. Investigate RCx netlist for couplings onto sensitive / high impedance nets. | DELIVERED |  | OPEN |  | A list of parasitic coupling for all the critical nodes will be produced and checked.
| 2.05 | Ensure matching sensitive circuits do not use minimum size devices | DELIVERED | OPEN | OPEN |  | Matching properties of critical circuit will be carefully simulated.
Analog Simulation Review | 3.01 | Ensure that the simulations run on actual schematics and indicate when ideal sources were or components are added to schematic to make simulations run properly. Indicate any manual or "hacking" of the netlist. Please avoid manual edits to the netlist whenever possible. | DELIVERED | OPEN | OPEN |  | The generated netlists will be checked in order to ensure there is no analogLib component.
| 3.02 | Verify simulation runs with actual bias blocks to ensure bias noise is included and correct polarity and magnitude of bias currents. |  | OPEN | OPEN |  | For noise simulations, all the relevant circuit and blocks will be added to the testbench.
| 3.03 | Includes PMIC/PMU noise and central bias noise by using noise files for supplies and bias currents. | DELIVERED | OPEN | OPEN |  | The testbenches include all the componets that contribute into noise of a block. Either the contibutor blocks will be added or a behavioral model for them will be added.
| 3.04 | Simulate corners with some margin in temperature and voltage above and below specification to understand design robustness and failure points. | DELIVERED | OPEN | OPEN |  | The simulations include 5oC margin for temperature and 30 mV margin for supplies.
| 3.05 | Corner sims include cross corners, include skewed passives. | DELIVERED | OPEN | OPEN |  | SF/FS Corner are checked and passives are skewed
| 3.06 | All bandgap or self biasing circuits have an appropriate DC startup circuit. | DELIVERED | OPEN | OPEN |  | The start-up of bandgap circuits are simulated very carefully. Both DC and transient simulations will be ran to ensure proper start-up.
| 3.07 | Check bias settling with different supply ramp rates. | DELIVERED | OPEN | OPEN |  | Bias block characterization will include any order power up and fast and slow rise times.
| 3.08 | Bias and signal settling time, Ton/Toff from block enable/disable. | DELIVERED | OPEN | OPEN |  | Bias block characterization will include any order power up and fast and slow rise times.
| 3.09 | Confirm that all the external components are modeled appropriately. ESR / ESL, capacitor / inductor voltage, inductor saturation current and temperature & ageing based de-ratings are considered per component datasheet. | DELIVERED | OPEN | OPEN |  | External cereamic package caps derated 50% by voltage and 10 degrees by temperature - ref "Systems Reliability Centre Part Derating Parameters", for benign Environments. Capacitance aging related detaring 1%. Capacitor models Manufacturers Spice based models or S-Parameters
| 3.1 | All testability circuits are implemented as part of design and all modes simulated. Include appropriate modeling of external voltage supplies and probes. | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | Test cicruits are verified by testbenches which stimulate the circuit in mission and test modes. Thereby supplies are modeled in such a way, that IR-drop and noise effects are modeled for various design stages e.g. transistor level, block-level, including power-routing up to the package level.
| 3.11 | All clocks always gated until oscillator / PLL stabilizes and synchronously released. | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | Asynchron reset keeps device in reset state. Start-up oscillator is providing start-up clock for digital core-logic while external reset is active. Digital logic guarantees proper start-up sequence of device which includes switching from start-up oscillator clock to default reference clock source and proper configuration, calibration and ramp-up of PLLs
| 3.12 | Mixed Signal interface elements will propagate X state or trigger errors. | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | From modelling side: if an input is X (or even HiZ), output is forced to X and thus propagation is done and checked. There are also checkers on the AD-interface listto check protocol and ensure no 'X'-states
| 3.13 | Load, package, PCB, external passives, pads and ESD circuits are modeled for all signals interfacing to pin. Series resistance from the power delivery network and battery/supply models are included in the simulations | DELIVERED | OPEN | OPEN |  | No external ESD circuits. A Pin based package model extracted with Cadence XtractIM for internal ESD structures on signal pins. External DC-DC convereters isoalate Kandou design from battery influences. Series resitance form DC-DC to Kandou device modelled at package level with Cadence Xtractim. PCB DCR can be extracted, but is currently estimated
| 3.14 | Describe the methodology used to check for floating nodes in all analog cirucit and level-shifters in all modes of operation. | DELIVERED | OPEN | OPEN |  | Level shifters are carefully checked with any order opwer up and fast and slow rise times.
| 3.15 | Behavioral models verified against schematics. | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time.
| 3.16 | Specify the matching requirements and random offsets in the schematics for matching devices |  | OPEN
| 3.17 | Simulate all the required specifications with top down extracted views that include device, routing and mutual coupling parasitic. Include top down parasitic resistances along with capacitances |  | OPEN | OPEN
| 3.18 | For extracted simulations, include IR drop from the bias or reference blocks to the DUT. Use mannual extractions if automated checks are not feasible |  | OPEN | OPEN
| 3.19 | Identify nested feedback loops. Stability analysis needs to be run for every nested loop and not just for the outermost loop. Bandwidth consideration should be made to understand the dominant loop and it’s impact on overall performance |  | OPEN | OPEN
ESD, Quality & Reliability | 4.01 | Provide ESD protection design/layout methodology, guidelines, block diagram and milestone checkpoints | DELIVERED | OPEN | OPEN |  | The ESD-Report including detail on package current capabilities has been updated and can be downloaded from the project page.
| 4.02 | Ensure ESD protection structures have low resistances in discharge path. Run automated tool (e.g Pathfinder) and provide results. | DELIVERED | OPEN | OPEN |  | Carefull placement of ESD structures is done. Layout has not reached a state where automatic tools can be used.
| 4.03 | Provide latchup prevention methodology, guidelines and milestone checkpoints | DELIVERED | OPEN | OPEN |  | Latchup-checking is implemented in TSMC's DRC rules. Early design stage already include guardrings around the building blocks. Especially the ESD diode comes with build-in guardring stuctures. No extra plans beside that.
| 4.04 | Provide SOA (Safe Operating Area) curves for relevant transistors in the process (minimum VGS vs VDS capability), including TLP measurement results | DELIVERED |  |  |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | SOA (COA) simulations are done with (spice) models supplied by TSMC, see also support document "TiogaPass_SiliconChecklist_AnalogSupport_180906.pptx", Item #4.04 in Radar AI 44459265.
| 4.05 | Provide transient simulation results for relevant transistors in the process, overlayed onto curves from item # 4.4, to confirm that SOA limits are not exceeded |  | OPEN | OPEN
| 4.06 | Provide hot carrier injection (HCI) threshold and transistor gm drift effect prevention methodology | DELIVERED |  |  |  | Never considered this up to now, will be addressed. | Aging simulations (BTI, HCI) are done with (spice) models provided by TSMC (TMI models)
| 4.07 | Review simulations that cover circuit performance degradation due to aging (NBTI, PBTI) |  | OPEN | OPEN
| 4.08 | Provide description of methodology to prevent oxide and junction overstress in circuits with multiple oxide thicknesses and/or multiple junction voltage ratings. What tools are used? What work is done to ensure 100% compliance? | DELIVERED | OPEN | OPEN |  | The TSMC spice/spectre models (few month ago) are up/to/data and COA replaces SOA file. It uses the reliability tools from Cadence Spectre/Meastro. Regarding verification: TBs to check transient power up/down sequences (ev. DC operating point as well) are used to see if a node is stuck for a longer time.
| 4.09 | Provide details of electromigration analysis and verification for power and signal paths | DELIVERED | OPEN | OPEN |  | All individual sub-blocks and high level blocks will be simulated using Cadence/Spectre tool to ensure there is no EM issue.
| 4.1 | Provide description of the methodology for transient thermal analysis of complete system, to ensure maximum junction temperature rating is never exceeded. Review thermal simulation | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | On circuit level: EMIR/SHE flow in place based on TSMC simulation models. On die level: Hot-Spot flow is used
| 4.11 | What is isolation strategy for the ESD cells used ? Do they use dnw/nbl/n+/p+ or something else? | DELIVERED | OPEN | OPEN |  | Isolation of esd devices is based on massive p+/n+ guardrings and spacing todriver and receiver circuits.
Bandgap Simulation | 5.01 | Low VDD and cold startup for bandgap and oscillators |  | OPEN | OPEN
| 5.02 | Ensure no significant IR drop on the ground line between the voltage references and destination. |  | OPEN | OPEN
| 5.03 | Ensure Bandgap are placed away from die edges/corners and under bumps to minimize shift due to package/ball stress |  | OPEN
| 5.04 | Ensure robustness of bandgap start up by injecting interference at sensitive nodes and monitoring the recovery. There should not be a dynamic start-up circuit | DELIVERED | OPEN | OPEN |  | The robustness of BG start-up is ensured by determining that there is only one stable point in the system and by systematicly monitoring the settling of the system towards the stable points in presence of inteference in each of sensitive nodes.
| 5.05 | Power supply transient and step recovery in both directions, run this across both slow and fast ramps (N us to N ms) |  | OPEN | OPEN
Amplifier | 6.01 | Stability - phase margin and phase dips (within the bandwidth) vs. load current and capacitor over PVT range. Check poles and zeros over frequency range |  | OPEN | OPEN |  | Detailed small signal and large signal simulations will be carried out to ensure stable operaiton of the amplifiers under practical operating condition. Both corner and Monte Carlo simulations will be perfomed.
| 6.02 | Stability - check phase margin at signal common mode as well as max and minimum swing extremes. |  | OPEN | OPEN |  | Stability of all the CM feedback loops will be performed.
| 6.03 | Stability - check phase margin with no load in the case (R, C, or current). | DELIVERED | OPEN | OPEN |  | Stability of all the loops will be checked with minimum and maximum possible load.
| 6.04 | Stability - transient input and supply ping tests and check for common-mode and differential oscillations. Check at antenna load extremes (VSWR) for radio amplifiers. Transients should be checked with no load (R, C or current). |  | OPEN | OPEN |  | Detailed stability analysis will be run to ensure robust operation of analog blocks and amplifiers (step response, AC simulation, and K-factor test).
| 6.05 | PSR - measure with Amp along with LDO. Also confirm large signal (transient) PSR using drive sinewaves. |  | OPEN | OPEN |  | Small and large signal simulations including step and noise on supply will be performed.
Current Density | 7.01 | Ensure current density is within the process limits (RMS, Peak, average) | DELIVERED | OPEN | OPEN |  | Careful EM, IR, and self heating simulations will be performed to ensure being within the spec.
Comparator | 8.01 | Comparators often use inverters as final gain stages. Ensure that the stage which drives the inverter can swing rail-rail. |  | OPEN | OPEN |  | The operation of comparators will be simulated to avoid having floating nodes, or nodes with incomplete swing.
| 8.02 | The comparator gain should be high enough to drive hysteresis feedback node rail-to-rail for a small (~1mV) change in the input voltage. | DELIVERED | OPEN | OPEN |  | Hysteresis and offset of all the comparators will be carefully simulated.
| 8.03 | There should be no comparator output chatter or oscillation for a slow-moving input signal |  | OPEN | OPEN
| 8.04 | The hysteresis circuit should latch the input stage current or voltage change before output signal asserts, for both positive-going and negative-going input signals. |  | OPEN | OPEN
| 8.05 | Make sure that the comparator input state does not cause threshold voltage offset drift over time (bias offset) in all modes of operation or states |  | OPEN | OPEN
| 8.06 | If the comparator is dynamically enabled/disabled, check for possible charge injection through input capacitance, back into the reference input or resistor divider. |  | OPEN | OPEN
Spare Devices | 9.01 | In general, have a robust spare circuit methodology for components such as de-coupling cap, logic gates, transistors, resistors and level-shifters etc. | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | spare components: will be implemented during circuit design and can be used as active devices through (metal) spin. transistors: implemented as dummy devices to account for strain- and lithography effects (to improve matching behaviour) but also extra dummy devices which can be used as spare devices. de-coupling caps: implemented as dummy devices which can be connected to required nodes of circuit. resistors: spare resistors (in e.g. resistor ladder structures) will be considered. level-shifter: level-shifter for spare configuration bits inclusive buffers/inverters will be implmeneted in design.
Test | 10.01 | Insert test points (testability circuits) on critical circuits and nodes | DELIVERED | OPEN | OPEN |  | Using AMUX technique, all the ctitical signals (low frequency) can be observed either through a dedicated bump, or through an internal ADC.
| 10.02 | Verify that trimmability is built in wherever necessary and that trim range covers process variation. | DELIVERED | OPEN | OPEN |  | All the key blocks include enough trimmability (bias current, BW, impedance, reference voltage, etc).
| 10.03 | Ensure digital has scan coverage and analog blocks are isolated in scan mode. Ensure testmode has access to all signals at analog-digital boundary | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | digital control logic for IP is ATPG scan-able. Analog logic is covered by an ATPG shell to ensure that configuration of analog logic is stable during scan.
| 10.04 | Recommend to design in an externally supplied clock (ATE/board) to all modules with internal clocks | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | , see support document "TiogaPass_SiliconChecklist_AnalogSupport_180906.pptx", Item #10.04 in Radar AI 44459265.
Crystal Oscillator | 11.01 | Do not exceed the manufacturer specs amplitude for the XTAL for the simple inverter type topology |  | OPEN | OPEN |  | The oscillator will have a programmable amplitude control, which controls the voltage swing of the XTAL/MEMS resonator, thus limiting also the max. power
| 11.02 | Show startup behaviour with the worst case corner and actual crystal model |  | OPEN | OPEN |  | PVT corner simulations will be done for XTAL and MEMS resonator to insure the oscillators performance, including the startup behaviour
Mixed Signal | 12.01 | Group digital and analog circuits seperately so that the digital can be run separately using digital methodology |  | OPEN | OPEN |  | A careful hierarchy for analog/mixed signal parts of the system will be used in order to properly simulate mixed-mode blocks.
Coupling | 13.01 | Coupling between sensitive analog and digital signals should be checked at block and top level. (A simple check of load cap to coupling cap based on the RCX netlist can point to this if sensitive nodes are labeled in the schematics) | DELIVERED | OPEN | OPEN |  | Careful simulations based on extracted netlist will be performed in different levels of hierarchy in order to observe the effect of coupling between sensitive analog and digital signals.
| 13.02 | Label sensitive signals on the schematics with a commond name Methodlogy (***_Sensitive) and identify agressors and victims with top integration simulations in mind | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | signals which require specific consideration (e.g. high-speed, differential, clocks, shielded, low-parasitic, matching) in layout are marked in the schematics (signals are highlighted, notes added to signals)
| 13.03 | Confirm that all layer-layer coupling is extracted and correctly modelled for the extracted simulations. Include all top layers such as RDL, bump and Pads in extraction | DELIVERED | OPEN | OPEN |  | Extraction of each block is done including its own supply grid. If supply grid is not in the target hierarchy, higher level simulations will be ran in order to make sure the coupling efffect of all the top metal layers are included.
| 13.04 | Edge rate should be considered along with frequency of aggressor when looking into digital to analog coupling | DELIVERED | OPEN | OPEN |  | Mixed mode simulations will be ran in order to take into account the effect of edge rate.
PLL | 14.01 | Run the VCO with input connected to the supply and ensure the divider works. Divider must work at least 10% higher than the VCO frequency in each PVT corner |  | OPEN | OPEN |  | This check is part of our PLL verification.
| 14.02 | Add a watch-dog circuit to catch the run-away frequency of the PLL |  | OPEN | OPEN |  | For each PLL there is a digital frequency detector, that monitors operation of PLL in order to avoid PLL run away problem.
| 14.03 | At the startup, make sure to check that the common mode oscillations split into differential oscillations as expected for differential VCO |  | OPEN | OPEN |  | Generally,checked at pll toplevel startup sims. Might make sense to create an additional testbench with VCO/LDO due to large loopfilter time constant
| 14.04 | For the dividers that has un-used states, make sure that un-used states logically links to used states | DELIVERED | OPEN | OPEN |  | Divider is designed like that. This Check item is not limited to dividers.
| 14.05 | There shoundn't be any AC coupled buffers inside the loop | DELIVERED | OPEN | OPEN |  | Between VCO and first stage there is an AC coupling. All other blocks are either DC coupled or partial AC coupled (CML to CMOS as example)
| 14.06 | Check symmetry of phase detector under lock condition. Asymetry can result from the NAND gate in the PFD feedback path |  | OPEN | OPEN |  | NAND gate is symmetric in the schematic and layout. Electrical lock point check will be done (not only affected by PFD offset)
| 14.07 | For VCO phase noise/jitter simulation include LDO (with reference) as well if VCO is powered by one |  | OPEN | OPEN |  | LDO is part of phase noise simulations in our PLL verification flow. Roger: IS A MUST. Also included all bias networks (at some point the BG as well). LDO also contains bias filter network.
| 14.08 | For VCO phase noise/jitter simulation include noise file from PMIC/PMU and central bias. |  | OPEN | OPEN |  | Central bias generators are part of our PLL verification flow. Roger: PXF sims done to figure out transfer function from supply to the output of the VCO (includes again LDO)
| 14.09 | Make sure leakage of PLL loop filter capacitor is modeled & simulated |  | OPEN | OPEN |  | Using realistic model for the loop filter components and also run them in all the corners.
| 14.1 | If calibration/trimming needed for VCOs, ensure proper operation of the PLL over the entire voltage and temperature range |  | OPEN | OPEN |  | LC VCO is frequency tuned and has a digital amplitude control and will be carefully checked. In addition to this, margin is added.
| 14.11 | Provide stability analysis methodology & simulation results |  | OPEN | OPEN |  | Small signal/linear model for initial guess. More sophisticated model in Matlab/Tau (incl. noise (RJ,DJ) TF etc.). Step response in spectre sims, if possible.
| 14.12 | If PLL feedback divider ratio is very large, provide additonal simulation data to ensure stability & performance |  | OPEN | OPEN |  | See Item #14.11. PLL is programmable incl. CP/LF.
Level Shifter | 15.01 | Level shifter design methodology (how to make sure that models propagate X for relevant conditions) | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | level-shifters will not propagate undefined states, regardless of power-sequence or input state. This is guarenteed by design and verified by simulation
| 15.02 | Simulate with proper assertion of level shifter in reset and non-reset state and validate the outputs |  | OPEN | OPEN
| 15.03 | Consider all possible input signal side and level shifter supply scenarios during reset state simulations (Input signal status in reset state (asserted vs not asserted, voltage domain powered vs unpowered)) |  | OPEN | OPEN
| 15.04 | Dynamic supply ramping considerations (power-up and power-down), including the possibility of floating nodes and high frequency oscillation (during extracted simulations) |  | OPEN | OPEN |  | Level shifters are carefully checked with any order power up and fast and slow rise times.
| 15.05 | Are any of the level-shifters power-gated? Can the power gating result in floating nodes? |  | OPEN | OPEN |  | No power gating in the level shifters
| 15.06 | Provide details of topologies of all level-shifter used in the chip, including use case scenarios | DELIVERED | OPEN | OPEN |  | Schematic available.
| 15.07 | Do not directly use the complementry outputs from level shifters but if needed, regerate in the output supply domain |  | OPEN | OPEN |  | Complementary outputs will come from a double inversion.
High Voltage & Power Supply Designs | 16.01 | List down all the HV devices used in the design and their characteristics such as RDSON (with area relation), breakdown BVDSS etc | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | nch_18_max, pch_18_mac, nch_18ud12_mac, pch_18ud12_mac, pdio_hia18_mac, ndio_hia18_mac |  |  |  |  | RDSon ?
| 16.02 | Detail the latchup prevention and isolation strategy for the sensitive design. Highlight the bias strategy for the deep-nwell/NBL/NWELL etc | DELIVERED | OPEN | OPEN |  | The latchup strategie is the same for all circuits. It is based on massive guardrings around ESD devices, connected low resistive to power and ground. Spacing between ESD protection elements and actual circuits is also part of this strategie. This is compliant to TSMCs recommendations. |  |  | 2 | 4 |  | ESD Review done. need CDM paper calculation
| 16.03 | Provide the switching transients on the inductor node(/LX) for boost/buck designs and show whether they cross the BVDSS of the connected devices. Include all the parasitic in connection path for this analysis | DELIVERED | OPEN | OPEN |  | There is no switching regulator in our design. |  |  | n/a
| 16.04 | Provide details of slew rate(preferably programmable) control at LX node for EMI mitigation | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | LX node is the low-speed, dc-coupled bi-directional link connected to CIO module and Feed-through Path. Slew rate is limited (non-programmable) by setting rise/fall time (10-90%) to a MINIMUM of 2.5ns for low Crosstalk and EMI. |  | 1 | 1 | 2
| 16.05 | LX node ESD protection may require special consideration. Provide details of LX pin ESD design strategy | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | Stacked ESD diode structure used to account for cases when signal voltage reaches 4V. |  | 1 | 3 | 2 | ESD Review done. 4v i/p pin strategy detailed
| 16.06 | Confirm that HV devices well diodes point in right directions for Vin < Vout and Vin > Vout conditions | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | Chip is using HV-devices only in SBU (LX) interface (and TSMC std-IOs). For SBU-IF well-voltage control has been implemented for PMOS when voltage at PAD goes above supply, e.g 4V case |  | 1 | 3 | 2
| 16.07 | For power supply designs, highlight that how the default state is set during shutdown. For example, is there an active discharge at the VOUT node that ensures Vout < Vin? If that’s not true, is there a need for VMAX circuit if application requires Vout > Vin in certain cases? | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | for BIAS circuitry: if the BIAS is disabled (powerdown), transistors are enabled to drive internal nodes to defined states/voltages to prevent floating nodes
| 16.08 | Highlight methodology to handle tricky testmodes especially those that assume high-current operation (OCP), high sensitivity (low Rdson), closed loop operation (OCP, Vout accuracy etc.) | DELIVERED | OPEN | OPEN |  | This item will be addressed when at next project milestone (7/13/18) as the schematic hierachies will be completed at that time. | such effects are covered by running stress-simulation (stimulating the circuit in active state @ increased supplies) and aging simulation
Note on C4: Kickoff: Provide block diagram of ASIC Midterm: Final block diagram Final: No checking required unless change to block diagram
Note on C5: Kickoff: Highlight and Justify Midterm: Verify
Note on C6: Kickoff: Highlight and justify Midterm: Verify/justify all flip-flops without preset/scan Final: Ensure no change from Midterm and if changed verify and justify
Note on C7: Midterm: Alert of methodology Final: Verify HV lines are checked automatically and if manually, double check.
Note on C8: Kickoff: Alert of methology Midterm: Verify Final: Ensure no change
Note on C9: Kickoff: Alert methodology Midterm: Ensure debounce, loading, timing, drive strength, voltage/current compatibility meet requirements Final: Ensure debounce, loading, timing, drive strength, voltage/current compatibility meet requirements.
Note on C10: Midterm : Provide schematic simulations Final : provide LPE simulations results
Note on C11: Kickoff: Alert of how correlation is done Midterm: Provide data of devices are used or not shared during Kickoff Final: Ensure no change
Note on C12: Kickoff: Provide methodology Midterm: Verify that no latches are used. If unavoidable, explain Final: Make sure no change
Note on C13: Kickoff: Provide full table with expected simulations to match spec compliance Midterm: Simulations must be complete for schematic level Final: Simulations must be complete for extracted. Table should cover: - Abs max ratings - Electrical specifications and conditions - Tables - Timing diagrams - State diagrams - Descriptions of operation
Note on C14: Kickoff: Provide methodology Midterm: Provide DC operating and ensure transistors are in intended regions of operations Final: Ensure no change
Note on C15: Kickoff: Provide methodology Midterm: Provide stability reports of schematic view over PVT Final: Provide stabilty reports of extracted netlist over PVT
Note on C16: Kickoff: Provide methodology Midterm: None Final: Provide Parasitic coupling report.
Note on C17: Kickoff: Provide methodology Midterm: Review schematics to ensure matching sensitive circuits don't use minimum devices size. If minimum devices are used, ensure leakage is not a concern. Final: Review any changes
Note on C18: Kickoff: Provide methodology Midterm: Verify simulations run on actual schematic Final: Verify simulations run on actual schematic with extracted netlist
Note on C19: Midterm: Review simulations Final: Review simulations
Note on C20: KickOff: Review methodology. Midterm: Review simulations Final: Review simulations
Note on C21: Kickoff: Provide methodology Midterm: Review simulations Final: Review simulations
Note on C22: Kickoff: Provide list of corners and methodology Midterm: Review simulations with all corners Final: Review simulations with all corners Preferred: Each Block's Simulation Report has a full page with table describing all corners run for the block and highlights which corners are worse case for that block and key specs for that corner.
Note on C23: Kickoff: Provide methodology Midterm: Provide schematics and simulations under all possible power up scenarios Final: Provide extracted simulations under all possible power up scenarios
Note on C24: Kickoff: Provide methodology Midterm: Verify simulations run on actual schematic Final: Verify simulations run on actual schematic with extracted netlist Check different ramp rates: 0.1V/us, 1V/us, 10V/us
Note on C25: Kickoff: Provide methodology Midterm: Verify simulations run on actual schematic Final: Verify simulations run on actual schematic with extracted netlist Confirm system spec is met (typically 2us for radio circuits)
Note on C26: Kickoff: Identify all external components, key parasitic parameters and where vendor will obtain the model Midterm: Schematic simulations with full model of external compoenent Final: Extracted simulations with full model of external compoenent
Note on C27: Kickoff: Provide methodolgy of simulating test modes. Midterm: Provide simulations schematic based Final: Provide simulations with extracted netlist.
Note on C28: Kickoff: Provide methodology of relesing clock from oscillator and/or PLL until stabilization. Midterm: Provide schematic based simulations showing clock is not released until stable Final: Provide extracted netlist simulations showing clock is not released until stable
Note on C29: Kickoff: Provide methodology of ensuring interface signal in unknown state will propagate unknown in digital. Midterm: Show simulations
Note on C30: Kickoff: Provide Methodology. Ensure Vendor can get loading and package models Midterm: Check Simulations Final: Check Simulations with extracted netlist
Note on C31: Kickoff: Provide Methodology Midterm: Ensure no floating nodes or if there any, it does not go to a gate of a transistor Final: Ensure no changes.
Note on C32: Kickoff: Provide methodology of modeling and verifying analog block in full chip simulations Midterm: Review simulations of behavioral vs. schematic based Final: Ensure no changes
Note on C37: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results. Provide block diagram detailing protection structures (diodes, clamps, back-to-back diodes) for each analog I/O. Final: Review final implementations with detailed simulations/results of the implementaiton. Provide updated block diagram for reference.
Note on C38: KickOff: provide methodology and tools used. Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C39: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C40: Kickoff: Provide SOA check methodology, guidelines and details of tools/simulations to check the SOA simulatons
Note on C41: Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C42: Kickoff: Provide methodology, guidelines and details of tools/simulations that will be performed
Note on C43: Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C44: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C45: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C46: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C47: Kickoff: Provide methodology, guidelines and tools/flows Midterm: Review detail of scheme and intermediate results Final: Review final implementations with detailed simulations/results of the implementaiton
Note on C48: MidTerm: Show schematic simulations Final: Show layout extracted simulations
Note on C49: Midterm: Plan for low IR drop on ground lines Final: Ensure low IR drop
Note on C50: Midterm: Floorplan should show bandgap is away from corner.
Note on C51: Kickoff: Review methodology Midterm: Show schematic simulations Final: Show extracted simulations
Note on C52: MidTerm: Show schematic simulations Final: Show layout extracted simulations
Note on C53: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C54: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C55: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C56: KickOff: provide methodology Midterm: provide simulation results on actual schematic Final: provide simulation results on extracted view.
Note on C57: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C58: Kickoff: Review methodology Midterm: Show schematic simulations Final: Show extracted simularions over corners
Note on C59: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C60: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C61: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C62: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C63: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C64: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C65: Kickoff: Review methodology Midterm: Show schematics Final: Show layouts
Note on C66: KickOff : Review methodology Midterm : Review the implementation Final Review : Review the implementation
Note on C67: KickOff : Review methodology Midterm : Review the implementation Final Review : Review the implementation
Note on C68: KickOff : Review methodology Midterm : Review the implementation Final Review : Review the implementation
Note on C69: KickOff : Review methodology Midterm : Review the implementation Final Review : Review the implementation
Note on C70: MidTerm: Show schematic simulations Final: Show layout extracted simulations
Note on C71: MidTerm: Show schematic simulations Final: Show layout extracted simulations
Note on C72: Midterm : Provide schematic implementation details Final Review : Provide layout implementation details
Note on C73: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C74: Kick Off : Provide methodology or design practices Midterm : Provide Schematic Details Final Review :Provide Layout Details
Note on C75: KickOff: Provide methodology & table
Note on C76: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C77: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C78: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C79: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C80: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results Example Case : A Divide-by-5 counter built with 3 Flip-flops, using 5 states but remaining 3 states aren't well defined.
Note on C81: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C82: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C83: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C84: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C85: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C86: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C87: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C88: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C89: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C90: Midterm : Provide Simulation results Final Review : Provide simulation results
Note on C91: Midterm : Provide Simulation results Final Review : Provide simulation results
Note on C92: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C93: Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C94: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C95: Midterm : Provide implementation details and Simulation results Final Review : Provide LPE simulation results
Note on C96: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C97: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C98: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C99: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C100: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C101: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C102: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results
Note on C103: Kick Off : Provide methodology or design practices Midterm : Provide Simulation results Final Review : Provide LPE simulation results

## Digital Chip
[13 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions June 2018 | Comments/Questions August 2018 | Deliverables | RT Logic Comments/Questions Nov 2018 | Jan'19 F2F | Effort | Risk | Readiness
Digital Design | 1.01 | Top-level Architecture review | 2017-12-15 | continuing |  | OPEN | David | Closed except for CIO. Design Reviews complete for all blocks except CIO (scheduled July/2018). Will mark closed after CIO Review. |  | Architecture Spec v1.30 published 6/11/2018 captures results of mid-term reviews. Architecture Spec v1.40 published on 8/10/2018. | Closed for RT Logic. Architecture Spec v1.30 published 6/11/2018 captures results of mid-term reviews conducted May/2018. Architecture Spec v1.40 published on 8/10/2018.
| 1.02 | List of clocks and resets (external and internal) | 2017-12-15 | 2018-09-30 |  | OPEN
| 1.03 | Clock architecture block diagram & clock gating descriptions | 2017-12-15 | 2018-09-30 |  | OPEN
| 1.04 | POR Review and Synchronization | 2017-12-15 | 2018-09-30 |  | OPEN
| 1.05 | Details on Reset & Power-up sequence, any special programming sequence | 2017-12-15 | 2018-09-30 |  | OPEN
| 1.06 | Analog/Digital boundary signals | 2018-10-30 | 2018-11-30 |  | OPEN |  | Initial Analog/Digital contract spreadsheets complete and under revision control. Frozen and subject to change management process control at tape out minus 3 months. |  |  | Initial Analog/Digital contract spreadsheets complete and under revision control. Frozen and subject to change management process control at tape out minus 3 months.
| 1.07 | Performance and bandwidth calculations | n/a | n/a |  | NA |  | Performance and bandwidth is determined by supported specifications defined by PRD. |  |  | Closed for RT logic. Performance and bandwidth is determined by supported specifications defined by PRD.
| 1.08 | Spare Gate Methodology | n/a | n/a |  | NA |  | Design will comply with internal requirements. |  |  | Closed for RT logic. GA fill provides spare gates for digital logic.
| 1.09 | Chip/System reviews | 2017-12-15 | continuing |  | OPEN |  | Chip/System architecture has been documented in Architecture Spec Rev 1.30. Review with Seeb has been ongoing. |  | Will close these upon signoff of Architecture Spec Rev 1.30. | Closed for RT logic. Chip/System architecture has been documented in Architecture Spec Rev 1.30/1.40. Review with Seeb has been ongoing.
| 1.1 | Revision planning | 2017-12-15 | continuing |  | OPEN |  | Chip revision plan has been documented and reviewed with Seeb. |  |  | Closed for RT logic. Chip revision plan has been documented and reviewed with Seeb.
| 1.11 | Review device interfaces and ensure conformity with system application | 2017-12-15 | continuing |  | OPEN |  | Device interfaces determined by supported specifications defined by PRD. Review with Seeb has been ongoing. |  |  | Closed for RT logic. Device interfaces determined by supported specifications defined by PRD. Review with Seeb has been ongoing.
Item 1,06 relating to memory in v3.2 is N/A for TP and not included
Micro-Architecture | 2.01 | Accurate/Detailed documentation at the block level of the design |  | 2018-09-30 |  | OPEN |  | Closed except for CIO. Detailed Design Documentation for XBAR, USB, DP is complete. Preliminary documentation for MCX is complete. MCX,CIO Detailed Design Documentation will be completed by end of July 2018. Register map will be frozen and subject to change management process control at tape out minus 3 months. |  |  | Closed except for CIO (targert date Nov 30, 2018). Detailed Design Documentation for XBAR, USB, DP, MCX is complete. CIO Detailed Design Documentation will be is in progress. Register map will be frozen and subject to change management process control at tape out minus 3 months.
| 2.02 | List modes of operation & expected behavior |  | 2018-09-30 |  | OPEN
| 2.03 | Table of architecture & design assumptions |  | 2018-09-30 |  | OPEN
| 2.04 | Register Specification |  | 2018-09-30 |  | OPEN
| 2.05 | Complete register map review and signoff across all stakeholders |  | 2018-09-30 | 2019-02-15 | OPEN
| 2.06 | Table of Interrupt & Error sources & handling mechanisms |  | 2018-09-30 |  | OPEN
| 2.07 | Detailed Performance & Power specifications |  | 2018-09-30 |  | OPEN |  | Initial power specifications are included with chip power estimates. This will be updated as needed until RTL complete. |  | Power estimates from synthesis have been provided in chip power estimates and will be updated as needed. | Power estimates from synthesis have been provided in chip power estimates and will be updated as needed.
| 2.08 | List of Arbitration points in the design |  | n/a |  | OPEN
| 2.09 | List of back pressure mechanisms supported in the design |  | n/a |  | OPEN
Item 2,06 of v3.2 is N/A for TP as Kandou does not have Apple models and so not included
Power | 3.01 | Review power requirements for digital from specification | 2017-12-15 |  |  | OPEN |  | Initial digital power specifications are included with chip power estimates. As documented in Architecture Specification, power reduction in digital domain is based on clock gating. All digital logic is powered on VDDD. |  | Clock gating reviewed as part of Block Design Reviews. Design Reviews have been completed on all blocks except CIO (scheduled July 2018). | Closed for RT logic except CIO (targert date Nov 30, 2018). Clock gating reviewed as part of Block Design Reviews. Design Reviews have been completed on all blocks except CIO (scheduled Nov 2018).
| 3.02 | Review power reduction methodology/techniques (clock gating, oscillator shutdown, analog shutdown etc) | 2017-12-15 |  |  | OPEN
| 3.03 | Review power domain crossings and power intent | n/a | n/a |  | NA
| 3.04 | List of Power gating & Clock gating domains if applicable. | n/a | n/a |  | NA
| 3.05 | Low power mode (sleep/shutdown mode). Simulate enter and exit plan for low power mode |  | 2018-09-30 | 2019-02-15 | OPEN |  | Initial simulations based on behavior models of analog by 7/31; based on analog netlist simulations by 11/30.
| 3.06 | Run CAD-tool based power analysis and verify power goals are met |  | 2018-09-30 | 2019-02-15 | OPEN |  | Initial power analysis based on P&R tools has been performed and results included in chip power estimation. Initial Voltus analysis by 11/30. |  |  | Closed for RT logic. Power analysis based on P&R tools has been performed and results included in chip power estimation.
RTL | 4.01 | Review block level checklists, change block list, and versions of all blocks |  | 2018-09-15 | 2019-04-25 | OPEN |  | Design Reviews for all blocks completed by 6/30. Tape out readiness review for all blocks completed by 11/30. |  |  | Closed for RT logic except CIO (targert date Nov 30, 2018). RTL is > 95% complete for all blocks; subject only to bug fixes. CIO review and documentation are pending; all RTL coded except for bug fixes.
| 4.02 | RTL review of blocks that changed (Diff with previous version) |  | 2018-09-15 | 2019-04-25 | OPEN
| 4.03 | Lint reports (latches, combinatorial loops, LHS/RHS mismatches, etc.) |  | 2018-09-15 | 2019-04-25 | OPEN
| 4.04 | Simulator compile log files (check warnings/errors) |  | 2018-09-15 | 2019-04-25 | OPEN
| 4.05 | RTL interfacing with SoC, including block level testbench for co-sim |  | 2018-09-15 | 2019-04-25 | OPEN |  | All blocks require designer testbench.
| 4.06 | RTL 75% complete milestone |  | 2018-04-30 | 2018-07-31 | OPEN |  | All RTL functions except CIO have been coded. CIO complete scheduled July 2018. RTL Freeze and subject to change management process control at tape out minus 3 months. | CIO RTL completed, with the exception of the updates received on Aug 2 2018.
| 4.07 | RTL 95% complete milestone |  | 2018-07-31 | 2018-10-31 | OPEN
| 4.08 | RTL Freeze |  | 2018-10-31 | 2019-02-15 | OPEN
Synthesis & Timing Constraints | 5.01 | Synthesis constraints, I/O constraints and overconstrained paths |  | 2018-09-28 | 2019-01-30 | OPEN |  | Constraints available and synthesis runs in progress. Constraints will be reviewed again before final integration phase. |  |  | Mid-term review closed for RT Logic. Constraints available and synthesis runs ongoing with no issues. Constraints will be reviewed again before final integration phase.
| 5.02 | Clock constraint checks |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.03 | Exceptions, multi-cycle paths and false paths with descriptions |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.04 | Confirm bussed signals are not bit blasted |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.05 | Synthesis log files |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.06 | Synthesis QoR |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.07 | Chip Interface Timing |  | 2018-09-28 | 2019-01-30
| 5.08 | Block level interconnect timing |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.09 | RTL -> netlist LEC results |  | 2018-09-28 | 2019-04-15 | OPEN |  | To be reviewed after timing closure of mock and production TO |  |  | Mid-term review closed for RT Logic. To be reviewed after timing closure of mock and production TO
| 5.1 | Netlist checks (latches, combinatorial loops, name rules, etc.) |  | 2018-09-28 | 2019-04-15 | OPEN
| 5.11 | Library chacterization at proper voltages and temperatures and QA of various views for all IPs |  | 2018-09-28 | 2019-01-30 | OPEN |  | To be done latest at midterm review, reviewed again before final integration phase. |  |  | Mid-term review closed for RT logic, reviewed again before final integration phase.
| 5.12 | Liberty file (.lib) review of boundary constraints |  | 2018-09-28 | 2019-01-30 | OPEN
| 5.13 | Top-level timing (including IOs) should be accounted for in digital synthesis constraints |  | 2018-09-28 |  | OPEN
Clock Domain Crossing | 6.01 | CDC Methodology and Architecture review |  | 2018-08-15 | 2019-02-15 | OPEN |  | CDC implementation reviewed in Design Reviews for all blocks except CIO (scheduled July 2018). Detailed CDC reviews will be completed by 9/30. |  |  | Mid-term review closed for RT logic except CIO (targert date Nov 30, 2018). Block level CDC analysis performed using Jasper tool. Results documented and reviews conducted. Actions closed. Final review will be conducted at macro level.
| 6.02 | CDC Constraints |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.03 | CDC protocol assertions |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.04 | CDC report (chip level) |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.05 | CDC waivers |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.06 | Ensure flops used as synchronizers have high MTBF | 2017-12-15 |  |  | OPEN |  | Flop selection same as GW16. Can be closed.
| 6.07 | Are there any CDC waivers from prior designs/IPs. If yes, complete justification for current design |  | n/a | n/a | OPEN
| 6.08 | Ensure that register drives the first flop in the synchronizer. If there is combinatorial logic to first flop, verify effect of potential glitches on downstream path from synchronizer |  | 2018-08-15 | 2019-02-15 | OPEN |  | CDC implementation reviewed in Design Reviews for all blocks except CIO (scheduled July 2018). Detailed CDC reviews will be completed by 9/30.
| 6.09 | Verify there is no logic in the path to 2nd flop in synchronizer pair |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.1 | Check synchronization of external/off-chip async signals |  | 2018-08-15 | 2019-02-15 | OPEN
| 6.11 | Reset Domain Crossing (RDC) checks |  | 2018-08-15 | 2019-02-15 | OPEN
DFT | 7.01 | DFT methodology review - BIST, Scan, A-D Interface, IP, Spare/ECO flops | 2018-10-31 |  |  | OPEN |  | Plan covers digital/SerDes/analog block testability; Spare/ECO flops, I think it is related to scan hook of spare flops(cells)?? Spare gate methodology is described in 1.08. |  |  | Discussed in F2F. Document dft_slides_f2f_Nov2018_v4.0.pptx uploaded in Radar AI 45987965.
| 7.02 | Test plan | 2018-09-15 |  | 2019-01-30 | OPEN |  | Test plan includes all the possible tests targeted for ATE. It covers digital/SerDes/analog blocks and basd DFT/Analog IP strategy. |  |  | Discussed in F2F. Document dft_slides_f2f_Nov2018_v4.0.pptx uploaded in Radar AI 45987965.
| 7.03 | Verify BIST via post-layout simulations |  | 2018-01-31 | 2019-03-31 | OPEN |  | BIST simulations are from SerDes (pad loop back) & External loop back.
| 7.04 | DFT coverage review |  |  | 2018-01-31 | OPEN |  | Coverage review targeted before RTL sign-off |  |  | First pass is done and document available atpg_cov_analysis_12Sept18_snapshot.pdf
| 7.05 | Analog IP test strategy | 2018-09-15 |  | 2018-01-31 | OPEN |  | Analog IP test strategy targeted to close by end July so that implementation/simulation can be done before end October (SerDes IP close) |  |  | Discussed in F2F. Document dft_slides_f2f_Nov2018_v4.0.pptx uploaded in Radar AI 45987965.
| 7.06 | ATPG vectors - simulations at full chip level with SDF backannotation |  |  | 2019-04-25 | OPEN |  | SerDes IP: Before end of October
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Power | 3.02 | Review power reduction methodology/techniques (clock gating, oscillator/PLL shutdown, analog shutdown etc) (v3.2/3,02) | 2017-12-15 |  |  | OPEN |  | Initial digital power specifications are included with chip power estimates. As documented in Architecture Specification, power reduction in digital domain is based on clock gating. All digital logic is powered on VDDD. |  | Clock gating reviewed as part of Block Design Reviews. Design Reviews have been completed on all blocks except CIO (scheduled July 2018). | Closed for RT logic except CIO (targert date Nov 30, 2018). Clock gating reviewed as part of Block Design Reviews. Design Reviews have been completed on all blocks except CIO (scheduled Nov 2018).
DFT | 7.07 | Fault coverage analysis (fault grading) at analog-digital and IP-digital boundary (v3.2/7,05) |  |  | MMDDYY
Note on C4: - Clock and Reset Generation logic should be logically partitioned in a separate block
Note on C5: Should include: - List of all clock, sources, periods and duty cycles - Generated clocks and sources - Inter-clock relationships
Note on C6: - Confirm digital core is reset until oscillator is stable (verify with simulation) - Review oscillator enable start and stop for lockup scenarios - Perform an assessment of all POR signals in the design and their synchronization wrt peripheral clock domains - During Kickoff, evaluate the use cases for POR and brownout scenarios in the context of system traffic on the peripherals - As a good practice, designs may consider by default to add synchronization logic for all clocks and then take out this logic when it is not needed on a clock-by-clock basis - Review GPIO defaults at POR and across all power modes (including supply brownout). Ensure conformity with system across all power conditions
Note on C7: - Powerup, power down and brownout scenarios - Clearly document illegal power sequence combinations
Note on C8: Analog/Digital boundary signals. Review "A-D Contract" worksheet for detailed information - Signal contract for all interface signals, behavior (level, edge, can glitch) and electrical specifications (.lib, source/destination power rails, level shifters, drive strength, loading and timing). - Ensure analog inputs have debounce (glitch prevention) logic inside digital - Outputs going into analog which must NOT glitch should be registered - Ensure all outputs have appropriate drive buffer for given loading - Check voltage/current compatibility of boundary ports - Check POR and powerdown values on level-shifter/isolation cell outputs are valid across all operating modes - All boundary signals between physical partitions should be registered
Note on C9: For example: Data Path BW, memory BW, etc. if applicable
Note on C10: Spare Gates: - explain spare gate methodology. Include appropriate spare types and density - After P&R, review placement of spares and ensure uniform distribution
Note on C11: Chip/System Reviews: - Has digital designer been included in system-level design reviews/meetings - Understand implication of analog behavior and any changes in analog on digital
Note on C12: - Ensure that device ID and I2C revision ID are not hard-coded inside the digital core (recommend using tie-off cells and utilize higher metal layers for ECO's) - Tie these with higher metal layers
Note on C13: - Review choice of IO buffers used in interfaces. Ensure the IO buffers meet system specs eg I2C IOs should incorporate glitch suppression and a Schmitt trigger for SCL/SDA - Review interface timing. Timing will influence IO buffer choice - Check IO pad voltage inside device and bus voltage in system - If voltages are not same, check leakage power in IOs - Is fail-safe operation needed - check if IO pins need pullup/pulldown and the value. Align value with system/application
Note on C15: This should include, but not be limited to, the following: - Block Diagram - Functionality - Dataflow - Clocking - Interfaces - Physical Dimensions
Note on C16: - Outline known implementation specific exposure windows - Key timing diagrams, state machines, interfaces, protocol, deviations from standard specs
Note on C18: Include atleast the following: - Register map - Register descriptions, reset values
Note on C19: - For MDR, ensure register definitions, control bits and register placement is inline with system and FW usage - For FDR, review register map in conjunction with detailed device functionality captured in the datasheet
Note on C21: - Power estimates in all modes of operation - Assumptions made in power estimation - Process corners used for power calculations - Power budgeting for chip - list analog and digital power - Target power budgets for each supply
Note on C22: Examples include: - Bus arbitration - Chip interfaces
Note on C23: Examples: - Underflow/overflow mechanisms - Video/audio datapath - Network datapath
Note on C27: - Ensure the default state of cells crossing power domains (isolation cells, level shifters) is correct across all operating modes the device will see in system
Note on C30: Run power analysis at the following stages: - RTL 90% complete - Gate-level with timing-closed SDFs - Ensure final power numbers are calculated with vcd's from representative simulations
Note on C32: - Ensure that design adheres to RTL coding guidelines - Review coding guidelines with Apple
Note on C35: Deliverable: a representative compile log from a simulation which show warnings, file names, and test logging.
Note on C36: If chip interfaces with another chip on a unique interface (other than I2C or SPI for example), then we need to run a co-simulation in-house to verify compatibility.
Note on C39: After this date, the RTL will not change, ECO's only. All FIXME's resolved
Note on C41: Synthesis constraints - ensure constraints are defined at legal points - ensure all sequential elements and memories are 100% constrained - ensure all i/o and ports are constrained
Note on C42: - Confirm source points of all generated clocks - Confirm edge relationship of generated clocks - Ensure correct clock group attributes being used: asynchronous, logically exclusive and physically exclusive - Check all the defined clocks being propagated to the intended destinations properly - Ensure no clock signals are used in datapath
Note on C43: - Check formal verification of exceptions - mcps and false paths
Note on C44: Ensure netlist from synthesis is compatible with all downstream tools
Note on C47: - Chip Interface Timing Constraints should accurately reflect setup/hold/prop delays/load/slew conditons for the interface pins as per spec and board topology - Take into account device use conditions in the system during creation of chip-level timing constraints for interfaces. Align with Apple system teams over usage of standards for the particular application. This applies even to standard interfaces like SPI and I2C
Note on C48: - Ensure top-level parasitic delays are accounted for during block time budgeting - this applies to block-block timing and top-interface timing constraints - Take into account delays through analog cells in block timing budgets
Note on C49: Formal Verification: - Run FV between RTL and synthesized netlist - Run FV between digital netlist in top-level schematic and RTL
Note on C52: Confirm all analog to digital timing arcs are included in the .lib file. Confirm timing budgets and assumptions are correct
Note on C55: - Schematics for each type of clock domain crossing implementation with timing waveforms. - CDC re-synchronized or considered static. - Asynchronous inputs synced or verified as static. - Clock reset to low state at POR to allow clock gating cells to wake up in a known state - Register all signals crossing clock boundaries at source - Pay attention to signals generated (or ending in) black boxes. Verify these are covered during CDC checking - Ensure that synchronizer logic is well covered in DV by introducing uncertainty in the signal propagation delays through synchronizers. Randomize this delay to be either 2 or 3 cycles and ensure downstream logic works in both scenarios - Perform netlist-level CDC checks in both functional and DFT modes
Note on C56: - Ensure clock directive used in CDC constraints is consistent with synthesis constraints
Note on C57: Ensure signal reconvergence check is enabled in CDC setup. Check level of reconvergence
Note on C59: - Check waivers on false paths - Ensure CDC directives like quasi-static signals, gray coding etc can be validated using DV assertions
Note on C60: Instantiate either synchronizer cell or two-flop cells in RTL - do not use inferred double flop. For two-flop combination, use explicit naming convention to identify these as synchronizers. This will facilitate placement checks
Note on C61: - If there are any CDC waivers captured from previous designs, revisit these in context of clocking scheme in current design
Note on C65: Review and verify all RDC scenarios where reset signal generated in one domain can create a potential metastable condition in another domain. This typically occurs when launch and capture domains have different reset signals
Note on C66: Review and verify all RDC scenarios where reset signal generated in one domain can create a potential metastable condition in another domain
Note on C67: Understand the overall DFT methodology - Muxing scheme for test clocks and preset/clear - block all free running internal clocks - control for asynchronous presets and clears - Check design requirements to run scan at desired frequency - bypass input filters on input pins (I2C) - push-pull driver instead of open-drain on output pins (I2C) - scan data out buffer should be able to support fast speeds during scan (10-20 MHz) - For test time optimization, identify bypass modes to speed up very slow timers - Ensure all on chip oscillators are off during scan mode - Ensure that analog inputs to digital are muxed to 0/1 during scan mode - Ensure that digital outputs to analog are muxed to a safe state during scan mode - For designs that are not fully synchronous, what is plan for testing non-scan logic - For outputs to NVM / EEPROM, gate off the EN, WR, RD signals in scan mode - For IDDQ measurement, ensure that the digital core is isolated so power supply can be supplied by tester directly.
Note on C68: At kick-off and final review: - Include details on trim, analog test and digital tests - Include inputs from validation and test in design and DFT planning - Make sure that test modes and trim functionality is verified in simulations
Note on C69: At Final Design Review: Make sure BIST simulations pass on final design netlist. Use parasitic information via backannotated SDF This check may appear in multiple tabs
Note on C70: Stuck at fault coverage > 98% Transition fault coverage > 85%
Note on C71: At kick-off: - Plan on Analog IP test strategy - The Analog test strategy may also be covered during the Analog review At final review: - Review Analog IP test strategy
Note on C72: - Ensure availibilty of vectors in time for ATE testing - List any exceptions/checks which will not be covered by ATPG vectors
Note on C83: - identify all nodes between IP-digital and analog-digital which are not covered by scan. Check test coverage of critical nodes through functional vectors

## Digital SerDes
[11 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Jan'19 F2F | Comments | Deliverables | Effort | Risk | Readiness
Digital Design | 1.01 | Top-level Architecture review | 2018-02-01 | continuing |  | OPEN | Klaas
| 1.02 | List of clocks and resets (external and internal) | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.03 | Clock architecture block diagram & clock gating descriptions | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.04 | POR Review and Synchronization | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.05 | Details on Reset & Power-up sequence, any special programming sequence | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.06 | Analog/Digital boundary signals | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.07 | Performance and bandwidth calculations | NA | NA |  | NA
| 1.08 | Spare Gate Methodology | 2018-02-01 | 2018-11-30 |  | OPEN
| 1.09 | Chip/System reviews | 2018-02-01 | continuing |  | OPEN
| 1.1 | Revision planning | 2018-02-01 | continuing |  | OPEN
| 1.11 | Review device interfaces and ensure conformity with system application | 2018-02-01 | continuing |  | OPEN
Item 1,06 relating to memory in v3.2 is N/A for TP and not included
Micro-Architecture | 2.01 | Accurate/Detailed documentation at the block level of the design |  | 2018-12-31 |  | OPEN
| 2.02 | List modes of operation & expected behavior |  | 2018-12-31 |  | OPEN
| 2.03 | Table of architecture & design assumptions |  | 2018-12-31 |  | OPEN
| 2.04 | Register Specification |  | 2018-12-31 |  | OPEN
| 2.05 | Complete register map review and signoff across all stakeholders |  | 2018-12-31 | 2019-02-01 | OPEN
| 2.06 | Table of Interrupt & Error sources & handling mechanisms |  | 2018-12-31 |  | OPEN
| 2.07 | Detailed Performance & Power specifications |  | 2018-12-31 |  | OPEN
| 2.08 | List of Arbitration points in the design |  | 2018-12-31 |  | OPEN
| 2.09 | List of back pressure mechanisms supported in the design |  | 2018-12-31 |  | OPEN
Item 2,06 of v3.2 is N/A for TP as Kandou does not have Apple models and so not included
Power | 3.01 | Review power requirements for digital from specification | 2018-02-01 |  |  | OPEN
| 3.02 | Review power reduction methodology/techniques (clock gating, oscillator shutdown, analog shutdown etc) | 2018-02-01 |  |  | OPEN
| 3.03 | Review power domain crossings and power intent | 2018-02-01 | 2018-11-30 | 2019-02-15 | OPEN
| 3.04 | List of Power gating & Clock gating domains if applicable. | 2018-02-01 | 2018-11-30 | 2019-02-15 | OPEN
| 3.05 | Low power mode (sleep/shutdown mode). Simulate enter and exit plan for low power mode |  | 2018-11-30 | 2019-02-15 | OPEN
| 3.06 | Run CAD-tool based power analysis and verify power goals are met |  | 2018-11-30 | 2019-02-15 | OPEN
RTL | 4.01 | Review block level checklists, change block list, and versions of all blocks |  | 2018-11-30 | 2019-02-28 | OPEN
| 4.02 | RTL review of blocks that changed (Diff with previous version) |  | 2018-11-30 | 2019-02-28 | OPEN
| 4.03 | Lint reports (latches, combinatorial loops, LHS/RHS mismatches, etc.) |  | 2018-11-30 | 2019-02-28 | OPEN
| 4.04 | Simulator compile log files (check warnings/errors) |  | 2018-11-30 | 2019-02-28 | OPEN
| 4.05 | RTL interfacing with SoC, including block level testbench for co-sim |  | 2018-11-30 | 2019-02-28 | OPEN
| 4.06 | RTL 75% complete milestone |  | 2018-11-30 |  | OPEN
| 4.07 | RTL 95% complete milestone |  | 2019-01-15 |  | OPEN
| 4.08 | RTL Freeze |  |  | 2019-02-28 | OPEN
Synthesis & Timing Constraints | 5.01 | Synthesis constraints, I/O constraints and overconstrained paths |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.02 | Clock constraint checks |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.03 | Exceptions, multi-cycle paths and false paths with descriptions |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.04 | Confirm bussed signals are not bit blasted |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.05 | Synthesis log files |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.06 | Synthesis QoR |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.07 | Chip Interface Timing |  | 2018-11-30 | 2019-02-28
| 5.08 | Block level interconnect timing |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.09 | RTL -> netlist LEC results |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.1 | Netlist checks (latches, combinatorial loops, name rules, etc.) |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.11 | Library chacterization at proper voltages and temperatures and QA of various views for all IPs |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.12 | Liberty file (.lib) review of boundary constraints |  | 2018-11-30 | 2019-02-28 | OPEN
| 5.13 | Top-level timing (including IOs) should be accounted for in digital synthesis constraints |  | 2018-11-30 |  | OPEN
Clock Domain Crossing | 6.01 | CDC Methodology and Architecture review |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.02 | CDC Constraints |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.03 | CDC protocol assertions |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.04 | CDC report (chip level) |  | 2018-11-30 | 2019-02-28 | OPEN
| 6.05 | CDC waivers |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.06 | Ensure flops used as synchronizers have high MTBF | 2018-02-01 |  |  | OPEN
| 6.07 | Are there any CDC waivers from prior designs/IPs. If yes, complete justification for current design |  | NA | NA | OPEN
| 6.08 | Ensure that register drives the first flop in the synchronizer. If there is combinatorial logic to first flop, verify effect of potential glitches on downstream path from synchronizer |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.09 | Verify there is no logic in the path to 2nd flop in synchronizer pair |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.1 | Check synchronization of external/off-chip async signals |  | 2018-11-30 | 2019-02-15 | OPEN
| 6.11 | Reset Domain Crossing (RDC) checks |  | 2018-11-30 | 2019-02-15 | OPEN
DFT | 7.01 | DFT methodology review - BIST, Scan, A-D Interface, IP, Spare/ECO flops | 2018-10-31 |  |  | OPEN |  |  | Discussed in F2F. Document wp16_dft_and_test_v1.01.pdf
| 7.02 | Test plan | 2018-09-15 |  | 2019-01-15 | OPEN |  |  | Please refer to the same item in Digital Chip.
| 7.03 | Verify BIST via post-layout simulations |  | 2018-01-15 | 2019-03-15 | OPEN
| 7.04 | DFT coverage review |  |  | 2018-01-31 | OPEN
| 7.05 | Analog IP test strategy | 2018-09-15 |  | 2018-01-31 | OPEN |  |  | Please refer to the same item in Digital Chip.
| 7.06 | ATPG vectors - simulations at full chip level with SDF backannotation |  |  | 2019-04-25 | OPEN
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Power | 3.02 | Review power reduction methodology/techniques (clock gating, oscillator/PLL shutdown, analog shutdown etc) (v3.2/3,02) | 2018-02-01 |  |  | OPEN
DFT | 7.07 | Fault coverage analysis (fault grading) at analog-digital and IP-digital boundary (v3.2/7,05) |  |  | MMDDYY
Note on C4: - Clock and Reset Generation logic should be logically partitioned in a separate block
Note on C5: Should include: - List of all clock, sources, periods and duty cycles - Generated clocks and sources - Inter-clock relationships
Note on C6: - Confirm digital core is reset until oscillator is stable (verify with simulation) - Review oscillator enable start and stop for lockup scenarios - Perform an assessment of all POR signals in the design and their synchronization wrt peripheral clock domains - During Kickoff, evaluate the use cases for POR and brownout scenarios in the context of system traffic on the peripherals - As a good practice, designs may consider by default to add synchronization logic for all clocks and then take out this logic when it is not needed on a clock-by-clock basis - Review GPIO defaults at POR and across all power modes (including supply brownout). Ensure conformity with system across all power conditions
Note on C7: - Powerup, power down and brownout scenarios - Clearly document illegal power sequence combinations
Note on C8: Analog/Digital boundary signals. Review "A-D Contract" worksheet for detailed information - Signal contract for all interface signals, behavior (level, edge, can glitch) and electrical specifications (.lib, source/destination power rails, level shifters, drive strength, loading and timing). - Ensure analog inputs have debounce (glitch prevention) logic inside digital - Outputs going into analog which must NOT glitch should be registered - Ensure all outputs have appropriate drive buffer for given loading - Check voltage/current compatibility of boundary ports - Check POR and powerdown values on level-shifter/isolation cell outputs are valid across all operating modes - All boundary signals between physical partitions should be registered
Note on C9: For example: Data Path BW, memory BW, etc. if applicable
Note on C10: Spare Gates: - explain spare gate methodology. Include appropriate spare types and density - After P&R, review placement of spares and ensure uniform distribution
Note on C11: Chip/System Reviews: - Has digital designer been included in system-level design reviews/meetings - Understand implication of analog behavior and any changes in analog on digital
Note on C12: - Ensure that device ID and I2C revision ID are not hard-coded inside the digital core (recommend using tie-off cells and utilize higher metal layers for ECO's) - Tie these with higher metal layers
Note on C13: - Review choice of IO buffers used in interfaces. Ensure the IO buffers meet system specs eg I2C IOs should incorporate glitch suppression and a Schmitt trigger for SCL/SDA - Review interface timing. Timing will influence IO buffer choice - Check IO pad voltage inside device and bus voltage in system - If voltages are not same, check leakage power in IOs - Is fail-safe operation needed - check if IO pins need pullup/pulldown and the value. Align value with system/application
Note on C15: This should include, but not be limited to, the following: - Block Diagram - Functionality - Dataflow - Clocking - Interfaces - Physical Dimensions
Note on C16: - Outline known implementation specific exposure windows - Key timing diagrams, state machines, interfaces, protocol, deviations from standard specs
Note on C18: Include atleast the following: - Register map - Register descriptions, reset values
Note on C19: - For MDR, ensure register definitions, control bits and register placement is inline with system and FW usage - For FDR, review register map in conjunction with detailed device functionality captured in the datasheet
Note on C21: - Power estimates in all modes of operation - Assumptions made in power estimation - Process corners used for power calculations - Power budgeting for chip - list analog and digital power - Target power budgets for each supply
Note on C22: Examples include: - Bus arbitration - Chip interfaces
Note on C23: Examples: - Underflow/overflow mechanisms - Video/audio datapath - Network datapath
Note on C27: - Ensure the default state of cells crossing power domains (isolation cells, level shifters) is correct across all operating modes the device will see in system
Note on C30: Run power analysis at the following stages: - RTL 90% complete - Gate-level with timing-closed SDFs - Ensure final power numbers are calculated with vcd's from representative simulations
Note on C32: - Ensure that design adheres to RTL coding guidelines - Review coding guidelines with Apple
Note on C35: Deliverable: a representative compile log from a simulation which show warnings, file names, and test logging.
Note on C36: If chip interfaces with another chip on a unique interface (other than I2C or SPI for example), then we need to run a co-simulation in-house to verify compatibility.
Note on C39: After this date, the RTL will not change, ECO's only. All FIXME's resolved
Note on C41: Synthesis constraints - ensure constraints are defined at legal points - ensure all sequential elements and memories are 100% constrained - ensure all i/o and ports are constrained
Note on C42: - Confirm source points of all generated clocks - Confirm edge relationship of generated clocks - Ensure correct clock group attributes being used: asynchronous, logically exclusive and physically exclusive - Check all the defined clocks being propagated to the intended destinations properly - Ensure no clock signals are used in datapath
Note on C43: - Check formal verification of exceptions - mcps and false paths
Note on C44: Ensure netlist from synthesis is compatible with all downstream tools
Note on C47: - Chip Interface Timing Constraints should accurately reflect setup/hold/prop delays/load/slew conditons for the interface pins as per spec and board topology - Take into account device use conditions in the system during creation of chip-level timing constraints for interfaces. Align with Apple system teams over usage of standards for the particular application. This applies even to standard interfaces like SPI and I2C
Note on C48: - Ensure top-level parasitic delays are accounted for during block time budgeting - this applies to block-block timing and top-interface timing constraints - Take into account delays through analog cells in block timing budgets
Note on C49: Formal Verification: - Run FV between RTL and synthesized netlist - Run FV between digital netlist in top-level schematic and RTL
Note on C52: Confirm all analog to digital timing arcs are included in the .lib file. Confirm timing budgets and assumptions are correct
Note on C55: - Schematics for each type of clock domain crossing implementation with timing waveforms. - CDC re-synchronized or considered static. - Asynchronous inputs synced or verified as static. - Clock reset to low state at POR to allow clock gating cells to wake up in a known state - Register all signals crossing clock boundaries at source - Pay attention to signals generated (or ending in) black boxes. Verify these are covered during CDC checking - Ensure that synchronizer logic is well covered in DV by introducing uncertainty in the signal propagation delays through synchronizers. Randomize this delay to be either 2 or 3 cycles and ensure downstream logic works in both scenarios - Perform netlist-level CDC checks in both functional and DFT modes
Note on C56: - Ensure clock directive used in CDC constraints is consistent with synthesis constraints
Note on C57: Ensure signal reconvergence check is enabled in CDC setup. Check level of reconvergence
Note on C59: - Check waivers on false paths - Ensure CDC directives like quasi-static signals, gray coding etc can be validated using DV assertions
Note on C60: Instantiate either synchronizer cell or two-flop cells in RTL - do not use inferred double flop. For two-flop combination, use explicit naming convention to identify these as synchronizers. This will facilitate placement checks
Note on C61: - If there are any CDC waivers captured from previous designs, revisit these in context of clocking scheme in current design
Note on C65: Review and verify all RDC scenarios where reset signal generated in one domain can create a potential metastable condition in another domain. This typically occurs when launch and capture domains have different reset signals
Note on C66: Review and verify all RDC scenarios where reset signal generated in one domain can create a potential metastable condition in another domain
Note on C67: Understand the overall DFT methodology - Muxing scheme for test clocks and preset/clear - block all free running internal clocks - control for asynchronous presets and clears - Check design requirements to run scan at desired frequency - bypass input filters on input pins (I2C) - push-pull driver instead of open-drain on output pins (I2C) - scan data out buffer should be able to support fast speeds during scan (10-20 MHz) - For test time optimization, identify bypass modes to speed up very slow timers - Ensure all on chip oscillators are off during scan mode - Ensure that analog inputs to digital are muxed to 0/1 during scan mode - Ensure that digital outputs to analog are muxed to a safe state during scan mode - For designs that are not fully synchronous, what is plan for testing non-scan logic - For outputs to NVM / EEPROM, gate off the EN, WR, RD signals in scan mode - For IDDQ measurement, ensure that the digital core is isolated so power supply can be supplied by tester directly.
Note on C68: At kick-off and final review: - Include details on trim, analog test and digital tests - Include inputs from validation and test in design and DFT planning - Make sure that test modes and trim functionality is verified in simulations
Note on C69: At Final Design Review: Make sure BIST simulations pass on final design netlist. Use parasitic information via backannotated SDF This check may appear in multiple tabs
Note on C70: Stuck at fault coverage > 98% Transition fault coverage > 85%
Note on C71: At kick-off: - Plan on Analog IP test strategy - The Analog test strategy may also be covered during the Analog review At final review: - Review Analog IP test strategy
Note on C72: - Ensure availibilty of vectors in time for ATE testing - List any exceptions/checks which will not be covered by ATPG vectors
Note on C83: - identify all nodes between IP-digital and analog-digital which are not covered by scan. Check test coverage of critical nodes through functional vectors

## A-D Contract
| < Chip Name > |  | Fill in the following information for all interface signals at the boundary of digital blocks - between analog-digital, digital-IP, digital-IO. Also include information about all signals which cross level-shifter/isolation cell boundaries (including signals which lie entirely within IP/analog modules)
Pin list of digital Part
|  |  | Note: | To be first filled in and reviewed during the Mid-term Design Review
To be reviewed again and signed off during the Final Design Review
tt2_cfg |  | tt2_name | tt2_dir | tt2_width
| Block name | Pin name | Dir | Width | Source Module | Destination Module | Level-Shifter | LS | LS | Default state with | Power-gated blocks | POR State of Signal | Load | Drive Buffer Type | STA Reference Clock | Sync Method | Debouncer / deglitch logic | Comments
[7 empty] | (LS) | Input | Output | with input | ISO / CLAMP cell
[7 empty] | Needed? | Supply | Supply | supply absent | power domain
<Block1> example
|  | sclk | in | 1 | Oscillator | Digital | Yes | VDDOSC | VDDCORE | Low |  |  | N/A | 10x | Signal is Clock | no_sync | N/A
|  | sdi | in | 1 | [11 empty] | sync | 0ms/5ms/10ms/50ms/500ms/750ms/1000ms
|  | sdc | in | 1 | [11 empty] | reset_sync | N/A | Passed through a standard reset synchoniser
|  | reset_n | out | 1 | [11 empty] | no_sync
<Block2> example
|  | otp0_data | in | 8 | [11 empty] | bus_sync | N/A | Data is stable when sampled
|  | otp0_pa | out | 8
|  | otp0_pdin | out | 8 | Digital | OTP | Yes | VDDCORE | VDDOTP | Low |  |  | 100fF | 10x | SCLK
|  | otp0_pwe | out | 1 |  |  | No
|  | otp0_pprog | out | 1
|  | otp0_ptm | out | 2
|  | otp0_prd | out | 1
|  | otp1_data | in | 8 | [12 empty] | N/A | Data is stable when sampled
|  | otp1_pa | out | 8
|  | otp1_pdin | out | 8
|  | otp1_pwe | out | 1
|  | otp1_pprog | out | 1
|  | otp1_ptm | out | 2
|  | otp1_prd | out | 1
Apple Confidential - Do not duplicate
KA
KA
tt2_end
Note on D9: In: Input to core Out: Output from core to Analogue Mux: Output from core to Digital Mux
The A-D inteface list was agreed in June 2018 F2F to be tracked as a separate document.
Document uploaded in Radar 40623962, doc names: interface_template_AD-1.xlsx and Matterhorn_Interfaces_0.2.xlsx

## ESD & LUP
# | Expectation of Methodologies applied to ESD/LUP Design and Review by Chip Vendors | Expected Deliveries at KO |  | Expected Deliveries at MDR |  | Expected Deliveries at FDR |  | Conclusion | Effort | Risk | Readiness | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
0 | ESD spec: HBM/CDM respective passing voltages and IEC-41000-4-2 spec details if applicable | List of ESD requirements for every pin. Translate CDM passing voltage to peak current. | OPEN | Confirmation of no changes/updates. | OPEN | Confirmation of no changes/updates since MDR. | OPEN
1 | Component ESD characteristics (such as TLP I-V curves) should be collected for every type of transistor/diode/devices, used in ESD protection and functional circuit blocks. Vendor should conduct ESD design window (SOA) analysis. | List of components missing ESD characteristics, and plan of test chip to collect missing data. | OPEN | Confirmation of ESD design rules up-to-date with the ESD char data. | OPEN | Confirmation of no changes/updates since MDR. | OPEN
2 | Report characterization of ESD cells and/or padring cells used. New ESD components and cells must be verified. | Report the status of ESD cell qualification: un-validated, test-chip validated, or product validated. Present a development plan if any new ESD cell needs to be created and plan of test chip. ESD/LUP reports of existing, comparable products, or test chip. | OPEN | All ESD cells should be qualified by test chip or prior products. | OPEN | Confirmation of no changes/updates since MDR. | OPEN
3 | Compile the chip level ESD protection diagram, and verify discharge paths exist for all stress combinations. Describe cross-domain situations and solutions. All pad names must be labeled in the top level diagram. | General ESD scheme, or using previous generation product as example. ESD protection plan of current project. | OPEN | Top-level ESD diagram that lists every pin, their voltage ratings and ESD protection cell/type. Projected clamp placement and alignment to leakage/inrush requirements of project. Confirmation of cross-domain protection. | OPEN | Confirmation of no changes/updates since MDR. | OPEN
4 | Place ESD cells to serve each power/ground domain and conduct ESD network analysis to show low resistance ESD discharge paths. | General strategy of ESD cell placement, or using previous generation product as example. | OPEN | Floorplan of chip and locations of key ESD components, with highlights of global ESD buses. | OPEN | Finalized floorplan, ESD locations, and ESD buses. Snapshot of RDL, or connection of pads to ESD. | OPEN
5 | Verification of ESD network with automated checkers. | description of the work flow of ESD/LUP design, verification and sign-off. List the automated checkers. Confirmation of design verification methodology up-to-date with data and lessons-learnt. | OPEN | verification of top-level ESD protection diagram schematic. List the bus resistance design targets. | OPEN | verification of ESD protection scheme with layout extraction. Confirmation of meeting requirement. comparison to verification of prior Si-proven products. | OPEN
6 | In-depth analysis, such as simulation, of all circuits that are not Si proven, especially new parasitic components. | identification of circuit blocks or pin combinations with un-proven ESD/LUP robustness, e.g, new pad cell design, parasitic components. | OPEN | verification of ESD/LUP strategy/methodology to include relevant models for parasitic components. Simulation results that confirm the circuit design, layout floorplan. | OPEN | Confirmation of passing simulation or analysis results on final layout. | OPEN
7 | Detailed layout review of self-protecting circuits/blocks, including both ESD and LUP sensitivity. | identification of self-protecting circuits/blocks | OPEN | Confirmation of layout review of the self-protection blocks, with either comparison to Si-proven designs or simulation results. | OPEN | Re-confirmation with final layout. | OPEN
8 | System level ESD spec (including IEC-61000-4-2 and others applicable) requirement, and corresponding solution at chip level. Verification, simulation and review process needed to expand for these checks. | Alignment of on-chip ESD and system level ESD protection. Translation of system level ESD spec to on-chip ESD requirements. | OPEN | Confirmation on ESD protection scheme, including on-chip and off-chip components; agreement on all details of verification/test setup. Simulation results of schematic with projected layout factors. | OPEN | Verification of ESD event simulation with layout, including designated and parasitic ESD current paths, at preset process corners and chip power states. Verification of test chip results. | OPEN
9 | Design rule ownership and coverage on LUP rules. Cross-section of NBL/PBL and bias scheme. System ESD/EOS events induced LUP. | Description of design rule ownership, list of waived conditions in previous designs. Confirmation of rule coverage for non-standard bias schemes, especially for negative supplies, HV, deep wells, isolated wells, etc. List pins exceeding 0.5X VDD overshoot/undershoot during operation or system-ESD conditions. | OPEN | Description of checking methodology, including voltage tagging, IO pin labels, etc. Description of areas with critical spacing requirements in chip floorplan. Topologies/strategies for the strong overshoot pins. | OPEN | Verification of checking methodology, review of violation/flags and waivers. Layout review of strong (beyond 0.5X VDD) overshoot/undershoot pins (such as system-ESD conditions, power transistors). Foundry approved waivers. | OPEN
10 | ESD/LUP testability (package review) and Si verification plan | Description of ESD and LUP test plan, including equipments and facilities to be used. Package plan and testability. Prepare for pre-qualification/first lot qual stress to failure plan by QA. | OPEN | Update of package profile, NC pins, power states, and updates for ESD/LUP test plans. LUP test plan with power states. Pin categorization in LUP test plan. | OPEN | Final confirmation of ESD/LUP testability and schedule. Prepare for pre-qualification/first lot qual stress to failure plan by QA. | OPEN
Apple Confidential - Do not duplicate

## Analog Layout
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review | Mid-term Review | Final Review | DRI | Comments/Questions | Deliverables |  | Effort | Risk | Readiness
|  |  |  | 2019-01-31 | 2019-03-31
Analog Layout | 1.01 | Part has sufficient spare capacitors and resistors. |  | OPEN | OPEN | Ivaylo
| 1.02 | High voltage lines are not routed over low voltage circuitry. |  | OPEN | OPEN |  | Highest voltage is 3.3V which is only used in SBU, XTAL and TSMC stdIO. Special design rules cover details in TSMC DRC
| 1.03 | Current density and joule heating requirements met for all metals. |  | OPEN | OPEN |  | This is part of EM checks
| 1.04 | No ESD diode clamps are placed on switching pins (with external inductance). Power FETs are self protecting. |  | OPEN | OPEN |  | Device does not require external inductors. There is only cable and PCB connected
| 1.05 | Inspect critical blocks for cross talk |  | OPEN | OPEN |  | Will show up in BA simulations
| 1.06 | Inspect layout matching of differential signal paths |  | OPEN | OPEN |  | Done by design and will also show up in BA
| 1.07 | Inspect critical signal path layouts in the core and I/O ring |  | OPEN | OPEN
| 1.08 | Isolate all sensitive circuitry in their own well and add sufficient guard rings where applicable. Moreover, highlight the changes to guard-ring, isolations and spacing changes made from previous IPs to the present designs |  | OPEN | OPEN |  | Guadrings are required due to design rules. This topic is already part of detail floorplaning.
| 1.09 | Review routing of interface signals (e.g. SPI, I2C SCL/SDA) lines at top-level, ensure minimum skew |  | OPEN | OPEN |  | This is part of digital place and route and should be covered by constrains.
| 1.1 | Power circuit blocks (e.g., LDOs, bucks and power-gating switches) that employ kelvin sensing using metal interconnections shall have the top level metal connections pushed into the sub-block, so that an accurate representation of the layout is extracted and re-simulated for final verification purposes. In addition, force and sense connections should use different pin names to separate these signals in the LVS net list. |  | OPEN | OPEN |  | By default all metal from top-level is copied into a stand-alone cell. For detailed BA simulation this metal cell is added and aligned to the layout before extraction.
| 1.11 | Verify use of dummies for matched devices including resistors. Also, make sure that the matched devices/resistors are placed in wells connected to same potentials |  | OPEN | OPEN |  | Will be done and is also visible for most devices in BA data.
Apple Confidential - Do not duplicate
Note on C10: * Make sure critical top level signals are handled properly in layout. Eg. Clock nets, interface nets, timing critical nets

## Physical Design
[11 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions | Comments Nov 6-8 2018 | Deliverables | Effort | Risk | Readiness
PnR DFT checks | 1.01 | Scan insertion / reorder / repartition PnR report review. Review integrity with ATPG tool |  | 2019-01-26 | 2019-04-09 | OPEN | Karsten
| 1.02 | Confirm BIST integrity is checked ( usually via DV simulations.) |  |  | 2019-01-26 | OPEN
| 1.03 | DFT coverage review |  |  | 2019-01-26 | OPEN
STA & Noise | 2.01 | STA methodology - timing closure/ margins / tools - setup & versions review | 09/28/18 |  | 2019-01-26 | OPEN |  | Details will be avaialble not before at beginning of trial runs | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 2.02 | STA Sign-off Corners & modes | 09/28/18 |  | 2019-01-26 | OPEN
| 2.03 | Extraction corners | 09/28/18 |  | 2019-01-26 | OPEN
| 2.04 | SDC constraints review | 09/28/18 | 2019-01-26 | 2019-04-09 | OPEN
| 2.05 | SDC exceptions review |  | 2019-01-26 | 2019-04-09 | OPEN
| 2.06 | Analog <-> digital timing budget review. Check of timing models of the analog IP |  | 2019-01-26 | 2019-04-09 | OPEN
| 2.07 | IO pin constraints review | 09/28/18 | 2019-01-26 | 2019-04-09 | OPEN |  | Details will be avaialble not before at beginning of trial runs | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 2.08 | Validation of unconstrained pins |  | 2019-01-26 | 2019-04-09 | OPEN
| 2.09 | Sign-off STA report (all corners & modes) |  |  | 2019-04-09 | OPEN
| 2.1 | Sign-off Noise reports |  |  | 2019-04-09 | OPEN
| 2.11 | Clock double switching nets (negative pulse) |  |  | 2019-04-09 | OPEN
| 2.12 | Duty cycle report on clocks |  |  | 2019-04-09 | OPEN
| 2.13 | Xtalk report |  |  | 2019-04-09 | OPEN
| 2.14 | Max CAP report |  |  | 2019-04-09 | OPEN
| 2.15 | transition time - data - report |  |  | 2019-04-09 | OPEN
| 2.16 | transition time - clock -report |  |  | 2019-04-09 | OPEN
| 2.17 | minimum pulse width checks |  |  | 2019-04-09 | OPEN
| 2.18 | floating gate check (digital logic only) |  |  | 2019-04-09 | OPEN
| 2.19 | Documented waivers for STA / Noise / Xtalk / Max CAP with justification and simulation results |  |  | 2019-04-09 | OPEN
| 2.2 | Timing closure methodology for metal ECOs | n/a |  | n/a | NA |  | Due to block size full layer ECO is expected. | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
Place & Route | 3.01 | PD methodology review - detailed methodology for the project - for either a flat or an hierarchical approach | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
General setup | 3.02 | Metal stack usage methodology review | 12/15/17 |  | 2019-01-26 | OPEN |  | Selection was driven by analog design group |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.03 | Spare gate methodology - types, percentage, | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.04 | Spare gate check - adherence to decided methodology |  |  | 2019-01-26 | OPEN |  |  | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 3.05 | Filler cell methodology - CAP fillers vs. non-CAP fillers | 09/28/18 |  |  | OPEN |  | Need some trials/experience with technology first
| 3.06 | Filler cell report check review |  |  | 2019-04-09 | OPEN
| 3.07 | Don't use cell list review to match synthesis | 09/28/18 |  | 2019-01-26 | OPEN |  |  | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 3.08 | Floorplan review, macro placement, target utilization | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.09 | Floorplan review - metal heavy hard IP placement near die edges | 12/15/17 |  | 2019-01-26 | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.1 | PnR reports with utilization |  | 2019-01-26 | 2019-04-09 | OPEN
IO | 3.11 | IO ring review - SSO, ESD, PG requirements | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.12 | IO ring - final ESD, SSO, PG compliance review |  |  | 2019-01-26 | OPEN
Placement and Power planning | 3.13 | PG structure methodology review | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.14 | RAMs and macros power connectivity review |  | 2019-01-26 |  | OPEN
| 3.15 | Redundant memories placement |  | n/a | n/a | OPEN |  | No RAMs in design
| 3.16 | If OTP is present, does it haveUV protection layer |  | n/a | n/a | OPEN |  | Not planned for this device
| 3.17 | Unplaced cells check |  |  | 2019-01-26 | OPEN
| 3.18 | scan chain reordering methodology | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.19 | Synchronizer pair flops review |  | 2019-01-26 | 2019-04-09 | OPEN
MultiVDD / power-gated designs | 3.2 | Level shifter validation report (multi VDD designs) |  |  | n/a | OPEN |  | not applicable for chip integration level
| 3.21 | Always ON cells validation report (power gated designs) |  |  | n/a | OPEN
| 3.22 | Clamp cell validation report (power gated designs) |  |  | n/a | OPEN
| 3.23 | Power switch connectivity validation report (power gated designs) |  |  | n/a | OPEN
| 3.24 | Power switch ramp-up time report (power gated designs) |  |  | n/a | OPEN
CTS / HFN | 3.25 | CTS methodology - skew, insertion delay, transition time, max CAP targets | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.26 | CTS skew, insertion delay, transition time and max CAP reports |  |  | 2019-04-09 | OPEN
| 3.27 | CTS methodology - CLK cell usage, Vt usage | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.28 | CTS CLK cell usage, Vt usage reports |  |  | 2019-04-09 | OPEN
| 3.29 | CTS methodology - routing topology layers, NDR, shielding | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.3 | CTS routing, NDR, shielding % reports |  |  | 2019-04-09 | OPEN
| 3.31 | Signal EM reports |  |  | 2019-04-09 | OPEN
Hierarchical designs | 3.32 | Pin size / off-grid check (hierarchical design - block level check only) |  |  | n/a | OPEN |  | No hierachical design
| 3.33 | Antenna diodes on all inputs (hierarchical design - block level check only) |  |  | n/a | OPEN
| 3.34 | Primary output contention checks (hierarchical design - block level check only) |  |  | n/a | OPEN
Special nets handling | 3.35 | Tie hi / lo methodology & review | 09/28/18 |  | 2019-01-26 | OPEN |  | Need some trials/experience with technology first | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 3.36 | Don't touch / Don't route / Hand route / special nets review |  |  | 2019-01-26 | OPEN
| 3.37 | Fuse / OTP connections Resistance requirement & compliance review | n/a |  | n/a | NA |  | Will not be used!
| 3.38 | Review of special cells - temperature / process monitors etc. |  |  | 2019-01-26 | OPEN
ECO | 3.39 | Functional ECO methodology review | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 3.4 | Functional ECO implementation ECO review |  |  | 2019-04-09 | OPEN |  | Subject to become N/A
other routes | 3.41 | RDL review |  |  | 2019-01-26 | OPEN
| 3.42 | Make sure that certain sensitive circuitry is not placed under the bumps | n/a |  | n/a | NA |  | Decidated analog macro cells will be instantiated, verified by analog design (timing)
| 3.43 | Routes requiring special considerations |  |  | n/a | NA
| 3.44 | Physical Feedthrough review | n/a |  | n/a | NA |  | no hierachical design
| 3.45 | Logical Feedthrough review | n/a |  | n/a | NA
power analysis | 4.01 | IR drop methodology - static and dynamic (vector or vectorless) | 09/28/18 |  |  | OPEN |  | Need some trials/experience with technology first
| 4.02 | IR drop budget calculations | 09/28/18 |  |  | OPEN |  |  | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 4.03 | Preliminary static IR drop reports |  | 2019-01-26 |  | OPEN
| 4.04 | Final static IR drop reports |  |  | 2019-04-09 | OPEN
| 4.05 | Final dynamic IR drop reports |  |  | 2019-04-09 | OPEN
| 4.06 | Power EM reports |  |  | 2019-04-09 | OPEN
| 4.07 | MVRC report review (power gated designs only) |  |  | 2019-04-09 | OPEN |  | Subject to become N/A
Physical verif, DFM, electrical & other analysis | 5.01 | DFM requirements methodology - wire spreading, redundant via insertion | 12/15/17 |  |  | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 5.02 | DFM requirements - wire spreading, redundant via insertion reports |  |  | 2019-04-09 | OPEN
| 5.03 | Base layer DRC review with macros included |  | 2019-01-26 |  | OPEN
| 5.04 | DRC reports review |  |  | 2019-04-09 | OPEN
| 5.05 | DRC metal density reports review |  |  | 2019-04-09 | OPEN
| 5.06 | DRC latch up report review |  |  | 2019-04-09 | OPEN
| 5.07 | DRC waivers documented with explanation |  |  | 2019-04-09 | OPEN
| 5.08 | LVS reports review |  |  | 2019-04-09 | OPEN
| 5.09 | LVS virtual interconnects report review |  |  | 2019-04-09 | OPEN
| 5.1 | LVS redundant / duplicate cells report review |  |  | 2019-04-09 | OPEN
| 5.11 | ERC report review |  |  | 2019-04-09 | OPEN
| 5.12 | ERC report floating inputs, unconnected pins, undriven nets check |  |  | 2019-04-09 | OPEN
| 5.13 | ERC waivers documentation with explanation |  |  | 2019-04-09 | OPEN
| 5.14 | ANTENNA report review |  |  | 2019-04-09 | OPEN
| 5.15 | PDK, PV rule-deck versions |  |  | 2019-04-09 | OPEN
| 5.16 | Sign-off signal EM report |  |  | 2019-04-09 | OPEN
Package Assembly Checks | 6.01 | RDL review | 09/28/18 | 2019-01-26 | 2019-04-09 | OPEN |  | For Kickoff: What is expected? | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 6.02 | Bump review | 12/15/17 |  | 2019-04-09 | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 6.03 | Bump placement review | 12/15/17 | 2019-01-26 | 2019-04-09 | OPEN |  |  |  | Supporting material for 12/15/17: F2F-Seeb - Review of Design Methodology .pptx, uploaded in Radar AI 35931905.
| 6.04 | Seal Ring Review / Passivation termination review | 09/28/18 |  | 2019-04-09 | OPEN |  | For KickOff: Is sealring available? | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
| 6.05 | DRC reports review |  |  | 2019-04-09 | OPEN
| 6.07 | DRC waivers documented with explanation |  |  | 2019-04-09 | OPEN
| 6.08 | Assembly DRC checks rule-deck versions | 09/28/18 |  | 2019-04-09 | OPEN |  | The item will be communicated when vendor is contracted. | Details available in MH16_PD_XDR-180917-181107.pdf uploaded in Radar AI 45987965.
Netlist / LEC / GDS special PAD checks | 7.01 | LEC report review (RTL <-> synthesis netlist <-> LVS netlist) |  | 2019-01-26 | 2019-04-09 | OPEN
| 7.02 | Make sure that the versions of the physical and logical views of all libraries match. |  |  | 2019-04-09 | OPEN
| 7.03 | Share the logs and error reports from db. transfer from the mock tapeout |  |  | 2019-04-09 | OPEN
| 7.04 | If design has probe pads - make sure that they conform to foundry specs |  | n/a | n/a | NA |  | No probe pads planned, FC design
Special checks for multi-DNW designs | 8.01 | Does the die have multiple Deep N-wells? |  | 2019-01-26 | 2019-04-09 | OPEN
|  | If Yes, Answer 7.02 and 7.03 below. |  |  |  | NA
| 8.02 | Does the ERC deck have a check for DNW charge sharing? |  | 2019-01-26 | 2019-04-09 | OPEN
| 8.03 | If no check exists in the ERC deck, read and follow comments. |  | 2019-01-26 | 2019-04-09 | OPEN
Apple Confidential - Do not duplicate
Note on C3: At mid-term review and final review: * If scan chains were reordered or repartitioned - make sure that PnR tool did not break the integrity of the scan chains. Verify reports from the PnR tool as well as from Tetramax (or other ATPG tool) that scan is still intact behaviorally. * Need to catch any tool misbehavior in the Mid-term Review. * Final Review will be late to fix issues. At Mid-term review: * PnR tools are notorious for breaking the sanity of scan chains. So an mid-term review showing that reordering is not breaking it. - reports / dumps from PnR tool - checks by some ATPG tool like Tetramax on the interim netlist At Final review: * checks from ATPG tool to make sure DFT is not broken after scan reordering.
Note on C4: At Final Design Review: To ensure that PnR tool did not break the BIST connectivity. This is not checked by PD. DV needs to make sure that BIST is not broken. This check may appear in multiple tabs
Note on C5: Stuck at fault coverage > 98% Transition fault coverage > 85% This check may appear in multiple tabs.
Note on C6: Finalize at kick-off and review at final review: * Review the strategy for the full chip timing closure including analog and digital. - CLEARLY identify if any timing modes / paths which will NOT be checked in STA but will rely on other mechanisms for the checks. e.g. Gate level simulations. * Review the setup of the tools used for any STA, Noise and glitch (Star RCXT, PT, PTSI, CeltIC/ETS etc.) * Review any additional margins and how they are derived. - e.g.. Extra hold margin to compensate for extraction inaccuracy. Additional OCV margins suggested by foundry. * Review and agree at kick-off * Ensure that the agreement held good during final review.
Note on C7: Finalize at kick-off and review at final review: * Table showing the corners, modes and conditions which the timing will be closed to. - Along with supporting documents showing it meets the product specs and fab specs. * Review and agree to conditions in the table at the kick-off review. * List corners, modes and conditions used in the PnR tool, if different from those used in the sign-off tool. At Final Review: * Make sure that timing was closed to the agreed conditions during final review.
Note on C8: Finalize at kick-off and review at final review: * Table showing the LPE / RC extraction corners. * Review and agree to the corners at the kick-off * Ensure corners were adhered to during the final sign-off review.
Note on C9: Present at kick-off and review at mid-term & final review: * Check clock definitions - make sure frequencies are correct - clocks are defined at the correct sources i.e.. on the physical output pins of an element which will not be optimized out e.g.. Mux, FF. - no clocks are defined on a logical pin of an internal module * Review exceptions (false / multicycle paths). - no constraints are defined on a logical pin of an internal module - no constraints are defined at the correct sources i.e.. on the physical output pins of an element which will not be optimized out e.g.. Mux, FF. - Justify the exceptions and add comments. - If legacy, revisit to make sure that they are still needed. * Constraints need to be: - reviewed and agreed to by mid-term review - reviewed at final review - reviewed at any mid-term milestones whenever they are modified Enough changes may warrant for more interim reviews.
Note on C10: Finalize at mid-term review and review at final review: *Subset of overall constraint reviews. Separate entry because there could be multiple independent exception files. To make sure that nothing is missed.* * Review exceptions (false / multicycle paths). - no constraints are defined on a logical pin of an internal module - constraints are defined at the correct sources i.e.. on the physical output pins of an element which will not be optimized out e.g.. Mux, FF. - Justify the exceptions and add comments. - If legacy, revisit to make sure that they are still needed. * Constraints need to be: - reviewed and agreed to at mid-term - reviewed at final review - reviewed at any mid-term milestones whenever they are modified Enough changes may warrant for more interim reviews.
Note on C11: Finalize by mid-term and review at final review: * Ensure the clock period is fairly shared between Analog and digital sections. * Ensure that the .lib (or any other timing model) for the analog, reflects correct conditions for synthesis tools e.g.. - correct extracted pin cap on input pins. - accurate Max delay on output pins of the analog IP. - correct duty cycle if the clock is an output from analog macro. Enough budget changes may warrant for more interim reviews.
Note on C12: Present at kick-off and review at mid-term & final review: * All primary IO should be constrained for STA. - all outputs should have loads - all inputs should have drive cell defined. Enough constraint changes may warrant for more interim reviews.
Note on C13: At Final Review (and mid-term reviews as needed) * Any primary IO / block IO which is unconstrained should have a reason and should be reviewed and agreed upon. * Should be reviewed and validated: - the first time such a condition occurs - at the final review
Note on C14: At Final review: *Sign-off STA reports for the following: - SETUP timing - reg to reg - IO - HOLD timing - reg to reg - IO showing that timing is closed to the - corners, - conditions, - modes, - margins and - constraints as agreed to (in sections 2.01 to 2.08) * Due at final review. - Intermediate reports are expected to show progress
Note on C15: At Final review: Sign-off tool report showing that the design is noise and glitch free at the agreed corners (usually fast corners)
Note on C16: At Final review: Sign-off tool report showing that there is no double switching of clocks.
Note on C17: At final review: * Duty cycle report for major clocks. (e.g.. Output of report_clock command PT / ETS) * Make sure duty cycle is met on clocks going to mixedIP blocks.
Note on C18: At Final review: Sign-off tool report showing that the design is free of cross talk violations
Note on C19: At Final review: Sign-off tool report showing that the max CAP conditions for all cells as included in the .lib have been met.
Note on C20: At Final review: Sign-off tool report showing that the transition times for data nets are met at all corners.
Note on C21: At Final review: Sign-off tool report showing that the clock slew times are met at all corners.
Note on C22: At Final review: Sign-off tool report showing that min pulse width requirements to input pins of hard macros are met
Note on C23: At FDR: - Run a check to report any floating inputs (non-primary) in the digital logic. Equivalent to check_design command in dc. LINT-0 (unconnected input pin) and LINT-3 (Undriven nets) messages. Example of a PT script: set all_drivers {} append_to_collection all_drivers \ [get_pins -hier * -filter {pin_direction =~ *out && is_hierarchical == false}] append_to_collection all_drivers \ [all_inputs] set all_loads {} append_to_collection all_loads \ [get_pins -hier * -filter {pin_direction =~ *in && is_hierarchical == false}] append_to_collection all_loads [all_outputs] set unloaded_nets [ \ remove_from_collection \ [get_nets -top -seg -of $all_drivers] \ [get_nets -top -seg -of $all_loads]] set undriven_nets [ \ remove_from_collection \ [get_nets -top -seg -of $all_loads] \ [get_nets -top -seg -of $all_drivers]] filter_collection $unloaded_nets {base_name !~ "?Logic??"}
Note on C24: At Final review: A document listing - all the failures in reports above (items 2.08 - 2.18) for which waivers are requested. - a reason why the violation can't be fixed and the reason for requesting the waivers - a scientific justification how the waiver will not affect the normal functioning of the chip. - any supporting reports (e.g.. Spice analysis etc.) in support of the waiver - if any of these waivers are a legacy.
Note on C25: Not generally applicable to all projects. To be discussed only for special cases.
Note on C26: Review of the PD methodology in detail - from netlist In to GDS Out
Note on C27: At kick-off: * Description of the metal stack used for the design: - layers for PG - layers for clock routing - layers for signal routing - Redistribution Layer - estimated percentage utilization for each. * How was the metal stack definition derived at. - studies showing if other metal stacks were considered - the die size / cost / utilization analysis with other metal stacks At final review: * % routing in each metal layer * % adherence to original estimates
Note on C28: At kick-off: *Discuss and agree to: - Types of spares to be used - % as of total instances (requirement min 2% of total std cells. Ideally 4% of total std cell count. - How will they be distributed - clocks for spare Flops? Tied off? Part of CTS? - scan pins of spare Flops? Tied off? Part of scan chain?
Note on C29: At final review: * Report showing the actual percentage and distribution of the spare cells * Visual inspection
Note on C30: At kick-off: * Types of fillers to be used- types and sizes of filler cells. * expected % of CAP fillers based on previous designs - the resultant decoupling CAP value expected - if available * methodology for filler insertions
Note on C31: At Final sign-off: * Report Final # / % of filler cells * Report Final % of CAP filler cells * Total DeCAP value as a result of CAP filler cells
Note on C32: At kick-off: *Don't use list in PD should match that used for synthesis with the exception of the CKINV / CKBUFs used for CTS. *Make sure that any cells that require special routing for EM reasons are part of the don't use list. E.g.. High drive (X16, X36 etc.) as defined in the design rules for the particular technology by the foundry * Make sure very low drive cells (X0) are included in the don't use list. At final review: * Make sure that the list was adhered to.
Note on C33: At kick-off: * Proposed floorplan review: -analog macro placement - data flow - digital blocks' utilization - power delivery - power IO, - multiVDD islands - if applicable - special IO / bump requests
Note on C34: At kick-off: * Review the metal heavy hard IP macros placement. - macro edges which contain IO pads are Ok to be flush with the die edge - macro edges without pads need to have a certain clearance from the die edge as defined by the foundry to reduce possibility of warping. - This clearance could be anywhere from the height of one pad to 3-5% of the dimension of the edge. - Please provide the relevant documentation from the foundry showing the clearance is equal or more than required. At final review: * Verify that the clearance rule was followed as per the foundry guidelines.
Note on C35: At MDR: Report from the PNR tools showing: - area of design (area of top and each block if hierarchical design) - utilization - number of placeable instances - number of FFs - number of FILLER cells - wire length - wire utilization per layer - out put of check_design (or equivalent command in PnR tool to check for floating inputs) At Final Review: * Report from the PNR tools showing: - area of design (area of top and each block if hierarchical design) - utilization - number of placeable instances - number of FFs - number of FILLER cells - wire length - wire utilization per layer - out put of check_design (or equivalent command in PnR tool to check for floating inputs)
Note on C36: At kick-off: * The ESD requirements from the foundry * The SSO requirements from the foundry * Proposed IO ring topology to meet the above * resistance requirement between Power bump and Power Pad (containing ESD clamp) for flip chip designs *
Note on C37: At Final Review: * Layout, IO ring document showing that the ESD requirements are satisfied. * SSO calculations showing it is within compliance limits. * Report of the path resistance between Power bump and Power Pad (containing ESD clamp) for either manually or from a commercial tool like Apache pathfinder - for flip chip designs *
Note on C38: At kick-off: * The proposed PG structure for the device: - PG mesh for preliminary PG - Plan for delivering PG to macros & RAMs. - Plan for multiVDD PD distribution - if applicable - Plan for level shifters - placement and hook up - applicable in multi VDD designs only - Plan for delivering PG to Always ON cells, clamp cells and switches - applicable only in power gated designs
Note on C39: At Mid-term Review: * A visual review of the actual PG connectivity to the RAMs and macros to make sure that the connections are robust and will satisfy the IR and EM rules. * This should be performed as soon as the placement of the RAMs and macros is locked down to avoid any disturbance to the design down the road.
Note on C40: At mid-term review : * If the memories have redundancy and the controller if shared - are they placed close together to reduce routing congestion and wire length. At Final review: * Check that the grouping is still intact.
Note on C41: If the OTP spec calls for UV shield, how has that been implemented?
Note on C42: At final review: * Make sure that there are no unplaced cells. A PnR tool will give this report. * Should be run before going into Calibre / Hercules LVS.
Note on C43: At kick-off: * Description of how the scan chain will be re-ordered in the PnR tool - if applicable * Description of when and how the re-ordering will be validated.
Note on C44: At Mid-term review: * To be performed after the first round of Placement. Check that: - all synchronizer pairs are covered - Flops from each synchronizers pair are placed within a pre-determined distance wrt to each other (10u - 20u) - there is no logic between the Q (1st FF) and D (2nd FF) of the pair. - Both the flops are on same clock tree buffer. (zero skew between the two flops) - The first flop of the two is faster (if both are same Vt type but different drive strengths) - The first flop is faster ( if both are different Vt types ) * If a custom integrated synchronizer cell is used, make sure that both are of same Vt type. At final review: * Repeat the checks.
Note on C45: For multi-VDD designs only: At final review: * Reports showing that the level-shifters are placed correctly: - location - power hook-up - all signals crossing voltage domains covered.
Note on C46: For Power Gated designs only: At final review: * Report showing that Always ON cells are indeed in the AON voltage domain (as decided in 3.13)
Note on C47: For Power Gated designs only: At final review: * Report showing that Clamp cells: - are in the correct locations - have correct voltage hook ups - all required nets are covered.
Note on C48: Power gated designs only: At final review: * Power switch placement and connectivity. * visual inspection of the PG supply to the power switches * size of switch to supply required current
Note on C49: Power gated design only: At final review: * Sign-off report showing that the ramp-up times for the switches are within spec.
Note on C50: At kick-off: * The timing constraints provided to CTS tool - expected skew - expected transition times - expected max CAP target - expected insertion delays for the clock tree
Note on C51: At final review: * Review reports / logs to make sure that all the CTS timing targets (from 3.27) have been met.
Note on C52: At kick-off: * The topology constraints to be provided to CTS tool: - type of tree: buffer only, invertor only, mixed - types and drive strengths of the cells to be used - the Vt of the cells to be used.
Note on C53: At final review: * Report / logs showing that the topology constraints (from 3.29) are met.
Note on C54: At kick-off: * Routing constraints for CTS tools: - layers to be used - routing topology and Non Default Routing rules - shielding topology - if applicable
Note on C55: At final review: * Confirm that all NDRs were applied correctly * check clock shielding reports * visually spot check shields for coverage and adequate taps to ground.
Note on C56: At final review: * Reports showing that the design is free of any violations on the signal nets which could cause any potential EM problems. (Most PnR tools will calculate EM limits and provide a report)
Note on C57: At final review - for Hierarchical Designs only - * This is a block level check - check that the blocks are placed on-grid in the top level - check that the pins on the block are on-grid so that the top-level routing is optimal
Note on C58: At final review - for Hierarchical Designs only - * This is a block level check - check that all the input pins on the block have an antenna protection diode. This is especially important if the physical verification checks are done hierarchically.
Note on C59: At final review - for Hierarchical Designs only - * This is a block level check - check that the block level output pins do not have contention issues when connecting to top level nets.
Note on C60: At kick off: * What is the methodology to tie off pins? - direct connection to rails OK? (Need document from the foundry) - tie cells to be used? * For tie cells: - what is the strength? - what is the fanout limit? - what is the physical placement limit? (distance from tie pins) At final review: * Logs / reports / post PnR netlist showing that the tie cells were used. * logs/ reports showing that fanout, placement conditions were met * visual spot checks at random showing the above.
Note on C61: At final review: (would be good to have at an interim point as soon as the routes are ready for review): * Usually "don't route" nets are nets which are hand routed or pre-routed for specific reasons. E.g.. Analog nets, top level clock nets, nets requiring special RC considerations. * This review will mostly be a visual check to go over these nets to make sure that they are OK in terms of: - routing layers - the path taken by the manual route - proper shielding - adequate vias - robust connections - no double routing (loop routing) introduced by the automatic router - unbuffered
Note on C62: At kick-off: * Any special requirements for fuse or OTP ROM from foundry regarding: - placement (near the chip edge / away from chip edge) - routing to the pad (resistance / current) At final review: * Calculations, visuals showing that the placement / routing / electrical requirement for fuses or OTP were met.
Note on C63: At final review: * Review of any special cells like temperature / process monitors were placed as per the foundry / IP provider guidelines.
Note on C64: At kick-off: * Contingency plans for any late functional ECOs arising out of: - late DV bugs - late IP provider bugs - late spec changes - issues caught in interim or final review * Plan to implement the ECO: - when will be a base ECO. - when will it be a metal ECO. * Approximate Turn Around Time in each case to implement ECO, fix timing, clean up DRCs and re-verify.
Note on C65: At final review (or Out of Bound review): * Applicable ONLY if functional ECOs were performed: - Review the implementation of the ECO and the timing and physical verification reports.
Note on C66: At final review: * Visual check of the RDL layer with the routing to the bump cells * 45 degrees / angle routing checks - in compliance with fab DRCs * check that voltage dependent RDL rules are complied
Note on C67: Issue: * Certain sensitive circuitry like band-gap voltage dividers, resistors and sensitive caps need to be kept away from directly under the bumps. They may react to pressures on the bumps due to various reason from the planarity of the PCB to solder flow under bumps. Issue seen mainly on WCSP. At kick-off: * Please make sure that during floorplanning, extra measures are taken to keep the sensitive circuitry away from under the bumps. At final review: * Visually review that the sensitive circuitry is not directly under bumps.
Note on C68: At Final Review: * Review any special routes, e.g. differential signals that require trace length matching, DDR channel length matching etc.
Note on C69: Not common. Design specific. At kick off : * Plan for feedthroughs, if required. - For digital Feedthrough in an analog hardIPs, the names, the buffering and implementation, including isolation of digital signals should be calculated. - For feedthroughs in the digital section, they should be calculated and the implementation worked out so that they are part of the RTL for the module. (For LVS, LEC issues) At final review: *Check that the implementation is as per the plans. * Visual checks may be required in addition to checking the netlist, LVS and LEC reports.
Note on C70: Not common. Design specific. At Final Review : * Verify all feedthrough logic inside the digital. * Understand that feedthrough logic can have glitches which can propagate into analog circuits. * If feedthrough logic is required, ensure analog circuits functionality does not break with these glitches.
Note on C71: At kick-off: * Description of IR drop analysis methodology: - static IR drop methodology, limits and conditions - dynamic IR drop - with vectors? - vectorless? - toggle / activity factor for clocks * Modes for both - functional modes - scan modes * Plans to include package model * Plans to fix IR issues
Note on C72: At kick-off: * Calculations - either hand calculated or any internal / commercial tool showing that the proposed PG structure (in 3.13) will meet the IR drop requirements.
Note on C73: * A mid-term check using the IR drop tool showing that the static IR drop is within control. * Expected to be run as soon as the macro / RAM placement is locked down.
Note on C74: At final review: * Reports from IR analysis tool showing IR drop requirements are met across the die
Note on C75: At final review: * Reports from IR analysis tools showing: - dynamic IR drop map - worst case dynamic IR drop instances - both above depicting that the IR drop is well within limits of the STA Worst case conditions
Note on C76: At final review: * Report showing that the vias on PG structures are large enough to carry the required currents and won't lead to EM issues.
Note on C77: At final review: * A report from either a commercial tool or home tool showing the Multi Voltage Rule Check results: - show that all required nets have level shifters - the polarity of level shifters is correct - they are hooked to the proper voltage domains - the placement is correct.
Note on C78: At kick-off: * Design for Manufacturability / Yield requirements by the fab for the technology used - wire spreading - redundant via - any other * Plan and methodology to be used to implement them.
Note on C79: At final review: * Logs / reports showing DFM rules were implemented: - wire spreading - % of redundant vias introduced - per layer
Note on C80: At Mid-term review: * The PnR tools check only for metal DRCs. Many times the Calibre / Hercules DRC is run very late and base layer DRCs - especially those related to macros, RAMs are discovered very late - leading to extra work and time. * This is a check to make sure that a base layer DRC is run as soon as the macro, RAM location is finalized and is clean.
Note on C81: At final review: * Reports from a commercial DRC tool showing: - all Design Rules Checked and passed for the design - for base layers as well as metal - RDL and bump included.
Note on C82: At final review: * Reports from a commercial DRC tool showing: - all metal densities are met as per foundry requirement. - if metal fill is done by foundry, then a report showing the differences in dummy metal fill done by vendor and that done by the foundry. (The metal fill affects timing - so both should be close)
Note on C83: At final review: * Reports from a commercial DRC tool showing: - the design is free of any scenarios which could cause possible latch-up issues.
Note on C84: At final review: * A summary of all the DRC rules which did not pass * The reason why the DRC could not be cleaned up * Reason why the requested waiver will not affect device functionality, performance and reliability
Note on C85: At final review: * LVS report showing that the design is LVS clean, including RDL and bumps * LVS rule deck * EDTEXT file, if used
Note on C86: At Final review: * Any supplemental LVS files in addition to the final report which provide additional information. E.g.. Lvs.rep.ext file in case Calibre is the tool used.
Note on C87: At final review: * The lvs log file which shows and resolves conflicts with cells of same name.
Note on C88: At final review: - ERC report for the design from a commercial tool.
Note on C89: At final review: * ERC report showing: - no floating inputs - no undriven nets - no unconnected input pins
Note on C90: At final review: * A summary of any ERC which could not be met. * Reason why they could not be met. * Reason why it is OK to waive.
Note on C91: At final review: * Report from a commercial tool showing that design has no antenna violations.
Note on C92: * List the PDK used for the project ( std-cell, Ios, memories) * List PV rulesets used for the project * verify that they are the latest from the foundry.
Note on C93: * Report from the sign-off tool for the worst case signal EM corner. (Usually FF cold corner)
Note on C94: At final review: * Specify the default spacing/min-width rules * Specify voltage dependent spacing rules, include the voltage dependent spacing table
Note on C95: At final review: * Provide details on folloing * UBM pitch, spacing * UBM enclosure by chip-edge & AP * UBM density * UBM pitch, spacing * Provide Bump pad structure details
Note on C96: At Mid-term review: * Dummy bumps requirement * Sensitive circuit placement under bumps, including power devices with min Rds on requirements * Checks for VIA/RV overlap with UBM, min spacing checks
Note on C97: * Specify SL structures used, Double or single SL * Details on CAS structures * Min spacing of TEG structures from SL
Note on C98: At final review: * Reports from a commercial DRC tool showing: - all Design Rules Checked for RDL/bumps and passed for the design
Note on C99: At final review: * A summary of all the Package DRC rules which did not pass * The reason why the DRC could not be cleaned up * Reason why the requested waiver will not affect device functionality, performance and reliability
Note on C100: * List PV rulesets used for the package aseembly checks * List rules checked manually, if any * verify that they are the latest from the assembly house and approved by package DRI
Note on C101: At final review: * LEC reports showing: - RTL to synthesis netlist logic equivalence - Synthesis to post PnR netlist logic equivalence * If ECOs were done, then LEC showing: - PnR post ECO netlist to hand-edited synthesis ECO netlist equivalence - ECO netlist vs. modified RTL equivalence A mid-term review may be required if there are enough changes that warrant it.
Note on C102: At Final Review: - Make sure that the latest version of IP models are being picked up for all analysis and gds merge. - Vendor to provide a list of IP versions (stdcell, IOs, memories and hard macros) used for gds merge and all final verification. Make sure that physical and logical versions match.
Note on C103: At Final review: - Vendor is expected to have done a mock Tapeout to the fab before the final design review. - The logs and error reports from the db. transfer should be shared. - The solutions for the errors identified and put in place - Feedback from the foundry about the QoR of mock TO db. to be shared.
Note on C104: At MDR & FDR: If probe pads are present, - make sure that they are labelled correctly and pass all DRC checks specified by the foundry. - make sure they have adequate clearance from any adjacent routing tracks for easy accessibility for probing.
Note on C106: Issue with multiple DNWs. - Yield loss due to gate-ox rupture in chips with multiple DNWs - Failure happens when a driver with a DNW (say DNW1) drove a Gate inside a different DNW (say DNW2) && The Driver to Gate connection is done at lower metal layers than those used to connect DNW1 and DNW2. i.e. the DNWs were electrically floating when the connection from Driver to Gate was made.
Note on C108: If no checks for DNW sharing exist in the ERC deck, then - Make sure that the DNWs are connected to each other in the lowest possible metal layer - The connection from the Driver in DNW1 to the Gates in DNW2 are in the highest possible metal layers. This will equalize the charges in the DNWs and reduce the exposure of the Gates to high voltage. - Gates in DNW should not be of minimum size. Should be as large as permissible.

## PnR visual review
PnR visual review checklist
Note: | Some of the checks in the Master Physical Design checklist need visual inspection to effectively sign them off. This checklist is used for these visual inspection checks.
Completing this checklist during the visual PnR review will automatically help in completing some of the checks in the Master Physical Design checklist.
This review will usually be done during the FDR by walking through the layout with the PnR lead.
Project name: |  | Attendees :
Review date: |  | Venue of review:
[5 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Check | Status | DRI | Comments | Effort | Risk | Readiness
General PnR
Top level | chip statistics: die size, # of IOs, # of hard macros, # of digital PnR blocks, utilization (aka die fact sheet) | OPEN |  | Please fill in the die fact sheet tab
| understand the floorplan, partitioning, placement, and the data flow through it | OPEN
| # of digital PnR blocks, std cell and PnR utilization for each | OPEN
| clearance between hard macros / analog and digital PnR blocks for coupling avoidance | OPEN
| guard-rings with substrate contacts around analog IP | OPEN
| fuses, special IP like temp or process monitors - review placement and hook ups | OPEN
| hard macros at top level - clearance from edges and corners | OPEN
| any non-default placement requirements for special IPs like PLLs, PHYs, OTP | OPEN
| memory placement - rams and roms placement | OPEN
IOs | IO ring: core PG pads, analog PG pads, signal GPIOs, breaker cells (voltage islands) | OPEN
| Crystal pad placement | OPEN
| ESD protection clamps / circuitry for core PG | OPEN
| ESD protection clamp for hard IP | OPEN
| OTP / fuse programing pads and routing meeting resistance requirements | OPEN
power gating | power domains and distribution | OPEN
| ESD protection methodology for each power domain | OPEN
| power switch distribution and placement | OPEN
| all enable signals are connected to proper clamps - always ON cells | OPEN
| all power gating control signals are connected to always ON cells | OPEN
| placement of level shifters | OPEN
| polarity of level shifter hook up | OPEN
| level shifter adequacy check - reports - cross check against layout | OPEN
power analysis | power distribution scheme on the chip including PG IOs, PG mesh, metal layers | OPEN
| std cell PG hook up - robust vias to PG mesh | OPEN
| power hook up to hard IP - in correct layers, widths and vias | OPEN
| power hook up to memories - vias dropped and distributed evenly | OPEN
| power hook up to specialty / analog IP like PLL - layers, widths, vias | OPEN
| spot check on power vias for size - at mesh/mesh intersection, at std-cell rail mesh intersection | OPEN
| cross-check top 5 - 10 worst EM spots from EM report vs layout | OPEN
| cross-check top 5 -10 worst IR spots from IR drop functional reports vs layout | OPEN
| cross-check top 5 -10 worst IR spots from IR drop scan mode reports vs layout | OPEN
| cross-check extracted grid accuracy vs layout (if any methodology involves manual checks) | OPEN
misc. | spare cell placement and distribution | OPEN
| Filler cell distribution - CAP fillers, non CAP fillers; report of % of CAP fillers as % of std cell | OPEN
| Tie hi / low methodology. Spot check some tie connections for tie cells, fanout, length of wires and vias | OPEN
| double via / redundant via check - report for % vias changed - spot check | OPEN
| End CAP cells - visual check | OPEN
| Antenna prevention methodology on primary inputs of a digital PnR block and interface to analog blocks | OPEN
| scan chain - spot check sanity of the scan chain after re-ordering or re-partitioning | OPEN
post PnR
RDL /bumps /fill | RDL distribution - visually check adequate vias to power grid - specially at 45 degrees routes | OPEN
| bumps - enough vias to the grid | OPEN
| no critical analog circuitry directly under bump | OPEN
| metal fill - spot check - if floating or tied to VSS - verify that it matches STA methodology. | OPEN
| How is chip /rev ID implemented?. Can the ID be changed in the same layer(s) which are used for the metal ECO? | OPEN
Clocks
CTS | CTS topology for each clock synthesized | OPEN
| cross check vs the sdc (constraints) that all clocks are accounted for | OPEN
| Types of cells used for clock tree - BUF / INV. All cells CK (balanced) type? | OPEN
| Only single Vt used in clock tree? ensure | OPEN
| placement of CTS elements showing they are not clustered together | OPEN
| CTS non default rules to avoid cross talk - spot check at random for spacing, layers and vias | OPEN
| shielding for each clock - % of clock shielded - spot check | OPEN
| shielding for each clock - scan for adequate taps to ground | OPEN
| report from tool showing clock, # of sinks, # of CTS cells, skew, insertion delay | OPEN
| Highlight the Clock tree for top fastest clocks and visually scan for any potential glitch possibilities | OPEN
synchronizers | Visually check synchronizer flop placement, interconnects and clock connections | OPEN
HFNS | Reset tree and high fanout nets | OPEN
| report from tool showing clock, # of sinks, # of HFNS cells, skew, insertion delay | OPEN
custom clocks | review any hand routed / custom clocks - width, spacing, vias, shielding, topology etc. | OPEN
| clocks to specialized IP - meet jitter and duty cycle requirements | OPEN
Waivers
DRC waivers | Highlight requested waivers on layout and get justification for waiving them. | OPEN
Other waivers | Justify on layout that violation is unfixable and also OK to waive - mainly on Hard IP. | OPEN
GDS & foundry
GDS | Check that the latest IP releases were used for GDS merge and physical verification. Document list with rev # | OPEN
Foundry | Double check that foundry is not adding any unproven test structures in the scribe lane. | OPEN
Note: | If the layout if hierarchical and has multiple PnR blocks / partitions - some of the checks should be done on each of the partition to check for consistency. | OPEN
Apple Confidential - Do not duplicate

## Die fact sheet
<Project Name> Die Fact Sheet |  |  |  |  | Legend
Current
[5 empty] | Final | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
|  |  | DESIGN STATISTICS: |  |  | Effort | Risk | Readiness
|  |  | Die Size (X µ X Y µ) | including scribe (X µ x Y µ) | 2092.200 x 2386.416
|  |  | (post shrink, if applicable) | scribe size (X µ x Y µ) | TSMC is adding scribe
|  |  |  | without scribe (X µ x Y µ) | 2077.800 x 2372.016
|  |  | Total Cells | # of std cell instances | 661709 / 230950
|  |  | Total flops | # of Flops | 32597
|  |  |  | # of scannable flops | 31012
|  |  | Total latches | # of latches | 603
|  |  | Total TRT | # transistors in design | To be communicated till 25/04/19
|  |  | Vt count | % of HVt, RVt, LVt std Cells | 84.52 / 14.33 / 1.15
|  |  | Spare gates | # / total % of std cells area | 2435 / 1.82%
|  |  | DECAP cells | # / total % of std cells area | 247963 / 190%
|  |  | Memories | Memory Count (# of instances) | N/A
|  |  |  | Total RAM (Bytes) | N/A
|  |  |  | Total ROM (Bytes) | N/A
|  |  | IP | # of Mixed-Signal hard IP | 15
|  |  | Area | Area of std cells / utilization | 230950 / 32.6 %
|  |  |  | Area of flops | 46380
|  |  |  | Area of memories | 0
|  |  |  | Area of Hard IP | 3422691
|  |  | Power | # of Power Gated Domains | Power domains (no gating): VDDA:2, VDDH:2,VSSA:2, VDDS:2, VDDD:5, VSSD: 6, VDDPST18: 1
|  |  |  | # of Core V Domains | VDDD:5, VSSD: 6
|  |  | IOs | Total # and area | (StdIOs only) 6 / 37094um^2
|  |  |  | Power ( incl analog power) | 5 (supply) + 2 (ground)
|  |  |  | Signal (incl analog) | 4x4 (high-speed), 2x2 (low-speed link)
|  |  |  | Breaker / slot | None
|  |  |  | # IO V Domains | 1
|  |  | Clocks | # sources / frequencies | Resonator RefClk / 25 MHz CMOS RefClk 25-100 MHz
|  |  | Package | type / vendor | ASE
|  |  |  | dimensions X, Y , Z | 4 x 4 mm & 5 x 5 mm, Height max = 1.1 mm
|  |  | Bump pitch | bump size and pitch | Non-uniform, > 150 um
Technology | Process / Fab / fab location | TSMC/Taiwan
| Poly / Metal count | 1 Poly, 13 Metals including M1 | Additional comments / information:
| Metal Stack | 1P13M_2Xa1Xd_h_3Xe_vhv_2Y2Yy2R UT-AlRDL | Note : std cell statistics are for core logic only. SerDes digital will be added by 1/31/2019
| Mask Count / wafer size | To be updated till 2/25/2018
| Wafer thickness : Nominal | To be updated till 2/25/2018
| Wafer thickness Final (after thinning) | To be updated till 2/25/2018
| Test location | Taiwan
| Assembly location | Taiwan
| Max Tj ℃ | 100
Apple Confidential - Do not duplicate
Picture of Floorplan showing the blocks
&
X & Y dimensions
Note on G8: Clearly mention if the number is post shrink and the shrink factor
Note on H11: Total standard cell instances - including FILL/DECAP. - excluding FILL/DECAP
Note on H12: Total flops in the design
Note on H15: Total transistors in the design. Usually found in LVS reports
Note on H16: HVt, RVt, LVt cells as a percentage of total standard cells
Note on H24: PHYs, LDOs, PLLs, SerDes Bucks, analog IP etc.
Note on H26: in mm2 - including FILL/DECAP - excluding FILL/DECAP utilization of std cell area. From the tool PnR reports.
Note on H27: in mm2
Note on H28: in mm2
Note on H29: in mm2 -
Note on H35: Total #
Note on H40: Define source of clocks: PLL, oscillator, external crystal etc. and the operational frequencies
Note on C49: e.g. M1,Mx,My,Mz,RDL for 6LM + RDL = M1+3Mx+My+Mz+RDL

## Packaging
1 | Documentations: | [7 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Item # | Document | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F | Effort | Risk | Readiness
1.01 | GDS file of top passivation, and RDL/bump layers (if applicable) |  |  | 2019-04-25 | OPEN | John | It will be provide by the Integation team (Karsten)
1.02 | Netlist |  |  | 2019-02-28 | OPEN
1.03 | Ball map |  |  | 2019-02-28 | OPEN
1.04 | Substrate design file (mcm) |  |  | 2019-02-28 | OPEN
1.05 | Substrate/Lead frame drawing (MCM or ACAD & PDF) |  |  | 2019-02-28 | OPEN
1.06 | Wire Bonding diagram (ACAD & PDF) |  |  |  | OPEN |  | N/A
1.07 | Package Outline Drawing (ACAD & PDF) |  |  | 2019-02-28 | OPEN |  | Prelimnary version provided by OSI, currently under NDA with ASE
1.08 | Thermal simulation report (Previous same size die/package, same package attributes) |  |  | 2019-02-28 | OPEN
1.09 | Package reliability qualification reports (Previous same size die/package, same package attributes) |  |  | 2019-02-28 | OPEN
1.1 | Application Notes |  |  | 2019-02-28 | OPEN |  | Using ASE generic - TFBGA app notes
1.11 | Board level reliability test report (Previous same size die/package, same package attributes) |  |  | 2019-02-28 | OPEN
1.12 | Control Plan and Process Flow |  |  | 2019-02-28 | OPEN |  | It will be available when parts hit assembly | This item is split in v.3.2 but is retained as one for v2.9
1.13 | Bake and Dry pack specification (if not MSL 1 certified) |  |  | 2019-02-28 | OPEN |  | Assumed Prelim of MSL3 - to be confirmed after reliability test completed.
1.14 | Substrate design rule and DFM review report |  |  | 2019-02-28 | OPEN |  | ? More clarification needed
1.15 | Bonding diagram design rule and review report |  |  |  | OPEN |  | N/A, Flipchip
1.16 | Package/Assembly process risk assessment report |  |  | 2019-02-28 | OPEN |  | ASE will provide when product definition becomes firmed.
1.17 | Mechanical Stress Simulation report (Previous same size die/package, same package attributes) |  |  | 2019-02-28 | OPEN
1.18 | BOM list |  |  | 2019-02-28 | OPEN
1.19 | Carrier tape / Tray drawing (Include Fit analysis report) |  |  | 2019-02-28 | OPEN
2 | Wafer/Die Related Informations:
Item # | Silicon Related | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
2.01 | Foundry/Site | 2017-12-12 |  | 2019-02-28 | OPEN |  | TSMC/Taiwan
2.02 | Fab Silicon Technology Node (0.25nm, 0.18nm, 0.13nm, 90nm, 65nm, 55nm, 45nm, 32nm, 28 nm, etc) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 16nm
2.03 | Wafer Size (150mm, 200mm, 300mm) |  |  | 2019-02-28 | OPEN |  | 300 mm
2.04 | Silicon Substrate Crystal Orientation (include Wafer V-notch position/orientation) |  |  | 2019-02-28 | OPEN
2.05 | Number of Passivation Layers | 2017-12-12 |  | 2019-02-28 | OPEN |  | 4 layers
2.06 | Passivation Material & Thickness | 2017-12-12 |  | 2019-02-28 | OPEN |  | Polyimide, Oxid: Pass1 to Pass 4: 750+7000+12000+7000°A
2.07 | Number of Metal Layers | 2017-12-12 |  | 2019-02-28 | OPEN |  | 13 layer metal
2.08 | Total Metal Layers Thickness (M1+M2…+Mx, etc) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 700+2*700+700+3*800+2*1500+2*2600+2*11500 = 36400 °A
2.09 | Top Metal material composition and thickness | 2017-12-12 |  | 2019-02-28 | OPEN |  | Cu, 11500 °A
2.1 | Passivation opening dimension | 2017-12-12 |  | 2019-02-28 | OPEN |  | 45um
2.11 | Dielectric Material Type |  |  | 2019-02-28 | OPEN
2.12 | - Non Low-K, Low-K/Ultra Low-K | 2017-12-12 |  | 2019-02-28 | OPEN |  | ELK (extra low k) and LK, USG (undoped silica glass)
2.13 | Number of RDL Layers | 2017-12-12 |  | 2019-02-28 | OPEN |  | 1 layer | Removed in v3.2 but retained in v2..9
2.14 | RDL Layer Material | 2017-12-12 |  | 2019-02-28 | OPEN |  | Al | Removed in v3.2 but retained in v2..9
2.15 | RDL Layer Thickness | 2017-12-12 |  | 2019-02-28 | OPEN |  | 28.000 °A | Removed in v3.2 but retained in v2..9
2.16 | Die Size | 2017-12-12 |  | 2019-02-28 | OPEN |  | X: 2005.8um by Y: 2335.008um (w/o seal ring)
2.17 | Scribe Seal Ring Width | 2017-12-12 |  | 2019-02-28 | OPEN |  | Following TSMC's rules: 5.4um (Seal ring enhanced zone) + 9 um (Sealring) + 7.2um (Scribe line dummy bar)
2.18 | Scribe Lane Width |  |  | 2019-02-28 | OPEN |  | Does TSMC define it?
2.19 | Single or Double scribe? |  |  | 2019-02-28 | OPEN
2.2 | Effective Sawing Lane Width (PI or PBO free lane) |  |  | 2019-02-28 | OPEN
2.21 | Are there Circuit Under Pads (CUP)? |  |  | 2019-02-28 | OPEN |  | yes
2.22 | Die Back Side Electrical Connection Required? (VSS or VDD) |  |  | 2019-02-28 | OPEN |  | We have no backside connection VSS/VDD connection
2.23 | Flip Chip, Wire bond or WLCSP? | 2017-12-12 |  | 2019-02-28 | OPEN |  | Flip Chip
2.24 | Any Large Memory Blocks? |  |  | 2019-02-28 | OPEN |  | no
2.25 | - Memory Type? |  |  |  | OPEN |  | NI/A
2.26 | Estimated Gross Die Per Wafer (GDPW) |  |  | 2019-02-28 | OPEN
2.27 | Dummy Bumps on Empty Area (>500x500 um)? |  |  | 2019-02-28 | OPEN |  | no
2.28 | Are Bump Exclusion Zone being followed? |  |  | 2019-02-28 | OPEN |  | yes, (triangular) bump exclusion region for chip area <= 100mm^2 is 1.7*Cw, with Cw the minor axis length of UBM (82um) (1.7 * 82 = 139um)
2.29 | Distance from the Die Edge to First Bump? |  |  | 2019-02-28 | OPEN |  | 39um (x-spacing), 49.96um (y-spacing)
2.3 | Maximum Current per Bump? | 2017-12-12 |  | 2019-02-28 | OPEN |  | <30mA
2.31 | Is Daisy Chain test chip available or When it will be available? |  |  | 2019-02-28 | OPEN
3 | Package Related Information:
Item # | Flip Chip Package & Bumping Information | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
3.01 | Ground up FC design or RDL FC design? | 2018-11-08 |  |  | OPEN |  | Ground up FC design
3.02 | Does the Wafer has PI (Or other dielectric material) Layer on Top of Si-Nitride? |  |  | 2019-02-28 | OPEN
3.03 | RDL Material and Thickness (includes seed layer) | 2017-12-12 |  | 2019-02-28 | OPEN |  | Cu, 2800nm
3.04 | Wafer Bumping Supplier | 2017-12-12 |  | 2019-02-28 | OPEN |  | TSMC
3.05 | Bump Height/Diameter before Flip Chip Attach Process | 2017-12-12 |  | 2019-02-28 | OPEN |  | 60um
3.06 | Minimum Bump Pitch | 2017-12-12 |  | 2019-02-28 | OPEN |  | 153.087um (layout) / 150.025um (Si)
3.07 | Bump Count | 2017-12-12 |  | 2019-02-28 | OPEN |  | 183 bumps total
3.08 | Bump Composition | 2017-12-12 |  | 2019-02-28 | OPEN |  | Cu
3.09 | Is the Bump Material Low or Ultra-low Alpha Solder? |  |  | 2019-02-28 | OPEN |  | Not found in TSMC's documents (yet)
3.1 | PI Opening | 2017-12-12 |  | 2019-02-28 | OPEN |  | 45um
3.11 | UBM Size/Diameter | 2017-12-12 |  | 2019-02-28 | OPEN |  | 105um (x), 82um (y)
3.12 | AP Layer Pad Size and Thickness | 2017-12-12 |  | 2019-02-28 | OPEN |  | AP Pad Size: 74um, Thickness: 2800nm
3.13 | CB Opening |  |  | 2019-02-28 | OPEN |  | n/a
3.14 | CB2 Opening | 2017-12-12 |  | 2019-02-28 | OPEN |  | 55um
3.15 | Top Metal Size Under Bump |  |  | 2019-02-28 | OPEN |  | Isthis RV vias?
3.16 | UBM Layer Material Composition/Thickness/Diameter (includes seed layer) |  |  | 2019-02-28 | OPEN |  | Not found in TSM's documents (yet)
3.17 | Total Bump Density Percentage( %) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 100% density
3.18 | Substrate or Leadframe based? | 2017-12-12 |  | 2019-02-28 | OPEN |  | substrate based
3.19 | Number of Substrate Layers | 2018-11-08 |  |  | OPEN |  | 8 layers
3.2 | Core or Coreless Substrate | 2018-11-08 |  |  | OPEN |  | Cored
3.21 | Substrate Type (organic, ceramic, etc) | 2018-11-08 |  |  | OPEN |  | Organic
3.22 | Substrate Finish (CuOSP, eNiG, etc). Provide metal thicknesses |  |  | 2019-02-28 | OPEN |  | Cu/OSP finish
3.23 | Underfill material used (Capillary or MUF)? | 2018-11-08 |  |  | OPEN |  | MUF - Mold Only
3.24 | Mold compound material/thickness (if over-molded) |  |  | 2019-02-28 | OPEN |  | G311 and 250u thickness min.
3.25 | Target Laser Marking Depth (min/max) |  |  | 2019-02-28 | OPEN |  | max 35um
Wire Bond Package Information
3.26 | Single die or multi-chip module (Stack-die or Side-by-side)? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A | Wirebond is N/A for TP so v3.2 changes are not included
3.27 | Bonding Pad Ring Layout (In-line, Staggered, 3-Tiers) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.28 | Minimum Bond Pad Pitch | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.29 | Minimum Bond Pad Opening/Size | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.3 | Total Number of Bond Pads | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.31 | Bond Pad Metal Thickness | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.32 | Bond Pad Structure | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.33 | Silicon/Die thickness and Tolerance | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.34 | Wire alloy (Au, Cu, PCC, etc) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.35 | Wire diameter (um/mils) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.36 | Different wire types in same package? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.37 | Leadframe/Substrate material | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.38 | Leadframe/Substrate thickness | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.39 | Leadframe finish metal stack-up/thickness | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.4 | Mount pad or Chip on Lead configuration? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.41 | Die attach material used (material and conductivity) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.42 | Mold compound material and Mold Cap Thickness (provide thickness tolerance) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.43 | Target Laser Marking Depth (min/max) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
N/A
WLCSP Package Information
3.44 | WL Package Information (BOP, Re-passivation, RDL, others) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A | WLCSP is N/A for TP so v3.2 changes are not included
3.45 | Wafer Bumping Supplier/s and Location | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.46 | BEOL Assembly Supplier/s and Location | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.47 | RDL Design/Layout | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.48 | RDL Sputtered Seed Layer Composition/Thicknesses | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.49 | RDL Plated Layer Composition/ Final Thickness | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.5 | RDL Capture Pad size/diameter and Minimum RDL Line and Space | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.51 | Solder Ball/Bump size/diameter (before/after re-flow) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.52 | Solder Bump/Ball Pitch | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.53 | Solder Bump/Ball Count | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.54 | Solder Bump/Ball Alloy Material and Composition | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.55 | Final Silicon/Die Thickness and Tolerance | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.56 | Final Total Package/Device Height | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.57 | Passivation Material and Thickness (PI-1/PI-2 or PBO-1/PBO-2) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.58 | What is your passivation 1 minimum thickness on top of final BEOL metal layer? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.59 | What is your passivation 2 minimum thickness on top of RDL ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.6 | Passivation Material Curing temperature, and time at peak (PI-1/PI-2 or PBO-1/PBO-2) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.61 | Are you using Furnace or Box Oven or both for passivation material curing ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.62 | UBM Sputtered Seed Layer Composition/Thicknesses | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.63 | UBM Plated Layer Composition/ Final Thickness/Diameter | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.65 | Are you using Backside Film (Provide Supplier & Part Number if using BSF) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.66 | Are you using a 2-in-1 backside film ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.67 | Backside Film Thickness and Tolerance | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.68 | What is the backside film curing temperature and time ? Is it O2 free ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
N/A
Package Type Information
3.69 | Package Body/ Die Size and Tolerance |  |  | 2019-02-28 | OPEN |  |  | Multi-Die is N/A for TP so v3.2 changes are not included
3.7 | Silicon/Die Thickness and Tolerance |  |  | 2019-02-28 | OPEN |  |  | Multi-Die is N/A for TP so v3.2 changes are not included
3.71 | Total Package/Device Thickness and Tolerance |  |  | 2019-02-28 | OPEN
3.72 | Total Package/Device Bump/Pin Count | 2018-11-08 |  |  | OPEN |  | Package Ball count 81 Balls
3.73 | Bump/Ball Pitch | 2018-11-08 |  |  | OPEN |  | Package Ball pitch = 0.4mm
3.74 | Bump/Ball Matrix and Pattern | 2018-11-08 |  |  | OPEN |  | 81 Ball in 9x9 matrix pattern
3.75 | Is Die Exposed or Over-molded | 2018-11-08 |  |  | OPEN |  | Die is over molded
Package-in-Package Information
3.76 | Inner Package Information (BOP, Re-passivation, RDL, others) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A | Package-in-Package or Package-on-Package are N/A for TP so v3.2 changes are not included
3.77 | - Does the inner package have PI (Or other dielectric material) Layer on Top of Si-Nitride? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.78 | - Wafer Bumping Supplier/s and Location | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.79 | - BEOL Assembly Supplier/s and Location | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.8 | - RDL Design/Layout | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.81 | - RDL Sputtered Seed Layer Composition/Thicknesses | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.82 | - RDL Plated Layer Composition/ Final Thickness | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.83 | - RDL Capture Pad size/diameter and Minimum RDL Line and Space | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.84 | - Solder Ball/Bump size/diameter (before/after re-flow) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.85 | - Solder Bump/Ball Pitch | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.86 | - Solder Bump/Ball Count | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.87 | - Solder Bump/Ball Alloy Material and Composition | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.88 | - Final Silicon/Die Thickness and Tolerance | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.89 | - Final Total Package/Device Height | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.9 | - Passivation Material and Thickness (PI-1/PI-2 or PBO-1/PBO-2) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.91 | - What is your passivation 1 minimum thickness on top of final BEOL metal layer? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.92 | - What is your passivation 2 minimum thickness on top of RDL ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.93 | - Passivation Material Curing temperature, and time at peak (PI-1/PI-2 or PBO-1/PBO-2) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.94 | - Are you using Furnace or Box Oven or both for passivation material curing ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.95 | - UBM Sputtered Seed Layer Composition/Thicknesses | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.96 | - UBM Plated Layer Composition/ Final Thickness/Diameter | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.97 | - Are you using Backside Film (Provide Supplier & Part Number if using BSF) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.98 | - Are you using a 2-in-1 backside film ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.99 | - Backside Film Thickness and Tolerance | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.1 | - What is the backside film curing temperature and time ? Is it O2 free ? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.101 | - Is the Bump Material Low or Ultra-low Alpha Solder? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.102 | Are you using the same dicing process as standard WLCSP? Please input details in 7.16 - 7.38. | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.103 | Are you doing 100% AOI after Wafer Saw (Provide AOI Vendor/Model, Camera Magnification and Inspection Set-up/Criteria)? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.104 | Total Bump Density Percentage( %) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.105 | Substrate or Leadframe based? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.106 | Number of Substrate Layers | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.107 | Core or Coreless Substrate | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.108 | Substrate Type (organic, ceramic, etc) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.109 | Substrate Finish (CuOSP, eNiG, etc). Provide metal thicknesses | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.11 | Underfill material used (Capillary or MUF)? | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.111 | Mold compound material/thickness (if over-molded) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
3.112 | Target Laser Marking Depth (min/max) | MMDDYY | MMDDYY | MMDDYY | OPEN |  | N/A
4 | Package Qualification Related Informations:
Item # | Package Qual Plan Condition and Result Information | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
4.01 | Qual requirements must follow the latest version of " General Qualification Procedure for Integrated Circuit" (Specification number : 062-0101. Current rev AB) |  |  | 2019-02-28 | OPEN |  | Received the reference document
4.02 | Moisture Sensitivity Level (MSL) |  |  | 2019-02-28 | OPEN |  | MSL 3 will be assumed, subject to qual completion
4.03 | MSL Bake Required? |  |  | 2019-02-28 | OPEN |  | Yes, MSL 3 flow to be followed for Qual unless directed otherwise.
5 | Board Level Reliability Testing Informations:
Item # | Board Level Reliability Testing Information (For reference only) | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
5.01 | All BLRT& Qualification reuirements must follow the latest version of "Procedure for Non-product Specific BLRT and Qualification - External" (Specification number: 080-5585. Current rev F) |  |  | 2019-02-28 | OPEN |  | Received the reference document
6 | Mechanical Stress Simulation Informations:
Item # | Device/Package Mechanical Stress Analysis | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
6.01 | Mechanical Stress Simulation report/s |  |  | TBD | OPEN |  | The date will be available with Operation team plannig
Critical layers / Sensitive circuits or IP's
6.02 | PI/RDL/UBM Interface integrity (Provide High Mag FIB or SEM cross-section images) |  |  | 2019-02-28 | OPEN
6.03 | Are Bumps near or on top of Inductors? | 2017-12-12 |  | 2019-02-28 | OPEN |  | yes
6.04 | Are Bumps near or on top of Capacitors (MIM Caps, others)? | 2017-12-12 |  | 2019-02-28 | OPEN |  | yes
6.05 | Are Bumps near or on top of Resistors (Band Gap, others)? | 2017-12-12 |  | 2019-02-28 | OPEN |  | yes
6.06 | Are Bumps near or on top of Oscillators? | 2017-12-12 |  | 2019-02-28 | OPEN |  | yes
6.07 | Are corner solder balls active or dummy/redundancy exists? | 2017-12-12 |  | 2019-02-28 | OPEN |  | dummy/redundancy
7 | Wafer Bumping and Backend Assembly and Production Information:
Item # | Assembly Related | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
7.01 | Critical Assembly Process Characterization/DOE reports | 7/312018 |  | 2019-02-28 | OPEN
7.02 | Control Plan | 7/312018 |  | 2019-02-28 | OPEN
7.03 | Process Flow (FEOL & BEOL) | 7/312018 |  | 2019-02-28 | OPEN
7.04 | Automated Visual Inspection | 7/312018 |  | 2019-02-28 | OPEN
7.05 | Are you doing 100% AOI after RDL (Provide AOI Vendor/Model, Camera Magnification and Inspection Set-up/Criteria)? | 7/312018 |  | 2019-02-28 | OPEN |  | Not Applicable - This is not WLCSP
7.06 | Are you doing 100% AOI after UBM (Provide AOI Vendor/Model, Camera Magnification and Inspection Set-up/Criteria)? | 7/312018 |  | 2019-02-28 | OPEN |  | N/A
7.07 | Are you doing 100% AOI after Ball Drop (Provide AOI Vendor/Model, Camera Magnification and Inspection Set-up/Criteria)? | 7/312018 |  | 2019-02-28 | OPEN |  | N/A
7.08 | Wafer Backgrind | 7/312018 |  |  | OPEN |  | Yes -
7.09 | Wafer Backgrind process (standalone or Inline) | 7/312018 |  |  | OPEN |  | Inline
7.1 | Backgrind Z1/Z2 grinding wheels grit size | 7/312018 |  |  | OPEN |  | Normal spec: Z1#300 / Z2#2000
7.11 | Is wafer backgrind polishing used (dry/wet) ? | 7/312018 |  | 2019-02-28 | OPEN |  | No used - not WLCSP, N/A
7.12 | Laser Marking | 7/312018 |  | 2019-02-28 | OPEN |  | Mold based
7.13 | Target Laser Marking Depth (min/max) | 7/312018 |  | 2019-02-28 | OPEN |  | max 35um
7.14 | Are you marking directly on Silicon or Backside film or through Dicing tape ? | 7/312018 |  | 2019-02-28 | OPEN |  | On Mold compound
7.15 | Are you adding Die Coordinates on wafer during laser marking ? | 7/312018 |  | 2019-02-28 | OPEN |  | Special requirement for WLCSP
7.16 | Wafer Dicing Technology | 7/312018 |  | 2019-02-28 | OPEN |  | See below - 7.22
7.17 | Mechanical Saw, Laser Grooving + Mechanical Saw, Stealth Laser | 7/312018 |  |  | OPEN |  | N/A
7.18 | - Cutting Method (Single Pass, Step-cut, Double Pass, others) | 7/312018 |  |  | OPEN |  | N/A
7.19 | - Blade Type/Part number/s (Z1 & Z2) | 7/312018 |  |  | OPEN |  | N/A
7.2 | - Wafer Dicing Tape Type/Part number | 7/312018 |  |  | OPEN |  | N/A
7.21 | - Mechanical Dicing Parameters (Feed-rate, RPM, Cut Depth, Others…) | 7/312018 |  |  | OPEN |  | N/A
7.22 | Laser Groove + Mechanical Saw | 7/312018 |  |  | OPEN |  | N/A
7.23 | - Laser Beam Type (Single Narrow, Split, Dual Narrow, Dual Wide, others...) | 7/312018 |  | 2019-02-28 | OPEN |  | Normal Spec: Dual Narrow+Single Wide
7.24 | - Number of Laser Passes | 7/312018 |  | 2019-02-28 | OPEN |  | Normal spec: 3 pass (Dual Narrow x1 + Single Wide x2
7.25 | - Laser Grooving Profile/Shape | 7/312018 |  | 2019-02-28 | OPEN |  | U shape groove
7.26 | - Laser Grooving Width (Top / Bottom of grooving profile and Dimensions) | 7/312018 |  |  | OPEN |  | Depend on scribe line width
7.27 | - Laser Grooving Depth | 7/312018 |  | 2019-02-28 | OPEN |  | Normal Criteria: 10~25um
7.28 | - Laser grooving Parameters (Power, Frequency, Beam Width, Mask Width, Speed, Others…) | 7/312018 |  | 2019-02-28 | OPEN |  | Follow SPEC# 90-31-A027-0001
7.29 | - Mechanical Dicing Cutting Method (Single Pass, Step-cut, Double Pass, Others...) | 7/312018 |  | 2019-02-28 | OPEN |  | FollowSPEC # 94-31-A030-0010
7.3 | - Blade Type/Part number/s (Z1 & Z2) | 7/312018 |  | 2019-02-28 | OPEN |  | FollowSPEC # 94-31-A030-0010
7.31 | - Wafer Dicing Tape Type/Part number | 7/312018 |  |  | OPEN |  | Tape select base on Pkg type/wafer thk
7.32 | - Mechanical Dicing Parameters (Feed-rate, RPM, Cut Depth, Others…) | 7/312018 |  | 2019-02-28 | OPEN |  | FollowSPEC # 94-31-A030-0010
7.33 | Stealth Laser | 7/312018 |  |  | OPEN
7.34 | - Laser Engine Type (Low Power-SD01, 200AS, others ; High Power- SD03, SD05, SD06, 700AS, 700SP, others) | 7/312018 |  |  | OPEN |  | N/A
7.35 | - Number of Laser Passes (1, 2, 3, 4, Others...) | 7/312018 |  |  | OPEN |  | N/A
7.36 | - Stealth Laser Parameters (Power, Frequency, Speed, Z-Height, BW, Others…) | 7/312018 |  |  | OPEN |  | N/A
7.37 | - Die Separation Method (With / Without Expasion ring) | 7/312018 |  |  | OPEN |  | N/A
7.38 | - Die Separation Parameters | 7/312018 |  |  | OPEN |  | N/A
7.39 | Are you meeting the Wafer Dicing Inspection requirements specified in 080-01150 Rev A? | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A
7.4 | Are you doing 100% AOI after Wafer Saw (Provide AOI Vendor/Model, Camera Magnification and Inspection Set-up/Criteria)? | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A | Retained v2.9 description instead of v3.2/7,08 as it requires more information
7.41 | Tape and Reel process (TnR Vendor/Model, Lowest Camera Magnification ) | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A
7.42 | What is your minimum die to die distance after stretching/before pickup ? | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A
7.43 | How many inspection stations are in the TnR process ? | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A
Production Related
7.31 | Capacity | 7/312018 |  | TBD | OPEN |  | The date will be available with Operation team plannig | Retained equivalent v2.9 descrition instead of v3.2/7,50
7.32 | Production History and Yield report (Similar Package/Device) | 7/312018 |  | TBD | OPEN |  | The date will be available with Operation team plannig | Retained v2.9 description instead of v3.2/7,51 as it requires more information
7.33 | Qualified Packaging Assemlby House/s | 7/312018 |  | TBD | OPEN |  | The date will be available with Operation team plannig
8 | Thermal Simulation Informations:
Item # | Package/Device Thermal Information | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
8.01 | Max Power (W) |  | 2017-12-12 | 2019-02-28 | OPEN |  | 580mW
8.02 | Power Map |  |  | 2019-02-28 | OPEN |  | In progress
8.03 | Ambient temp |  | 2017-12-12 | 2019-02-28 | OPEN |  | 0 -65C
8.04 | Device Grade (Ambient temperature allowed) |  |  | 2019-02-28 | OPEN |  | KB will provide Delphi CTM or 2R CTM to Seeb
8.05 | Air Flow (m/s) |  | 2017-12-12 | 2019-02-28 | OPEN |  | 0 m/s
8.06 | Maximum allowed operation junction temp |  | 2017-12-12 | 2019-02-28 | OPEN |  | 100C
8.07 | External HS required? |  | 2017-12-12 |  | OPEN |  | N/A
8.08 | PCB board layer count |  | 2017-12-12 | 2019-02-28 | OPEN |  | As defined in JESD51
8.09 | Maximum allowed HS size (XY, height) |  | 2017-12-12 |  | OPEN |  | N/A
8.10 | Thermal interface material requirement for HS |  | 2017-12-12 |  | OPEN |  | N/A
8.11 | Number of power cycle on/off per week |  |  | 2019-02-28 | OPEN
8.12 | Expected life in years |  |  | 2019-02-28 | OPEN
Package/Device Thermal Performance
| Air velocity | Tj, max °C | Tcase, °C | θja, °C/W | θjb, °C/W | Ψjc, °C/W
| 0 | 78.625 | 78.508 | 24.2759 | 13.1205 | 0.20855
| 0.508 | 77.2398 | 77.0986 | 22.0179 | 13.0908 | 0.25587
| 1.016 | 76.768 | 76.6078 | 21.2892 | 13.0669 | 0.29055
| 2.032 | 76.3698 | 76.1835 | 20.6132 | 13.0328 | 0.33782
9 | Package Risk Assessment
Item # | Risk | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name | JAN'19 F2F
9.01 | Have any other devices used this package in production? |  |  | 2019-02-28 | OPEN |  | Capacitors for SBU interface
9.02 | Estimated volume shipped with this package (None,<1Mu,10Mu,100Mu,1Bu+)? |  |  | 2019-02-28 | OPEN |  | Has to be checked with contacted vendor
9.03 | Overall Packaging Risk Level (High/Medium/Low)? |  |  | 2019-02-28 | OPEN |  | Medium
9.04 | Is a new supplier/factory being used for Wafer Bumping or Assembly? |  |  | 2019-02-28 | OPEN |  | No
9.05 | Will a packaging learning cycle build be performed? |  |  | 2019-02-28 | OPEN |  | Not likely but Can confirm after BOM list and package attributes are established | Retained v2.9 description instead of v3.2/9,05 as difference is negligible
9.06 | Has another device in this package passed 062-0101 rev AB qual requirements? |  |  | 2019-02-28 | OPEN
9.07 | Has similar device/daisy-chain in this package passed 080-5585 rev F BLR requirements? |  |  | 2019-02-28 | OPEN
9.08 | Are there any new processes, equipment, direct/indirect materials being used? |  |  | 2019-02-28 | OPEN |  | No
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
1 | Documentations:
Item # | Document | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name
1.2 | Substrate technology and process flow ( v3.2/1,16) |  | MMDDYY | MMDDYY | OPEN
1.21 | Package Layer stack-up diagram, layer thicknesses/dimensions (v3.2/1,19) | MMDDYY | MMDDYY | MMDDYY | OPEN
1.22 | CPI (Chip to Package Interaction) Study (v3.2/1,20) | MMDDYY | MMDDYY | MMDDYY | OPEN
2 | Wafer/Die Related Informations:
Item # | Silicon Related | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name
2.16 | Die Size (without SR, with SR, with SR + Kerf) (v3.2/2,20) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 28.000 °A
2.19 | - Single Scribe Lane or Double Scribe Lanes? (Provide dimension if double or more in one or both channels)? (v3.2/2,23) |  |  | 2019-02-28 | OPEN
2.2 | Effective Sawing Lane Width ( if PI/PBO terminates beyond the Scribe Seal Ring; Provide PI or PBO free lane width)? (v3.2/2,24) |  |  | 2019-02-28 | OPEN
2.23 | What will be the intended Package type (Flip Chip, Wire bond, WLCSP, others…)? (v3.2/2,28) | 2017-12-12 |  | 2019-02-28 | OPEN |  | Flip Chip
2.29 | Distance from the Die Edge to nearest Bump? (Or distance from Die Edge to center of nearest UBM/Bump) (v3.2/2,34) |  |  | 2019-02-28 | OPEN |  | 39um (x-spacing), 49.96um (y-spacing)
2.32 | Scribe Seal Ring design and Scribe lane details (provide x-sectional diagram with dimensions) (v3.2/2,13) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.33 | Number of Seal Rings (AP) (v3.2/2,13) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.34 | - If more than 1, are they electrically connected? (v3.2/2,14) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.35 | - If more than 1, distance between both (v3.2/2,16) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.36 | Thickness of top metal layer (AP) in the seal ring? (v3.2/2,17) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.37 | Is there a passivation trench/opening outside the SR or inside the SR? If yes, define location and dimensions? (v3.2/2,18) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.38 | PBO/PI layers termination near Scribe Seal ring (at inner side or ouside?). Provide detailed discription with x-sectional schematic and dimensions. (v3.2/2,19) | MMDDYY | MMDDYY | MMDDYY | OPEN
2.39 | Are TEG/PCM/Alignment markers centered or off-centered in the Scribe lane? If off centered, provide details and dimensions of offset from center and distance from Seal Ring. (v3.2/2,25) | MMDDYY | MMDDYY | MMDDYY | OPEN
3 | Package Related Information:
Item # | Flip Chip Package & Bumping Information | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name
3.04 | Wafer Bumping Supplier & Location? (v3.2/3,04) | 2017-12-12 |  | 2019-02-28 | OPEN |  | TSMC
3.08 | What is the Bump Composition and Bumping Process used (Electro-plated, Printed, others…)? (v3.2/3,08) | 2017-12-12 |  | 2019-02-28 | OPEN |  | Cu
3.11 | What is the UBM Size/Diameter and Thickness? (v3.2/3,11) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 105um (x), 82um (y)
3.13 | What is the CB Opening (Octagon, Circular, others…)? Minimum size? (v3.2/3,13) |  |  | 2019-02-28 | OPEN |  | n/a
3.14 | What is the CB2 Opening (Octagon, Circular, others…)? Minimum size? (v3.2/3,14) | 2017-12-12 |  | 2019-02-28 | OPEN |  | 55um
3.16 | UBM Layer Material Composition and Thickness (includes seed layer) (v3.2/3,16) |  |  | 2019-02-28 | OPEN |  | Not found in TSM's documents (yet)
3.18 | Is this a Laminate Substrate or Leadframe based Flip Chip Package? (v3.2/3,18) | 2017-12-12 |  | 2019-02-28 | OPEN |  | substrate based
3.22 | What is the Substrate Finish (Cu-OSP, ENIG, ENIPEG, others...)? Provide thickness of the different material layers. (v3.2/3,22) |  |  | 2019-02-28 | OPEN |  | Cu/OSP finish
3.23 | Is Underfill material used (Capillary or MUF type)? Provide Supplier and Part number. (v3.2/3,23) | 2018-11-08 |  |  | OPEN |  | MUF - Mold Only
3.24 | Will it be Over-molded? Provided Mold compound material Supplier and Part number. Provide Mold Cap thickness. (v3.2/3,24) |  |  | 2019-02-28 | OPEN |  | G311 and 250u thickness min.
3.113 | BGA Solder Ball material and diameter ? (v3.2/3,25) | MMDDYY | MMDDYY | MMDDYY | OPEN
3.114 | Substrate Pad size/diameter and SRO size? (v3.2/3,26) | MMDDYY | MMDDYY | MMDDYY | OPEN
3.115 | Do you have electrical die level traceability capability (die X-Y coordiante in a wafer)? (v3.2/3,28) | MMDDYY | MMDDYY | MMDDYY | OPEN
3.116 | Do you have physuical die level traceability capability ( X-Y coordinate added on the laser marking)? (v3.2/3,29) | MMDDYY | MMDDYY | MMDDYY | OPEN
7 | Wafer Bumping and Backend Assembly and Production Information:
Item # | Assembly Related | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name
7.04 | Automated Visual Inspection | 7/312018 |  | 2019-02-28 | OPEN
7.44 | - Are you doing 100% AOI during Tape and Reel (Provide Camera Magnification for all inspection stations and Inspection Set-up/Criteria)? (v3.2/7,09) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.08 | Wafer Backgrind | 7/312018 |  |  | OPEN |  | Yes -
7.45 | - What is the Z2 fine grind removal amount? (v3.2/7,12) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.46 | - What is final wafer backside roughness (Ra, Rt and Rmax) post backgrind? (v3.2/7,13) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.16 | Wafer Dicing Technology | 7/312018 |  | 2019-02-28 | OPEN |  | See below - 7.22
7.21 | - Provide Mechanical Dicing Parameters (Sawing Speed/Feed-rate, Spindle RPM, Cut Depth, Alignment frequency, Target Blade life, Others…) (v3.2/7,23) | 7/312018 |  |  | OPEN |  | N/A
7.39 | Are you meeting the Wafer Dicing Inspection requirements specified in Automated Optical Inspection Requirements for Integrated Circuit Packaging (080-01150 Rev B)? (v3.2/7,41) | 7/312018 |  |  | OPEN |  | Not WLCSP, N/A
7.47 | If using more than one OSAT for BE-Assembly. Provide tool matchnig documentation (tool type, process parameters, materials (blade type, grind wheel, tapes, others...). (v3.2/7,42) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.48 | What is the post bump and post saw AOI inspection guardband outside the final termination layer (SR, PI/PBO, others...)? (v3.2/7,43) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.49 | Tape and Reel Process | MMDDYY | MMDDYY | MMDDYY | OPEN
7.5 | - Is the TnR being used has capability to do 6-sides Inspection (By Optical, IR, others…)? (v3.2/7,48) | MMDDYY | MMDDYY | MMDDYY | OPEN
7.51 | - What is your push up tool design and material? (v3.2/7,49) | MMDDYY | MMDDYY | MMDDYY | OPEN
9 | Package Risk Assessment
Item # | Risk | Kick-off Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments, Radar Number and File Name
9.06 | Has another device in this package passed 062-0101 rev AC qual requirements? (v3.2/9,06) |  |  | 2019-02-28 | OPEN
9.07 | Has similar device/daisy-chain in this package passed 080-5585 rev H BLR requirements? (v3.2/9,07) |  |  | 2019-02-28 | OPEN
Note on D4: Raymundo Camenforte: If already available for initial review.
Note on D5: Raymundo Camenforte: If already available for initial review.
Note on E8: Raymundo Camenforte: If already finalized and available for initial review.
Note on D10: Raymundo Camenforte: If already available for initial review.
Note on D11: Raymundo Camenforte: If already available for initial review.
Note on D12: Raymundo Camenforte: If already available for initial review.
Note on D13: Raymundo Camenforte: If already available for initial review.
Note on D14: Raymundo Camenforte: If already available for initial review.
Note on D15: Raymundo Camenforte: If already available for initial review.
Note on D19: Raymundo Camenforte: If already available for initial review.
Note on D20: Raymundo Camenforte: If already available for initial review.
Note on D21: Raymundo Camenforte: If already available for initial review.
Note on D61: Raymundo Camenforte: If already available for initial review.
Note on D62: Raymundo Camenforte: If already available for initial review.
Note on D69: Raymundo Camenforte: If already available for initial review.
Note on D73: Raymundo Camenforte: If already available for initial review.
Note on D75: Raymundo Camenforte: If already available for initial review.
Note on D76: Raymundo Camenforte: If already available for initial review.
Note on D79: Raymundo Camenforte: If already available for initial review.
Note on D80: Raymundo Camenforte: If already available for initial review.
Note on D81: Raymundo Camenforte: If already available for initial review.
Note on D82: Raymundo Camenforte: If already available for initial review.
Note on D83: Raymundo Camenforte: If already available for initial review.
Note on D84: Raymundo Camenforte: If already available for initial review.
Note on D85: Raymundo Camenforte: If already available for initial review.
Note on D134: Raymundo Camenforte: If already available for initial review.
Note on D135: Raymundo Camenforte: If already available for initial review.
Note on D136: Raymundo Camenforte: If already available for initial review.
Note on D137: Raymundo Camenforte: If already available for initial review.
Note on D138: Raymundo Camenforte: If already available for initial review.
Note on D139: Raymundo Camenforte: If already available for initial review.
Note on D140: Raymundo Camenforte: If already available for initial review.
Note on D184: Raymundo Camenforte: If already available for initial review.
Note on D185: Raymundo Camenforte: If already available for initial review.
Note on C190: e.g. for BLR-Drop Test Test condition: 10,000G peak accelation; 0.25ms pulse duration Reference Spec: JESD22-B104C Sample size / criteria : 11 components each from 3 assembly lots ; 0F/33 Failure criteria : Test up to 18 drops or until all parts fail Notes: 1. BLR-Drop and BLR-TC test to be done on parts with and without underfill (To use Apple qualified reworkable underfill material 2. BLR-Drop: Report number of drops for the first 5% and 63.2% of the population failure e.g. for BLR-TC Test Test condition: - 40 to 85 C, 30 minutes per cycle Reference Spec: JESD22-A104A Sample size / criteria : 11 components each from 3 assembly lots ; 0F/33 Failure criteria: Test up to 1000 cycles or until all parts fail Notes: 1. BLR-Drop and BLR-TC test to be done on parts with and without underfill (To use Apple qualified reworkable underfill material
Note on D196: Raymundo Camenforte: If already available for initial review.
Note on C210: Raymundo Camenforte: For similar package type, body/die size.
Note on D210: Raymundo Camenforte: If already available for initial review.
Note on C211: Raymundo Camenforte: For similar package type, body/die size.
Note on D211: Raymundo Camenforte: If already available for initial review.
Note on C212: Raymundo Camenforte: For similar package type, body/die size.
Note on D212: Raymundo Camenforte: If already available for initial review.
Note on D213: Raymundo Camenforte: If already available for initial review.
Note on D214: Raymundo Camenforte: If already available for initial review.
Note on D215: Raymundo Camenforte: If already available for initial review.
Note on D216: Raymundo Camenforte: If already available for initial review.
Note on D217: Raymundo Camenforte: If already available for initial review.
Note on D218: Raymundo Camenforte: If already available for initial review.
Note on D219: Raymundo Camenforte: If already available for initial review.
Note on D220: Raymundo Camenforte: If already available for initial review.
Note on D221: Raymundo Camenforte: If already available for initial review.
Note on D222: Raymundo Camenforte: If already available for initial review.
Note on D223: Raymundo Camenforte: If already available for initial review.
Note on D224: Raymundo Camenforte: If already available for initial review.
Note on D225: Raymundo Camenforte: If already available for initial review.
Note on D226: Raymundo Camenforte: If already available for initial review.
Note on D227: Raymundo Camenforte: If already available for initial review.
Note on D228: Raymundo Camenforte: If already available for initial review.
Note on D229: Raymundo Camenforte: If already available for initial review.
Note on D230: Raymundo Camenforte: If already available for initial review.
Note on D231: Raymundo Camenforte: If already available for initial review.
Note on D232: Raymundo Camenforte: If already available for initial review.
Note on D233: Raymundo Camenforte: If already available for initial review.
Note on D234: Raymundo Camenforte: If already available for initial review.
Note on D235: Raymundo Camenforte: If already available for initial review.
Note on D236: Raymundo Camenforte: If already available for initial review.
Note on D237: Raymundo Camenforte: If already available for initial review.
Note on D238: Raymundo Camenforte: If already available for initial review.
Note on D239: Raymundo Camenforte: If already available for initial review.
Note on D240: Raymundo Camenforte: If already available for initial review.
Note on D241: Raymundo Camenforte: If already available for initial review.
Note on D242: Raymundo Camenforte: If already available for initial review.
Note on D243: Raymundo Camenforte: If already available for initial review.
Note on D244: Raymundo Camenforte: If already available for initial review.
Note on D245: Raymundo Camenforte: If already available for initial review.
Note on D246: Raymundo Camenforte: If already available for initial review.
Note on D247: Raymundo Camenforte: If already available for initial review.
Note on D248: Raymundo Camenforte: If already available for initial review.
Note on D249: Raymundo Camenforte: If already available for initial review.
Note on D250: Raymundo Camenforte: If already available for initial review.
Note on D251: Raymundo Camenforte: If already available for initial review.
Note on D252: Raymundo Camenforte: If already available for initial review.
Note on D255: Raymundo Camenforte: If already available for initial review.
Note on D256: Raymundo Camenforte: If already available for initial review.
Note on D257: Raymundo Camenforte: If already available for initial review.
Note on E265: Raymundo Camenforte: If already available for initial review.
Note on E267: Raymundo Camenforte: If already available for initial review.
Note on E274: Raymundo Camenforte: If already available for initial review.
Note on E275: Raymundo Camenforte: If already available for initial review.
Note on D290: Raymundo Camenforte: If already available for initial review.
Note on D291: Raymundo Camenforte: If already available for initial review.
Note on D292: Raymundo Camenforte: If already available for initial review.
Note on D293: Raymundo Camenforte: If already available for initial review.
Note on D294: Raymundo Camenforte: If already available for initial review.
Note on D295: Raymundo Camenforte: If already available for initial review.
Note on D296: Raymundo Camenforte: If already available for initial review.
Note on D297: Raymundo Camenforte: If already available for initial review.
Note on E308: Raymundo Camenforte: If already finalized and available for initial review.
Note on D309: Raymundo Camenforte: If report is avaialble for simialar size die or package type.
Note on D310: Raymundo Camenforte: If report is avaialble for simialar size die or package type.
Note on D333: Raymundo Camenforte: If already available for initial review.
Note on D335: Raymundo Camenforte: If already available for initial review.
Note on D337: Raymundo Camenforte: If already available for initial review.
Note on D338: Raymundo Camenforte: If already available for initial review.
Note on D339: Raymundo Camenforte: If already available for initial review.
Note on D347: Raymundo Camenforte: If already available for initial review.
Note on D349: Raymundo Camenforte: If already available for initial review.
Note on D352: Raymundo Camenforte: If already available for initial review.
Note on D353: Raymundo Camenforte: If already available for initial review.
Note on D354: Raymundo Camenforte: If already available for initial review.
Note on D363: Raymundo Camenforte: If already available for initial review.
Note on D364: Raymundo Camenforte: If already available for initial review.

## Process
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions | JAN'19 F2F | Deliverables | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Process Technology | 1.01 | Provide the base technology node, lithography and class (CMOS/BiCMOS/BCDMOS etc) | 2017-12-15 |  | 2019-02-28 | OPEN | Anant / Frank | 1P13M_2Xa1Xd+I2:I37_h_3Xe_vhv_2Y2Yy2R UT-AlRDL,RF option, CMOS |  |  | Effort | Risk | Readiness
| 1.02 | Provide a brief process flow inclduing masking layers |  |  | 2019-02-28 | OPEN |  | Working with Open Silicon to provide
| 1.03 | Provide the device list and voltage ranges associated with each (inclduing passives) | 2017-12-15 |  | 2019-02-28 | OPEN |  | SVT, LVT, ULVT + Material on DVS
| 1.04 | Provide details of the Foundry, Fab(s) and locations |  |  | 2019-02-28 | OPEN |  | Fab 14, TSMC, Tianan, Taiwan
| 1.05 | Provide details of wafer size |  |  | 2019-02-28 | OPEN |  | 12 inch (300 mm)
| 1.06 | Have there been any supply interruptions or yield excursions as a result of semiconductor manufacturing of this process |  |  | 2019-02-28 | OPEN |  | TBD under investigation
| 1.07 | Are all open process items closed and the process confirmed ready for MP |  |  | MMDDYY | OPEN |  | Using Standard process technology, no changes to the process flow, will continue to monitor
| 1.08 | How many substrate vendors are planned for each fab/foundry? |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
| 1.09 | For any non internal foundry complete 3-way NDA for the process technology and foundry(s) applicable | 2017-12-15 |  |  | OPEN |  | NDA signed | removed in v3.2 but retained in v2.9
Special Components | 2.01 | Provide NVM technology(s) used | MMDDYY |  |  | OPEN |  | N/A
| 2.02 | Provide ECC and Redudnace plans for NVM (ECC or differential cell is required for all OTP). This does not remove the retention/bake requirements for EEPROM and eFlash | MMDDYY |  |  | OPEN |  | N/A
| 2.03 | Provide details of SRAMS and other Volatile memory. What SER concerns and mitigtion plans are there | MMDDYY |  |  | OPEN |  | N/A
| 2.04 | Provide HCl, BVdss, Electrical and Thermal SOA for all HV devices and overlay transient use condition wave forms. Any violation requires Apple approval and can trigger additional reliability constraints and testing. |  |  | 2019-02-28 | OPEN |  | N/A - No High Voltage devices used
| 2.05 | For any devices exceeding / possibly exceeding and SOA boundry provide data confirming rleiablity and aging under planned use consitions |  |  | 2019-02-28 | OPEN |  | TBD
PDK | 3.01 | Provide details of PDK maturity including version number and orginal V1.0 release date | 2017-12-15 |  | 2019-02-28 | OPEN |  | v1.0_2p1a 2016/09/30
| 3.02 | Provide SPICE models vs. Si data over volume for key components | MMDDYY |  | 2019-02-28 | OPEN |  | Requested from TSMC
Process Maturity | 4.01 | Has this process been used by your company for any released products | 2017-12-15 |  |  | OPEN |  | Yes, 16 nm, not this metal stack
| 4.02 | Has the process been used in other Apple programs - if so provide details | 2017-12-15 |  |  | OPEN |  | Not with Kandou
| 4.03 | How long has the process been released to manufacturing |  |  |  | OPEN |  | TBD in discussion with Open Silicon TSMC
| 4.04 | How many wafers have shipped in total post release |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon TSMC
| 4.05 | Is there a plan to add additional capacity for this program |  |  | 2019-02-28 | OPEN |  | None
| 4.06 | Are all devices used in this product monitored by scribe line structures |  |  | 2019-02-28 | OPEN |  | Using TSMC GIGAFAB 14 capacity
| 4.07 | Provide in-line and E-Test (WAT) targets, limits and operational CpK data |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon and TSMC
| 4.08 | Identify ANY process steps that rely on a single fab tool |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon and TSMC
| 4.09 | Describe any safe launch plans for a new process or new process component/device |  |  | 2019-02-28 | OPEN |  | Safe Start Specification drafted and under development
| 4.1 | Specifically identify any in-line or parametric test CpK data <1.3 or >3 and identify corrective action or provide explanation to waive |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
| 4.11 | Provide foundry or fab data confirming all in-line process and WAT E-Test paramters are in-spec and meet above CpK requirement |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
| 4.12 | Complete 3-way Maufacturability Robustness Review with Apple and Foundry (or 2-way if internal fab) or obtain Apple waiver |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
| 4.13 | Provide Instrinsic Process Qualification data for device sizes and styles used in this program |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
Process Modifications | 5.01 | Are there ANY changes/modifications to the process or device list for this program no matter how minor | 2017-12-15 |  |  | OPEN |  | No
| 5.02 | Are there are previously not used components that will be used in this program | 2017-12-15 |  |  | OPEN |  | No
| 5.03 | Are there any changes to the PDK | 2017-12-15 |  | 2019-02-28 | OPEN |  | No
| 5.04 | Are there ANY areas considered medium or high risk with this process for this product | 2017-12-15 |  |  | OPEN |  | No
| 5.05 | Are there any new scribe line monitor devices for this product | 2017-12-15 |  |  | OPEN |  | No
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Process Technology | 1.02 | Provide a brief process flow including masking layers. State if BEOL is Aluminum with Tungsten Vias, or Copper (v3.2/1,02) |  |  | 2019-02-28 | OPEN |  | Working with Open Silicon to provide
| 1.08 | List all substrate vendors that are planned for each fab/foundry (v3.2/1,09) |  |  | 2019-02-28 | OPEN |  | TBD in discussion with Open Silicon & TSMC
| 1.1 | Confirm that all poly is automatically doped by rule (v3.2/1,03) | MMDDYY |  |  | OPEN
Note on C15: For circuit operating conditions where devices exceed their voltage rating or SOA provide data to confirm reliabity of the deive in that operating condition and aging data.

## TE_v3p2
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
[10 empty] | Effort | Risk | Readiness
Category | Item # | Checklist Item/Concern | KickOff Review Date | Post TO | Pre MP | Status | DRI | Comments/Questions | Deliverables
Design Phase | 1.01 | ATE Production Test Plan | MMDDYY | MMDDYY | MMDDYY | OPEN
| 1.01.1 | Test Stage Process | MMDDYY |  |  | OPEN
| 1.01.2 | Test Items Sequential Order In Test Program | MMDDYY | MMDDYY | MMDDYY | OPEN
| 1.01.3 | Test Program Detail Summary List |  | MMDDYY | MMDDYY | OPEN
| 1.01.4 | Coverage Table Including Coverage Summary per Items/Functions/% |  | MMDDYY | MMDDYY | OPEN
| 1.02 | ATE Test and Test Development Strategy and Flow | MMDDYY |  |  | OPEN
| 1.02.1 | Test Development Strategy | MMDDYY |  |  | OPEN
| 1.02.2 | Test Platform and Instrumentation | MMDDYY |  |  | OPEN
| 1.02.3 | Test Program Development Phases and Definitions | MMDDYY |  |  | OPEN
| 1.02.4 | Risk Assessment and Mitigation Plan | MMDDYY | MMDDYY |  | OPEN
| 1.03 | Production Test Program Revision Control, Release Process | MMDDYY |  |  | OPEN
| 1.04 | Trim Plan | MMDDYY | MMDDYY |  | OPEN
| 1.05 | ATE HW Documentation |  | MMDDYY |  | OPEN
| 1.06 | ATE Characterization Plan |  | MMDDYY |  | OPEN
| 1.07 | Test Insertion Correlation Plan |  | MMDDYY
| 1.08 | Test HW debugging |  | MMDDYY |  | OPEN
TO Phase | 2.01 | Test program readiness for initial bring-up |  | MMDDYY |  | OPEN
| 2.01.1 | Test HW readiness: validation results |  | MMDDYY |  | OPEN
| 2.02 | Reliability HW Status Check (HTOL Board/Socket, HAST Board/Socket) |  | MMDDYY |  | OPEN
| 2.03 | ATE Characterization Test Program Status |  | MMDDYY |  | OPEN
ES Phase | 3.01 | Verification: No Risk of Inducing EOS during Test |  | MMDDYY | MMDDYY | OPEN
| 3.02 | Qual Test Program Summary |  | MMDDYY | MMDDYY | OPEN
| 3.03 | HVS Development |  | MMDDYY | MMDDYY | OPEN
| 3.04 | Production HW Test implementation |  | MMDDYY | MMDDYY | OPEN
Pre-MP Phase | 4.01 | eQA Program Status |  |  | MMDDYY | OPEN
| 4.02 | SBL/SBC Establishment Status |  |  | MMDDYY | OPEN
| 4.03 | MP Test Program Release Readiness Check |  |  | MMDDYY | OPEN
| 4.03.1 | Test Plan Updated |  |  | MMDDYY | OPEN
| 4.03.2 | Test Final Coverage And Conditions Reviewed |  |  | MMDDYY | OPEN
| 4.03.3 | Test Limit With Final Guardbands Implemented |  |  | MMDDYY | OPEN
Apple Confidential - Do not duplicate
|  | This tab is new in v3.2 version of the checklist and is imported into the augmented v2.9 checklist, named v2.9+ | [5 empty] | This tab is new in v3.2 version of the checklist and is imported into the augmented v2.9 checklist, named v2.9+
Note on E3: One week after TO
Note on F3: 6 weeks before MP
Note on C4: Test plan should be updated at each milestone and checkpoint to reflect the test program
Note on C5: Details test device test flow, for example: Bump → Wafer Sort → Assembly → FT → FQA ...
Note on C6: for example: Continuity → Power Short → IO → HVS → IDDQ, …
Note on C7: Include the followingsfor for all test stages: * item * Temperature * Desciptions * Test/Measurement Method * Test Conditions * Test Specificaitons: datasheet spec and ATE limits
Note on C8: Structural test converages; comparison between ATE parametric test converage and ERS/DS, note the reason for any discreepancy
Note on C10: * Test list/coverage definition process * Test method definition process * Test implementation, test program developement process: automation, structure, library, modulalization *
Note on C15: Trim Parameter list; Trim Algorithm/Flow/Steps
Note on C16: Schedule; Schematics; Validation plan
Note on C17: Should include all items in production test; List all additional char items, and measurement/test methods Also includes Temperature ranges and corner ranges
Note on C18: Correlation among tests at all stages all the way to Bench correlation
Note on C19: Design/Layout Check
Note on C21: List the status of each item in the test plan; Highlight differences if any between DS spec and ATE limits, if any guardbands included
Note on C24: List char program implementation status against the char plan
Note on C26: Check for any voltage spikes
Note on C27: Coverage Default Test guardband Detail description
Note on C28: HVS Evaluation plan and Qualification plan, HVS conditons, duration, coverage, pass/fail criteria. HVS screen failure rate goal and actual
Note on C29: HW connectivity and component tests/diagnoses program/process implementation and coverage, inline and manual
Note on C31: AQL Goal 0.065% or tighter
Note on C32: Control limit default at 3<sigma>
Note on C33: Per established checklist and available lesson learned
Note on C35: Test Coverage Goal: 100% Test Fault Coverage Goal: 100%
Note on C36: Including Reliability guardband

## Qualification
| Note: | Tape-Out/Pre-Qual Period = TO and before Qual starts; | [7 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
|  | Qual/Post Qual Period = During Qual, before MP starts | [7 empty] | Effort | Risk | Readiness
Category | Item # | Checklist Item/Concern | KickOff Review Date | Tape Out/Pre-Qual Period | Qual/Post Qual Period | Status | DRI | Comments/Questions | Deliverables
Qualification Plan | 1.01 | List all items from latest Qual requirement that need discussion/approval. | 2019-12-31 |  |  | OPEN | Frank | Working on material. BLRT requires clarification and discussion. Reduction of multiple package scenarios e.g. asssembly sites, substrate vendors and package size. Quality and reliability lead to be hired Q1'19
| 1.02 | Provide lifetime calcuations to show HTOL conditions can meet use case requirement |  | 28/2/2019 |  | OPEN |  | Under review
| 1.03 | Provide the process technology qualification data/report. Highlight any sensitive/critical parameters that require close monitoring. |  | 28/2/2019 |  | OPEN |  | In discussion with Open Silicon
| 1.04 | Provide locations of Rel stress labs, Qual FT, FA lab |  | 28/2/2019 | TBD | OPEN |  | Mapping out with Open Silicon for A0-A1. Currently hiring Quality & Reliability resource to transfer thought leadership from Open Silicon to KB.
| 1.05 | List all probing pads with metal + active circuits under them (CUP) |  | 28/2/2019 |  | OPEN |  | Working with KB Design Engineering for handover to Ops.
| 1.06 | List the Pkg BOM/Design rule changes from previous generation of device | 2018-07-31 |  |  | OPEN |  | N/A, this is the first generation of device.
| 1.07 | List all DRC + Antenna waivers (same as PD checklist) |  | 28/2/2019 | TBD | OPEN |  | Working with KB Design Engineering for handover to Ops.
| 1.08 | Provide qual pkg information, if it is different than MP pkg |  | 28/2/2019 | TBD | OPEN |  | Under review
| 1.08.1 | By default, no underfill (UF) for qualification unless otherwise specified. |  | 28/2/2019 | TBD |  |  | Under review
| 1.09 | Provide notification + 8D/FA report for any and all qual failures, even if failures are not induced by rel stresses. |  | 28/2/2019 | TBD | OPEN |  | Post Tape-Out activity, working through planning assumptions
| 1.1 | Provide/add specific rel stresses that is unique to the product under qual. |  | 28/2/2019 |  | OPEN |  | Under review
| 1.11 | Qual lots should be from POR flow only. All control/spec, in-line data/inspection must be in spec for each and every data point. |  | 28/2/2019 |  | OPEN |  | Under review
| 1.12 | Prior to TO, provide finalized lookahead Qual schedule for review and approval for items specified in section 6. |  |  |  | OPEN |  | In discussion with Open Silicon
| 1.13 | List and describe any special process or package that required additional independent process Qual besides regular product Qual. For example, TSV process module. And, provide its corresponding Qual report for review. |  | 28/2/2019 |  | OPEN |  | Under review
HTOL/BHAST Schmatics/ Harware Setups | 2.01 | Provide HTOL + BHAST schematic for review and apporval including information of BIB/socket, carrier board, coupon/daughter boards, sockets design plus its associated SMT soldering process/methodology (WLCSP must be SMT mounted on PCB/DC/Coupon for TMCL at a minimum). |  | 28/2/2019 |  | OPEN |  | Under review with Open Silicon
| 2.01.1 | How was Tj measured for HTOL? | 2018-07-31 | 28/2/2019 |  | OPEN |  | Power Measurements are done on a Fully populated Burn-In Board in the with patterns running at 5-10MHz. The current drawn per supply is recorded at different oven temperatures (Ta) and Vdd accelerations and used to calculate the total power dissipation per device (P). Knowing the package thermal resistance (Θja) the Final HTOL Vdd & Temp is set such that the device junction termp (Tj) does not exceed 125C: Tj = Ta + Θja*P
| 2.02 | Provide HTOL vectors toggle coverage summary |  | 28/2/2019 |  | OPEN
| 2.03 | Provide validation report of HTOL vectors on ATE under HTOL conditions |  | 28/2/2019 |  | OPEN
| 2.04 | Provide HTOL + bHAST checkout sheet to demonstrate the BIB/Sockets been checked with functional units |  | 28/2/2019 |  | OPEN
| 2.05 | Provide a copy of SOP of Qual samples handling |  | 28/2/2019 |  | OPEN |  | TBD. Should include packing requirements. Trays are preferred for initial bring up and qual material. Working wth Open Silicon to finalise approach
| 2.06 | Show evidence of reference units included in qual population for T0 and each read point |  | 28/2/2019 |  | OPEN
| 2.07 | Provide HW capacity plan to be reviewed andfor approval including Oven, BIB, Sockets, ESD/LU tester, etc. |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon for A0-A1 silicon
| 2.08 | Provide evidence of verification of waveforms and voltage/current spikes analysis (scope shots) |  | 28/2/2019 |  | OPEN
Qual Units Traceability | 3.01 | Provide details of qual lots traceability. |  | 28/2/2019 | TBD | OPEN |  | All units used will be assembled, marked and tracked as "Qual Material" at Assembly with special engineering handling. Will be marked as engineering material as defined by the product marking specification. Material used for testing will be logged. Engaged with ASE to develop die level traceabilty.
| 3.02 | Provide evidence of Qual units can be traced back to wafer location level with Die ID (X, Y coordinate) and/or location on an PKG assembly strip | 2018-07-31 | 28/2/2019 | TBD | OPEN |  | ASE has indicated that they can support the wafer location tracking as well as strip location tracking. We can work out the details of how this is managed later. This is limited to qual lots only. This is being discussed as part of overall solution for production traceabilty. ASE woking on providing solution.
| 3.03 | Provide Qual units assembly in-line data record report |  | 28/2/2019 | TBD | OPEN
| 3.04 | Qual material need to be stored under controlled environment for minimum one full year post Qual |  | 28/2/2019 | TBD | OPEN |  | Requires further clarification
| 3.05 | Qual data and all related reports to be documented with traceability for minimum of 5 years |  | 28/2/2019 | TBD | OPEN
|  |  | 2018-07-31 | 28/2/2019 | TBD |  |  | Working with Open Silicon and transfering to KB Ops
Qulalifcation Program /Test Coverage | 4.01 | To confirm test program for Qual as the frozen final test program with spec for MP. If not, needs to provide gap analysis report including test/fault coverage, test guardband for review and approval |  | 28/2/2019 |  | OPEN |  | Hiring Production Test lead 19-Nov, finalo production test approach TBD.
| 4.02 | Provide a DVS validation report to confirme stress voltage + duration are safe on ATE/ or bench |  | 28/2/2019
| 4.03 | Provide test program coverage summary for Qual |  | 28/2/2019 | TBD | OPEN
| 4.04 | Show test guardband limits vs. data sheet limits |  | 28/2/2019 | TBD | OPEN
| 4.05 | Provide evaluation + notification of any O/S or gross failure due to die crack during FT |  | 28/2/2019 | TBD | OPEN
| 4.06 | Provide an analysis report of any leakge/continuity failure at FT (suspected) may due to ESD/EOS |  | 28/2/2019 | TBD | OPEN
| 4.07 | Document and notifiy when any rel stress readpoin failed to meet JEDEC test window requirement |  | 28/2/2019 | TBD | OPEN
| 4.08 | Continue on Fail (COF) for Qual material initial/readout test |  | 28/2/2019 | TBD | OPEN
| 4.09 | Bin reading values in test datalog needed besides pass/fail |  | 28/2/2019 | TBD | OPEN
| 4.1 | Products with ECC must report qual results with ECC on and ECC off. |  | 28/2/2019 | TBD | OPEN
Post Qualification Activities | 5.01 | Provide FA reports with root cause identification for each and every qual failure |  |  | TBD | OPEN
| 5.02 | Provide a drift analaysis report for all critial parameters, for all reliability stresses. |  |  | TBD | OPEN
| 5.02.1 | Example of drift analysis points (HTOL): Probe->T0->T168->T500->T1000 |  |  | TBD | OPEN
| 5.03 | Provide a final qual report with clear risk assessment, including FIT + DPPM |  |  | TBD | OPEN
| 5.04 | Provide final test program version detail and final test guardband indicating whether or how much for reliability consideration |  |  | TBD | OPEN
| 5.05 | Provide an ORM Plan |  |  | TBD | OPEN |  | Will be provided in accordance with customer requirements
Look ahead Qualification Activities | 6.01 | First article BI boards available (8 weeks after TO) |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon to provide
| 6.02 | Qual ES , blind build, in qual pkg avaiable (~10 days after first ES, if qual pkg is different than initial blind ES ) |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon to provide
| 6.03 | Look ahead Qual ATE program contents and test fault coverage available (4 weeks after first ES for lookahead qual) |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon to provide
| 6.04 | Look ahead qual start (4 weeks after first ES for lookahead qual) |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon to provide
| 6.05 | Both look ahead lot + first qual lot's HBM + CDM must be stressed to failure or 3x minimum spec. levels, whichever is lower, for margin to failure check. |  | 28/2/2019 |  | OPEN |  | Working wioth Open Silicon to provide
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
Qualification Plan | 1.14 | Confirm DFR and DFT to be simulated/analyzed during design phase to ensure Stress and test capability per Qual spec 062-0101 requirement (v3.2/1,14) | MMDDYY | MMDDYY |  | OPEN
| 1.15 | Confirm Qual plan to be compliant with Apple Qual spec 062-0101 (v3.2/1,15) | MMDDYY | MMDDYY |  | OPEN
| 1.16 | Any deviation or QBS from Qual spec 062-0101 needs to be proposed with supporting evidence and approved is writing in advance during design phase (v3.2/1,16) | MMDDYY | MMDDYY |  | OPEN
| 1.17 | QBS needs to include process change record and package information (v3.2/1,17) | MMDDYY | MMDDYY |  | OPEN
| 1.18 | Process change record and related reliability qual data/result for the process technology to be used by the product of interest (v3.2/1,18) | MMDDYY | MMDDYY |  | OPEN
| 1.19 | In case ERS requirement topped Qual requirement 062-0101, ERS supercedes Qual spec unless otherwise negotiated and approved (v3.2/1,19) | MMDDYY | MMDDYY |  | OPEN
HTOL/BHAST Schmatics/ Harware Setups | 2.08 | Provide evidence of verification of waveforms and voltage/current spikes analysis (scope shots) in oven in room temp and high temp as for HTOL (v3.2/2,08) |  | 28/2/2019 |  | OPEN
Qulalifcation Program /Test Coverage | 4.11 | Test detail datalog turned on for Qual and ES materials with bins/parameters reading values recorded for analysis and traceability (v3.2/4,11) |  | MMDDYY
Note on C4: Provide a list of exceptions/waivers requests that require discussion. Close all outstanding items, including qual schedules before qual starts.
Note on C5: Show Vuse, Vstress, Voltage Accleration (Gamma) + Tuse, Tstress, Activation Energy. Use case life time = ?
Note on C6: Must use proper criteria for WLR tests. Example: HCI should be Vdd + 10%, 0.2yr (DC) with <10% Idsat degradation @ 0.1% cum.
Note on C7: Just the locations for now. A list of capabilities of each labs may be needed at a later dates.
Note on C8: Need to make sure all probe pads had been labled correctly and checked with currect DRC rules
Note on C9: For pkg qual QBS
Note on C10: Show a link/radar # of DRC/Antenna rules waivers
Note on C11: For recalcuating Tj for MP pkg, if it is different than Qual pkg.
Note on C12: Use of UF for qualification units must be approved in advance and only in specified stress to prevent/limit performance enhancing effects, intentional or otherwise.
Note on C13: All failures occur during qual must be disclosed, including spare units. All discounts must be accepted by Apple
Note on C14: Non-standard Si, such as MEM or COG may required Rel stresses no in Apple's existing requirement. Please discuss the appropriate stresses for any unique product with us.
Note on C15: Do not use average or mean values to determine spec compliance.
Note on C16: goal to have BIB available 8wks post TO and to start lookahead BI in a month post FO using ATE program version by then
Note on C20: Include all bias conditions + current/fuse rating for each PS/socket.
Note on C21: With a thermal couple or on die thermal sensor? Or ???
Note on C22: Show % of toggle coverage for each functional block. MBIS should be 100%.
Note on C23: Verify HTOL vectors will run at HTOL conditions on ATE. Find the voltage level, temperature level where vectors will no longer function
Note on C24: Show current draw fo each PS: 1) empty board 2) with only 1 unit 3) fully loaded Show Power up/down sequence Show Tc at room + during stress for Show wave forms of monitored outputs
Note on C30: WAT/PCM, lot/sub-lot history. CP yield + failure Pareto FT T0 yield + failure Pareto
Note on C32: Include assembly yield + failure Pareto for all steps.
Note on C36: Record of bins test list and limits need to be provided
Note on C37: DVS = Dynamic Voltage Screen, or voltage bump is required to reduce IM dppm.
Note on C38: Show qual program coverage vs. SCM For speed sensitive products, show Vccmin coverage
Note on C39: Provide a copy of SCM showing locked Qual, FT vs. DS and their corresponding guardband for test/tester variation and lifetime guardband post HTOL 1000 hours
Note on C41: Include ATE transient analysis results.
Note on C45: Any NVM/memory filaure with ECC turned off shall be isolated down to bit cell level for PFA. Official qual results can be reported with ECC turned on, provided ECC turn off results had been fully disclosed/PFA completed.
Note on C48: Detect any parametric drift as a result of T0 sample preperation i.e. re-package into a qual specific package. Example of T0 qual testing where parametric drfits may be detected: 1)Final package test (if applicable) 2)Post preconditioning (if applicable) 3)Post SMT to coupon board (if applicable)
Note on C49: Use agreed to voltage + temperature accleration factors + HTOL conditions to calculate FIT + DPPM @ 60% confidence level
Note on C50: ORM = On Going Reliability Monitoring. Include plan for scrap + storage of post stressed units. +Procedure of ORM failure notification. + Cumulative FIT + DPPM updates
Note on C53: Minimum qty. should be sufficient to run 1 HTOL lot (77).
Note on C54: Can use SHL material for look ahead qual. Purpose.
Note on C55: Look ahead qual program coverage negotiable. Must be able to detect gross failure mode + all I/O leakages
Note on C56: 24hrs + 168hrs read points minimum.
Note on C57: Look ahead lot and first qual lot are both required as they can have different level of test coverages.
Note on C67: Conduct circuit level aging simulation per required voltage supplies condition of 1.2xVccMax to ensure DfR/DfT

## PTE
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Post TO | Pre MP | Status | DRI | Comments/Questions | Deliverables | Effort | Risk | Readiness
Test Development | 1.01 | Provide Test Plan | 30-11-2018 | 2019-06-30 |  | OPEN | Frank | Test plan in development with OSI and KB Test Development team. KB Operations Test starting Nov-18
| 1.02 | Provide Test delopment flow | 2019-02-28 | 2019-06-30 |  | OPEN |  | Test plan in development with OSI and KB Test Development team. KB Operations Test starting Nov-18
2019-06-30
Program | 2.01 | Final test Program ( sample, OTP ) and its summary including test fault coverage and guardband |  | 2019-06-30 | TBD | OPEN |  | Test plan in development with OSI and KB Test Development team. KB Operations Test starting Nov-18
| 2.02 | Char Program |  | 2019-06-30 |  | OPEN |  | With KB test development
| 2.03 | Qual program and its summary report as comparison to Final test program |  | 2019-06-30 |  | OPEN |  | Test development and TE. Ops Test Engineering resource joining Nov-18
2019-06-30
Characterization | 3.01 | List the material flow used for Char | 30-11-2018 | 2019-06-30 |  | OPEN
| 3.02 | List the package type used for char | 30-11-2018 | 2019-06-30 |  | OPEN |  | Package type will be the same
| 3.03 | List char temperatures | 2019-02-28 | 2019-06-30 |  | OPEN
| 3.04 | Provide the data analysis |  | 2019-06-30 |  | OPEN
Repeatability & Reproducibility | 4.01 | Provide the R&R methodology | 2019-02-28 |  |  | OPEN |  | Gage R&R methodology - Ops Test Engineering resource joining Nov-18
| 4.02 | R&R Plan for all test sites |  | 2019-06-30 |  | OPEN |  | Ops Test Engineering resource joining Nov-18
| 4.03 | Report GR&R Report |  |  | TBD | OPEN |  | Ops Test Engineering resource joining Nov-18
Correlation | 5.01 | List the Wafer Sort & Package test sites | 2019-02-28 |  |  | OPEN |  | ASECL & ASEK
| 5.02 | Provide the Correlation plan include methodology & schedule |  | 2019-06-30 |  | OPEN |  | Ops Test Engineering resource joining Nov-18
| 5.03 | Report Correlation Report |  |  | TBD | OPEN |  | TBD Ops Test Engineering
GuardBand & Final Limit | 6.01 | Provide methodology used to determine Guardband | 2019-02-28 |  |  | OPEN |  | TBD Ops Test Engineering
| 6.02 | Report GuardBand result |  |  | TBD | OPEN |  | TBD Ops Test Engineering
| 6.03 | Report final limit |  |  | TBD | OPEN |  | TBD Ops Test Engineering
Yield Check | 7.01 | Report the bin yields of the first 3 MP (Mass Production) wafer lot/Fab ( wafer sort ) |  |  | TBD | OPEN |  | TBD Ops Test Engineering
| 7.02 | Report the yields of the first 3 assembly lot/asembly site ( Package) from MP |  |  | TBD | OPEN |  | TBD Ops Test Engineering
Apple Confidential - Do not duplicate
New or updated checklist items from v3.2 of Silicon Checklist
GuardBand & Final Limit | 6.03 | Provide a comparison table showing final ATE limits Vs. DS+SCM+GB limits (v3.2/6,03 PE tab) |  |  | TBD | OPEN |  | TBD Ops Test Engineering
Note on E3: One week after TO
Note on F3: 6 weeks before MP
Note on C4: Include QA program coverage, Char program coverage, Final test program coverage
Note on C5: Please include estimated cycle time.
Note on C7: Provide the sample program with datasheet limit +OTP.
Note on C8: contain all the voltage, temperatures for char programs.
Note on C9: Contain all the critical parametric test
Note on C11: If any change , please post after Tapeout. Fab, assembly, test sites.
Note on C12: If the package is different from the final package. Please list the difference of the programs.
Note on C13: Base on datasheet
Note on C14: Test limit & CPK. All the CPK should be >1.33. Bivariate analysis, if need!
Note on C17: Include schedule
Note on C18: Mean, Stdv, CPK on each site
Note on F18: Before release the HW & SW to product site
Note on C23: Wafer sort; < 1% yield between development and Production site. All the fail bin should be the same. Package: one lot ( at least 1Kunits ). All the fail bin should be the same. <1% yield
Note on F23: Before release the HW & SW to product site
Note on C26: The CPK for all the production test parameters should be >1.33.
Note on F26: Before start the MP
Note on F27: Before start the MP
Note on F39: Before start the MP

## Additional Requests
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions | Deliverables | Effort | Risk | Readiness
Additional Requested Items | 1.01 |  |  |  |  | OPEN
| 1.02 |  |  |  |  | OPEN
| 1.03 |  |  |  |  | OPEN
| 1.04 |  |  |  |  | OPEN
MISC. | 2.01 |  |  |  |  | OPEN
| 2.02 |  |  |  |  | OPEN
| 2.03 |  |  |  |  | OPEN
| 2.04 |  |  |  |  | OPEN
Apple Confidential - Do not duplicate

## ECO update
[10 empty] | lo=1:hi=5 | lo=1:hi=5 | ready=2: wait T/O=1
Category | Item # | Checklist Item/Concern | KickOff Review Date | Mid-term Review Date | Final Review Date | Status | DRI | Comments/Questions | Deliverables | Effort | Risk | Readiness
Design | 1.01 | List of delta design changes from previous version (if applicable) |  |  | MMDDYY | OPEN
RTL | 2.01 | RTL review of blocks that changed (Diff with previous version) |  |  | MMDDYY | OPEN
| 2.02 | RTL complete milestone |  |  | MMDDYY | OPEN
| 2.03 | RTL diff logs |  |  | MMDDYY | OPEN
CDC | 2.01 | Review any changes to CDC |  |  | MMDDYY | OPEN
DV | 3.01 | Verification plan update |  |  | MMDDYY | OPEN
| 3.02 | Functional Coverage - All RTL tests must be re-run and changes documented |  |  | MMDDYY | OPEN
| 3.03 | Code Coverage - re-generate coverage reports with changes documented |  |  | MMDDYY | OPEN
| 3.04 | Mixed Signal Simulations - All tests must be re-run and changes documented |  |  | MMDDYY | OPEN
| 3.05 | Gate-level simulations (Max, Min, Typ) - All tests must be re-run, changes documented |  |  | MMDDYY | OPEN
| 3.06 | Verify Revision ID register |  |  | MMDDYY | OPEN
Synthesis | 4.01 | Review any changes to synthesis constraints |  |  | MMDDYY | OPEN
DFT | 5.01 | DFT coverage review |  |  | MMDDYY | OPEN
5.02
STA | 6.01 | Timing report review for all corners and clock domains |  |  | MMDDYY | OPEN
| 6.02 | LEC: RTL <-> final netlist |  |  |  | OPEN
PD | 7.01 | LVS report review |  |  | MMDDYY | OPEN
| 7.02 | ERC/DRC report review |  |  | MMDDYY | OPEN
| 7.03 | LVL |  |  | MMDDYY | OPEN
| 7.04 | Method for differentiating between old and updated masks |  |  | MMDDYY | OPEN
| 7.05 | Vendor tape out checklist |  |  | MMDDYY | OPEN
Apple Confidential - Do not duplicate
Note on C28: At final: * vendor needs to provide a method by which they will differentiate between the old mask and the new mask for any layer which has been updated and ensure that the old mask does not accidently find its way into the fabrication. This method could include: - having a visual die ID updated on the layout for each layer that changed. - a bar code system to differentiate and track the masks. - physically pull out the old masks from the fab - any other method which is reliable

## SCM Template
| Note that this tab contains a template for the SCM format that is required for verification by simulation and validation of silicon. |  |  | GBSPC = Guarenteed By Statistical Process Controls. GBD = Guarenteed By Design | DATASHEET (TEMP) |  |  |  |  | VERIFICATION METHOD | BACK ANNOTATED | SIMULATION RESULTS | [7 empty] | LAB-TO-ATE CORRELATION |  |  | SILICON BENCH EVALUATION AND CHARACTERIZATION RESULTS | [7 empty] | ATE CHARACTERIZATION RESULTS (HISTOGRAMS OVER PVT)
| SYMBOL | PARAMETER | UNIT | TEST CONDITIONS | MIN | TYP | MAX | ATE / GBSPC / EVAL / GBD | COMMENTS | Transistor-level simulation, AMS, ATE, lab evaluation | (Yes/No) | MIN | MEAN | MAX | SIGMA | SIMULATION LEVEL (PVT/RCX/MC) | SPEC COMPLIANCE? | DATE COMPLETE | COMMENTS | ATE | LAB | ATE REPEATABILITY | # UNITS TESTED | MEAN | SIGMA | MIN | MAX | SPEC COMPLIANCE? | DATE COMPLETE | COMMENTS | MEAN | SIGMA | MIN | MAX | CPK+ | CPK- | ATE TEMP RANGE | SPEC COMPLIANCE GUARANTEED BY SPC? | DATE COMPLETE | COMMENTS
not started | System Performance
issue | IDDQ_STBY | Standby supply current | uA |  |  |  | 2 | GBSPC | [8 empty] | YES |  |  |  |  | YES | [15 empty] | YES
done | IDDQ | Dynamic operating supple current | mA |  |  | TBD |  | EVAL | Component specs: COUT1 = TDK ……, L = Toko…… | [7 empty] | YES |  |  |  |  | YES | [15 empty] | TBD
not started | VUVLO_TH+ | UVLO threshold (rising supply) | V |  |  | 2.5 |  | GBD
not started | VUVLO_HYST | UVLO hysteresis | mV |  |  | 100 |  | GBD
not started | Buck Converter Performance
not started | VOUT1 | Buck output voltage accuracy (VOUT1 = 1.00V) | mV | Initial accuracy, 25C | N/A |  | N/A
|  |  |  | Temperature variation | -4.6 |  | 4.6 | GBSPC | [8 empty] | YES |  |  |  |  | YES | [15 empty] | NO
|  |  |  | Line regualtion (3.4V < VDD_MAIN < 4.6V) | -2.3 |  | 2.3 | GBSPC
|  |  |  | DC load regulation (1mA < ILOAD < IMAX, Auto mode) | -22 |  | 22 | GBSPC | Component specs: COUT1 = TDK ……, L = Toko……
|  |  |  | Load transient response (1mA < ILOAD < IMAX, Auto mode, COUT1 = 22uF, L = 1uH) | -20 |  |  | EVAL | Component specs: COUT1 = TDK ……, L = Toko……
|  |  |  | Static output ripple voltage (1mA load, Auto mode, COUT1 = 22uF, L = 1uH) |  | 10 | 15 | EVAL | Component specs: COUT1 = TDK ……, L = Toko……
not started | fSW | Switching Frequency | MHz |  | 2.7 | 3 | 3.3 | GBSPC
not started | tON | Turn on time | ms |  |  | 1 |  | GBSPC
not started | tOFF | Turn off time | ms |  |  | 1 |  | GBSPC
not started | LDO Performance
not started | VOUT2 | LDO output voltage accuracy (VOUT2 = 3.3V) | mV | Initial accuracy, 25C | N/A |  | N/A
|  |  |  | Temperature variation | -66 |  | 66 | GBSPC
|  |  |  | Line regualtion (3.4V < VDD_MAIN < 4.6V) | -5 |  | 5 | GBSPC
|  |  |  | DC load regulation (1mA < ILOAD < IMAX, Auto mode) | -33 |  | 0 | GBSPC | Component specs: COUT2 = TDK ……
|  |  |  | Load transient response (1mA < ILOAD < IMAX, COUT2 = 2,2uF) | -33 |  |  | EVAL | Component specs: COUT2 = TDK ……
not started | Logic Interface Characteristics
not started | VIL | Input Low Level | V |  |  |  | 0.4 | GBSPC
not started | VIH | Input High Level | V |  | 1.25 |  |  | GBSPC
not started | II | Input Current | mA |  | -1 |  | 1 | GBSPC
not started | VOL | Output Low Level | V | ISDA = 3 mA |  | 0.3 | 0.5 | GBSPC
not started | IO | Output Leakage | mA | VSDA = 2.8V |  |  | 1 | GBSPC
Apple Confidential - Do not duplicate